## Cover
ALLEGATO A.4 — INTERFACE CONTROL DOCUMENT (ICD) v1.0
Documento | Allegato A.4 — Interface Control Document (ICD) preliminare v1.0
Progetto | Studio di Fattibilità HALE/VTOL — Firmamento Technologies
Bando | Cooding Prototypes (Coopfond / Legacoop)
Volume | Volume 2 — Allegati tecnici
Versione | v1.0 (M+3 baseline, post-Allineamento Strategico Maggio 2026)
Data | 2026-05-17
Status | Preliminary (concept-level + preliminary spec)
Conformità metodologica | ARP4754A (System Development); ISO/IEC/IEEE 24765:2017 (SE Vocabulary); NASA SE Handbook §6.3 (Interface Mgmt)
Conformità procedurale IT | D.Lgs. 36/2023 art. 41 + Allegato I.7 (PFTE - Relazione Tecnica)
Numero interfacce | 50 interfacce dettagliate, 8 categorie
Owner documento | Senior Systems Engineer (Firmamento) + Integration Engineer Lead
Boundary conditions | B1 (modello service-only cooperative); B2 (visione 10 anni EU sovereign HAPS)
Disciplina epistemica | Skill epistemic-rigor: confidence levels + falsifying observations per interfacce critiche (≥ 5)
Riferimento padre | Cap. 4 §4.4 (ICD preliminare 20 interfacce primarie); Cap. 6 (architettura)
Riferimento agenti | avionics-gnc; telecom-ntn-payload; aerodynamics-structures; earth-observation
Note | L'ICD è preliminary, NON engineering-grade. Specifiche byte-level e latency end-to-end deferite a Phase A/B Detailed ICD.

## All_Interfaces
ID | Nome | Tipo | Parte A | Parte B | Direzione | Standard di riferimento | Owner | Test Method | Status | Confidence
INT-6A-PHY-001 | Airframe VTOL ↔ Modular Payload Bay | Fisica meccanica | VTOL Airframe (JOUAV CW-30E o eq.) | Payload Module (EO/IR/telecom) | Bidirezionale (statica) | MIL-STD-810H §514.8 (vibration); ISO 9022-2:2016 (mechanical mounting); vendor-specific dovetail mount | Avionics Integration Lead (Firmamento) + JOUAV Liaison | Inspection + analisi CG calc + shake table test | Preliminary | medium
INT-6A-PHY-002 | Payload Power Rail 28 VDC | Fisica elettrica | VTOL Power Distribution Unit (PDU) | Payload Module (load fino a 100 W) | Unidirezionale (PDU → Payload) | MIL-STD-704F (aircraft electrical power); DO-160G §16 (Power Input); MIL-STD-1377 (28 VDC) | Power Management SE + Avionics Lead | Lab bench test + transient injection + load step | Preliminary | high
INT-6A-PHY-003 | Payload Data Port Ethernet | Fisica elettrica + dati | Payload Module (camera/sensor) | Mission Computer (MC) VTOL | Bidirezionale full-duplex | IEEE 802.3 (Ethernet); IEEE 802.3at (PoE+); ANSI/TIA-568 (cabling) | Avionics Lead + Payload SE | Cable certification (Fluke DSX) + ping test + throughput iPerf3 | Preliminary | high
INT-6A-PHY-004 | Ground Antenna Mount (parabolica 1.2 m) | Fisica meccanica | GS fissa Pentema (container) | Antenna parabolica RF 2.4 GHz | Statica (mount) | EIA-222-H (structural standards for steel antenna supports); IEC 60721 (environmental conditions) | RF Systems Engineer + Civil Works Lead | Inspection + load calc + alignment test | Preliminary | high
INT-6A-PHY-005 | Airborne RF Antenna Whip (2.4 GHz) | Fisica meccanica + RF | VTOL airframe (ventral) | Whip antenna 5 dBi omni vertical polarization | Bidirezionale (RF) | MIL-STD-348B (RF connectors); MIL-C-39012 (SMA family) | RF Systems Engineer | VNA sweep (VSWR + gain pattern) + range test | Preliminary | medium
INT-6A-PHY-006 | Battery Pack ↔ Power Distribution (LiPo 6S 22.2V) | Fisica elettrica | Battery Pack 6S LiPo 22.2V 16000 mAh (≈ 356 Wh) | Power Distribution Unit (PDU) | Unidirezionale (Bat → PDU) + telemetry (BMS → MC) | RTCA DO-311A (Rechargeable Lithium Battery); UN 38.3 (transport); IEC 62133 (safety) | Power Management SE + Battery Specialist | Capacity test + thermal runaway test + cycle test | Preliminary | high
INT-6A-PHY-007 | Thermal Interface Payload-Airframe | Fisica termica | Payload (heat generation 50-100 W) | Airframe (heat sink, ambient air) | Unidirezionale (heat flow) | DO-160G §4 (Temperature); MIL-STD-810H §501.7 (High Temp), §502.7 (Low Temp) | Thermal Engineer + Payload SE | Thermal vacuum chamber test (per HALE) + thermal cycle (per VTOL) | Preliminary | medium
INT-6A-PHY-008 | VTOL Landing Gear ↔ Helipad Surface | Fisica meccanica | VTOL landing gear (skid o quad) | Helipad/touchdown surface (Pentema/mobile) | Contatto meccanico transitorio | FAA AC 150/5390-2D (Heliport Design); EASA CS-HPT (Heliport Design Manual) — applicabile per drone heliports | Operations Lead + Civil Works | Site survey + load calc + landing test | Concept | high
INT-6A-PHY-009 | GS Power Supply (230 VAC mains) | Fisica elettrica | Rete elettrica Pentema (Enel Distribuzione) | GS fissa container + GS mobile veicolo | Unidirezionale (mains → GS) | CEI 64-8 (impianti elettrici utilizzatori); IEC 61000-4 (EMC immunity) | Civil Works Lead + IT Operations | Load test + outage simulation + UPS autonomy test | Concept | medium
INT-6A-PHY-010 | Backhaul Internet Connection (GS → Cloud) | Fisica + dati | GS fissa Pentema | Backhaul WAN (FWA Linkem/Open Fiber/Starlink) | Bidirezionale | ITU-T G.983 (PON); IEEE 802.3ah (Ethernet First Mile); 3GPP TS 23.501 (5G architecture) | IT Operations + Cloud Architect | iPerf3 throughput + ping latency + outage test | Concept | medium
INT-6A-DATA-001 | Payload EO RGB → Mission Computer | Funzionale data | Camera Phase One iXM 100 (100 MP, 11608×8708 px) | Mission Computer (MC) airborne | Unidirezionale (Camera → MC) | GigE Vision 2.1 (AIA standard); GenICam 3.x; NTP v4 RFC 5905; PPS NMEA 0183 | Payload SE + Avionics Lead | Image capture test + geotag accuracy verification + throughput test | Preliminary | high
INT-6A-DATA-002 | Payload IR LWIR → Mission Computer | Funzionale data | Camera termica FLIR Vue Pro R / WIRIS Pro (640×512 px LWIR 7.5-13.5 μm) | Mission Computer airborne | Unidirezionale | USB 3.0 specification; FLIR Atlas SDK; ASTM E1862-97 (IR camera calibration) | Payload SE | Radiometric accuracy test (calibrazione blackbody) + frame rate verification | Preliminary | high
INT-6A-DATA-003 | Mission Data Storage (onboard NVMe SSD) | Funzionale data | Mission Computer (MC) | NVMe SSD storage 2 TB ruggedized (industrial) | Bidirezionale (R/W) | NVMe 1.4 specification; PCIe Gen3 (PCI-SIG) | Avionics Lead + Mission Computer SE | Throughput benchmark + power-off recovery + thermal cycling | Preliminary | high
INT-6A-DATA-004 | Mission Data Upload GS → Cloud | Funzionale data | GS post-flight ingest (NVMe rimovibile o WiFi 6) | Cloud Object Storage (S3-compatible, Aruba/OVH) | Unidirezionale (GS → Cloud) | AWS S3 API v4; TLS 1.3 RFC 8446; Tus.io resumable upload spec | Cloud Architect + DevOps | Upload time vs object size benchmark + interrupted resume test | Preliminary | high
INT-6A-DATA-005 | Telemetry Real-time Stream (UAV → GS) | Funzionale data | VTOL FCS (Flight Computer System) | GS Telemetry Dashboard (operator UI) | Unidirezionale (UAV → GS) | MAVLink Protocol v2.0 (Dronecode); AES-256-GCM (NIST SP 800-38D) | Avionics Lead + GCS UX Developer | Packet capture + decode + latency measurement (link tester) | Preliminary | high
INT-6A-DATA-006 | Video Downlink Preview (Low-bitrate) | Funzionale data | Payload EO RGB (preview pipeline) | GS Operator Display | Unidirezionale (UAV → GS) | ITU-T H.265 / ISO/IEC 23008-2 (HEVC); RFC 3550 (RTP); RFC 7826 (RTSP 2.0) | Payload SE + GCS Developer | Latency measurement (timestamp injection) + decoder compatibility test | Preliminary | medium
INT-6A-DATA-007 | Photogrammetry Pipeline (Cloud) | Funzionale data | Cloud Object Storage (raw images) | Photogrammetry Engine (Pix4D/Agisoft/OpenDroneMap) | Bidirezionale | OGC GeoTIFF; ASPRS LAS 1.4; EXIF 2.32; OGC WMTS | GIS Engineer + Cloud Architect | Pipeline test end-to-end + output validation | Preliminary | medium
INT-6A-DATA-008 | Audit Log + Operational Telemetry → SIEM | Funzionale data + sicurezza | GS + Cloud + Mission Computer (log producers) | SIEM (Security Information & Event Management) | Unidirezionale (producers → SIEM) | RFC 5424 (Syslog); RFC 5425 (Syslog over TLS); ArcSight CEF; ISO/IEC 27037 (digital evidence) | Cybersecurity Engineer + DPO | Log ingestion test + correlation rule verification + retention check | Concept | medium
INT-6A-C2-001 | C2 Uplink Primary (RF 2.4 GHz ISM) | Funzionale control | GS RF Transceiver (Microhard pMDDL2450 o eq.) | UAV RF Transceiver (FCS-side) | Unidirezionale (GS → UAV) per comandi | EN 300 328 (ISM 2.4 GHz harmonized standard EU); RED 2014/53/EU; AGCOM PNRF | RF Systems Engineer + AGCOM Liaison | Range test campo aperto + fade margin verification + spectrum analyzer | Preliminary | medium
INT-6A-C2-002 | C2 Downlink Telemetry (RF 2.4 GHz) | Funzionale control | UAV FCS + Telemetry Aggregator | GS Telemetry Receiver | Unidirezionale (UAV → GS) | MAVLink v2.0; CRC-32 IEEE 802.3; AES-256-GCM NIST SP 800-38D | Avionics Lead + RF Systems Engineer | BER test + encryption verification + replay attack test | Preliminary | high
INT-6A-C2-003 | C2 Secondary SATCOM (Iridium Certus L-band) | Funzionale control | UAV Iridium Certus 100 modem (Cobham/Honeywell) | Iridium NEXT constellation + GS Hub Iridium | Bidirezionale | ITU-R RR Article 22 (MSS L-band); Iridium Certus service specification; DO-262C (airborne SATCOM) | Avionics Lead + SATCOM Vendor Liaison | Link test + handover test + latency measurement | Concept | medium
INT-6A-C2-004 | C2 Lost-Link Procedure (Autonomous RTH) | Funzionale control + safety | FCS Flight Computer | Autopilot State Machine | Internal logic | RTCA DO-377 (C2 link); JARUS SORA 2.5 Annex F (lost-link procedure); EUROCAE ED-269 | Avionics Lead + Safety Engineer | Simulation HIL + flight test (in autorizzazione condizionata) | Concept | medium
INT-6A-C2-005 | Cybersecurity C2 Link (Mutual TLS + JWT) | Funzionale control + sicurezza | GS Operator (authenticated user) | UAV C2 endpoint | Bidirezionale (handshake) | TLS 1.3 RFC 8446; X.509 v3 RFC 5280; JWT RFC 7519; DO-326A (Airworthiness Security) | Cybersecurity Engineer + Avionics Lead | Penetration test (selettivo) + certificate validation test + JWT replay test | Concept | medium
INT-6A-C2-006 | ADS-B IN Receiver (Cooperative DAA) | Funzionale control + safety | UAV ADS-B IN receiver (e.g. PingRX Pro by uAvionix) | FCS Conflict Manager | Unidirezionale (Air Traffic → UAV) | RTCA DO-260C (ADS-B MOPS); ICAO Annex 10 Vol IV; EUROCAE ED-102B | Avionics Lead + DAA Specialist | Reception test in area aerea attiva (e.g. vicino aeroporto) + range verification | Concept | high
INT-6A-C2-007 | Non-Cooperative DAA (Visual EO or Acoustic) | Funzionale control + safety | UAV onboard EO camera + AI inference engine | FCS Conflict Manager | Unidirezionale (Sensor → FCS) | RTCA DO-365B (DAA MOPS); ASTM F3442/F3442M-23 (DAA Performance) | Avionics Lead + AI/ML Engineer | Detection range test (vs target ULM) + false alarm verification | Concept | low
INT-6A-C2-008 | Geofence Boundary (No-Fly Zone enforcement) | Funzionale control | GS Mission Planner (waypoint validator) | UAV FCS (geofence enforcer) | GS pre-flight upload; FCS runtime check | OGC GeoJSON RFC 7946; ASD-STAN prEN 4709 (UAS direct remote identification) | GCS UX Developer + Avionics Lead | Mission rejection test (waypoint in NFZ) + runtime breach test | Preliminary | high
INT-6A-GS-001 | GS Control Room HMI | Funzionale + operativa | Pilot/Operator + Observer | GS Workstation (3 monitor: map + telemetry + video) | Bidirezionale (HMI) | ISO 9241 (Ergonomics of HCI); MIL-STD-1472H (Human Engineering); EUROCAE ED-269 §4 (Remote Pilot Station) | GCS UX Developer + Human Factors Engineer | Usability test + workflow validation + cognitive workload assessment | Concept | medium
INT-6A-GS-002 | GS Mobile Vehicle Integration | Fisica + funzionale | Veicolo (Fiat Ducato L3H2 o eq.) outfitted GS | GS portable rack + antenna telescopic | Hosting | ISO 16750 (automotive electrical); IEC 60529 IP54 (rack protection) | Civil Works + Operations Lead | Deploy time test + vibration test + thermal test in cabina | Concept | medium
INT-6A-GS-003 | Cooperative Dashboard (Web App) | Funzionale data | Cooperative User (browser HTTPS) | Cloud Dashboard backend (SaaS Firmamento) | Bidirezionale (HTTPS) | SAML 2.0 (OASIS); SPID (AgID Linee Guida); OWASP ASVS 4.0; WAI-ARIA (accessibility) | Cloud Architect + Frontend Developer + DPO | Functional test + RBAC verification + accessibility audit (WCAG 2.1 AA) | Concept | medium
INT-6A-GS-004 | Protezione Civile Emergency Trigger | Operativa + contrattuale | Sala Operativa PC Regione Liguria (operatore) | Firmamento GCS On-Call Pilot | Bidirezionale (PC → Firmamento richiesta; Firmamento → PC stato) | SOP standard tabletop tested M+6-M+7; D.Lgs. 1/2018 Codice Protezione Civile; convenzione operativa ex art. 15 L. 241/90 | Operations Lead + PC Liaison Officer (Regione) | Tabletop exercise + scenario simulation + response time measurement | Concept | medium
INT-6A-GS-005 | Flight Authorization Workflow (Internal) | Operativa | Mission Planner (pre-flight check) + Pilot | Operations Manager (approval) + Safety Officer (oversight) | Workflow approval | EUROCAE ED-269; SOP Firmamento (DEL-PFTE-04 ConOps); JARUS SORA 2.5 OSO #19 | Operations Manager + Safety Officer | Workflow walk-through + audit trail verification | Concept | medium
INT-6A-GS-006 | GS Maintenance Console (Health Monitoring) | Funzionale data + operativa | UAV onboard Health Monitoring System (HMS) | GS Maintenance Console + remote alerts | Unidirezionale (UAV → GS) | ARINC 624 (Onboard Maintenance System); MIL-HDBK-2155 (Logistic Support Analysis) | Maintenance Manager + Avionics Lead | Fault injection test + alert verification | Concept | medium
INT-6A-GS-007 | Data Anonymization Pipeline (GDPR) | Funzionale data + regolatoria | Cloud Raw Image Storage | Anonymized Public Dataset Repository | Pipeline (Raw → Anonymized) | GDPR Reg. UE 2016/679 Art. 17 + Art. 25 (privacy by design); ISO/IEC 27701 (privacy info management) | DPO + Data Engineer + AI/ML Engineer | Anonymization quality test + DSAR workflow test + audit | Concept | medium
INT-6A-GS-008 | Backup & Disaster Recovery | Funzionale data + operativa | Cloud Primary (Aruba IT) | Cloud Backup (OVH IT EU separate region) | Replication scheduled | ISO/IEC 27031 (ICT readiness for business continuity); NIST SP 800-34 Contingency Planning | Cloud Architect + DevOps | Restore test (mensile) + DR drill (semestrale) | Concept | medium
INT-6A-REG-001 | ENAC SORA Authorization (SAIL III BVLOS) | Regolatoria | Firmamento Technologies (operatore UAS) | ENAC Ufficio RPAS | Bidirezionale (application + authorization) | Reg. UE 2019/947 art. 12 + AMC Amendment 3 (Sett 2025) SORA 2.5 EU; ENAC Reg. APR Ed. 3 | Aviation Regulatory Counsel + ENAC Liaison | Documentation review + pre-application feedback | Concept | medium
INT-6A-REG-002 | AGCOM Spectrum Authorization (2.4 GHz + L-band) | Regolatoria | Firmamento Technologies | AGCOM (Autorità Garante Comunicazioni) | Bidirezionale (application + authorization) | D.Lgs. 207/2021 Codice Comunicazioni Elettroniche art. 11; PNRF (Piano Nazionale Ripartizione Frequenze); EN 300 328 | Aviation Regulatory Counsel + RF Systems Engineer + AGCOM Liaison | Documentation review + AGCOM response | Concept | medium
INT-6A-REG-003 | ENAV/D-Flight U-Space Coordination | Regolatoria + operativa | Firmamento GCS | ENAV / D-Flight USSP (U-Space Service Provider) | Bidirezionale (flight authorization + network ID) | Reg. UE 2021/664 (U-Space framework); ENAC LG-2023/006; D-Flight USSP+CISP API | Aviation Regulatory Counsel + GCS Developer | API integration test + USSP coordination | Concept | medium
INT-6A-REG-004 | Garante Privacy DPIA + DSAR Procedure | Regolatoria | Firmamento (titolare + co-titolare con Regione) | Garante per la Protezione Dati Personali | Notifica + audit | GDPR Reg. UE 2016/679 Art. 35 + Art. 17; D.Lgs. 196/2003 novellato; Provv. Garante 1.8.2013 (videosorveglianza) | Data Privacy Counsel + DPO Firmamento + DPO Regione | DPIA review + DSAR drill test | Preliminary | medium
INT-6A-REG-005 | Assicurazione Aviation Third-Party Liability | Regolatoria + contrattuale | Firmamento (insured) | Insurance Broker + Carrier (Lloyd's / AON / Marsh) | Polizza contrattuale | Reg. UE 785/2004 (insurance requirements air carriers); ENAC LRA 25/2023 (UAS insurance) | CFO Firmamento + Insurance Broker | Polizza review + claim simulation | Concept | medium
INT-6A-REG-006 | NIS2 Cybersecurity Notification (D.Lgs. 138/2024) | Regolatoria | Firmamento (entità essenziale o importante TBD) | ACN (Agenzia Cybersicurezza Nazionale) | Notifica incident + reporting | D.Lgs. 138/2024 (recepimento Dir. UE 2022/2555 NIS2); ENISA Threat Landscape report 2025 | Cybersecurity Engineer + Legal Counsel | Incident response drill + notification workflow test | Concept | medium
INT-6B-PHY-001 | HALE Airframe ↔ Solar Panel Array | Fisica meccanica + termica | HALE Wing structure (CFRP + lino secondario) | Solar Panel Array (GaAs multi-junction Spectrolab XTJ Prime) | Statica (bonded) | ECSS-Q-ST-70-71 (Materials and Processes for spacecraft); ASTM E1980 (solar reflectance) | Aerodynamics-Structures Engineer + Solar Cell Specialist | Bonding strength test (lap shear) + thermal cycling + UV exposure | Concept | low
INT-6B-PHY-002 | HALE Wing Spar ↔ Fuselage Structural Joint | Fisica meccanica + strutturale | Wing spar carry-through (CFRP unidirezionale) | Fuselage frame ring (CFRP woven) | Statica (bolted + bonded) | ECSS-E-ST-32-08 (Materials); MIL-HDBK-17 (Composite Materials); ASTM D5868 (lap shear) | Aerodynamics-Structures Engineer | FEA analysis + GVT (Ground Vibration Test) + structural test article | Concept | low
INT-6B-PHY-003 | HALE Battery Pack Thermal Management | Fisica termica | LiS Battery Pack (target 350 Wh/kg, 100+ kWh capacity) | Thermal control system (passive + active heater) | Bidirezionale (heat flow + control) | DO-311A; UN 38.3; IEC 62133; ECSS-E-ST-31C (Thermal Control) | Thermal Engineer + Battery Specialist | Thermal vacuum chamber simulation + heater verification | Concept | low
INT-6B-PHY-004 | HALE Antenna Aperture (Ka-band 31 GHz) | Fisica meccanica + RF | HALE underbelly antenna mount | Ka-band feeder antenna (steerable phased array) | Statica + steerable | ITU-R F.1500 (HAPS RF specs); RTCA DO-262C (airborne SATCOM) | Telecom-NTN Payload Expert + RF Engineer | Pattern measurement (compact range) + thermal cycling | Concept | low
INT-6B-NTN-001 | 5G NR-NTN Service Link Downlink (HAPS → UE) | Funzionale + RF | HAPS gNodeB regenerative payload | User Equipment 5G NTN-capable (smartphone, IoT) | Unidirezionale (DL) | 3GPP TS 38.211/.212/.213/.214 (NR L1); TS 38.811 (NTN study); TS 38.821 (NTN solutions); ITU-R M.2150 | Telecom-NTN Payload Expert | Link budget simulation + over-the-air test (vs UE simulator) | Concept | low
INT-6B-NTN-002 | 5G NR-NTN Service Link Uplink (UE → HAPS) | Funzionale + RF | User Equipment 5G NTN-capable | HAPS gNodeB receiver | Unidirezionale (UL) | 3GPP TS 38.101-5 (NR-NTN UE requirements); ITU-R M.2150 | Telecom-NTN Payload Expert | Link budget verification + UL throughput test | Concept | low
INT-6B-NTN-003 | NTN Doppler Compensation | Funzionale RF | HAPS gNodeB onboard | UE (Doppler offset compensation) | Bidirezionale signaling | 3GPP TS 38.811 §6.4 (Doppler); TS 38.821 §6.4.2 (Doppler shift compensation) | Telecom-NTN Payload Expert + 5G Algorithm Specialist | Simulation OFDM Doppler vs SINR + lab test | Concept | medium
INT-6B-NTN-004 | Inter-Beam Handover (intra-HAPS) | Funzionale | HAPS gNodeB multi-beam (16-32 beam) | UE in motion (cross-beam boundary) | Bidirezionale signaling | 3GPP TS 38.331 (RRC); TS 38.300 (NR overall); TR 38.821 §7.4 (mobility NTN) | Telecom-NTN Payload Expert | Simulation handover + measurement campaign | Concept | medium
INT-6B-FEEDER-001 | Ka-band Feeder Link Downlink (HAPS → Gateway) | Funzionale + RF | HAPS AESA Ka-band antenna | Gateway HAPS ground station (parabola 3-5 m) | Unidirezionale (DL HAPS → Gateway) | ITU-R F.1500/F.1891 (HAPS specs); ETSI EN 302 307-2 (DVB-S2X); ITU-R P.618-14 (rain fade) | Telecom-NTN Payload Expert + Ka-band RF Engineer | Link budget calculation + rain fade simulation + outage analysis | Concept | low
INT-6B-FEEDER-002 | Ka-band Feeder Link Uplink (Gateway → HAPS) | Funzionale + RF | Gateway HAPS ground station transmitter | HAPS AESA Ka-band receiver | Unidirezionale (UL Gateway → HAPS) | ITU-R F.1500; ITU RR Appendix 30B | Telecom-NTN Payload Expert | Link budget + interference analysis vs FSS | Concept | low
INT-6B-FEEDER-003 | Gateway HAPS ↔ Core Network 5G | Funzionale data | Gateway HAPS ground station | 5G Core Network (5GC) operator partner | Bidirezionale | 3GPP TS 23.501 (5G architecture); TS 29.281 (GTP-U); IETF RFC 3031 (MPLS) | Telecom-NTN Payload Expert + 5G Core Specialist | Integration test (lab + field) + interop testing | Concept | low
INT-6B-OPS-001 | HALE Air Traffic Coordination (ENAV) | Regolatoria + operativa | Firmamento HALE Operations Center | ENAV ACC (Area Control Center) Milano | Bidirezionale (clearance + position reporting) | ICAO Annex 11 (Air Traffic Services); ICAO Doc 4444 (PANS-ATM); Reg. UE 923/2012 SERA | Aviation Regulatory Counsel + HALE Operations Manager | Flight plan submission test + ATC coordination drill | Concept | low
INT-6B-OPS-002 | EUROCONTROL Cross-Border Coordination | Regolatoria | Firmamento HALE Operations Center | EUROCONTROL Network Manager (Brussels) | Bidirezionale (flight plan + slot) | EUROCONTROL FPL format; ICAO Doc 7030 (Regional Supplementary Procedures) | Aviation Regulatory Counsel | Flight plan test + EUROCONTROL coordination | Concept | low
INT-6B-OPS-003 | HALE Launch & Recovery Site (Glider-style) | Operativa + fisica | HALE airframe | Launch site (runway grass ≥ 800 m oppure aerotraino con winch) | Operativa (singolo evento per missione) | FAA AC 91-79 (Mitigating Risks Associated with Approach and Landing); EASA AMC1 SPA.SPO (Specialised Operations) | HALE Operations Manager + Civil Works | Site survey + weather window analysis + recovery drill (subscale) | Concept | low
INT-X-CLOUD-001 | Cloud Hosting GAIA-X Compliant | Funzionale + regolatoria + contrattuale | Firmamento Cloud Workload (data + apps) | Cloud Provider GAIA-X compliant (Aruba/OVH/IONOS) | Contrattuale | GAIA-X Compliance Framework v22.10; ISO/IEC 27001; SOC 2 Type II; CSA STAR Level 2 | Cloud Architect + Procurement + DPO | Provider audit + GAIA-X attestation review + data residency test | Concept | high
INT-X-PRIVACY-001 | Data Subject Access Request (DSAR) Workflow | Regolatoria + operativa | Data Subject (cittadino, cooperativo, dipendente) | DPO Firmamento + Customer Support | Bidirezionale (request + response) | GDPR Reg. UE 2016/679 Art. 12-22; EDPB Guidelines 01/2022 (Data Subject Rights) | DPO + Customer Support | DSAR drill (semestrale) + response time audit | Concept | high
INT-X-CYBER-001 | Penetration Testing + Vulnerability Management | Regolatoria + sicurezza | Firmamento attack surface (apps + infra + UAS) | Pentest Provider (TÜV / DNV / Yarix) | Servizio professionale | OWASP Testing Guide v4.2; PTES (Penetration Testing Execution Standard); ISO/IEC 27001 A.12.6 | Cybersecurity Engineer + CISO (Y3+) | Pentest report + remediation tracking + retest | Concept | high
INT-X-LOGGING-001 | Centralized Logging + Audit Trail | Funzionale + regolatoria | All system components (UAS + GS + Cloud + Apps) | SIEM Central (e.g. Elastic SIEM, Wazuh, Splunk) | Unidirezionale (components → SIEM) | RFC 5424 Syslog; CEF Common Event Format; NIST SP 800-92 (Log Management); GDPR Art. 32 (accountability) | DevOps + Cybersecurity Engineer + DPO | Log ingestion test + retention verification + audit | Concept | high
INT-X-VENDOR-001 | Vendor SLA Framework (UAS Manufacturer) | Contrattuale | Firmamento Technologies (buyer) | UAS Vendor (JOUAV / Tekever / Quantum / FlyingBasket) | Contratto fornitura | AS/EN 9100D (Quality Mgmt Aerospace); ICAO Annex 19 (Safety Mgmt); contratto fornitura ex artt. 1470-1547 c.c. | Procurement Lead + Quality Manager | Vendor audit + warranty claim simulation + SLA monitoring | Concept | medium

## Physical_Interfaces
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-6A-PHY-001 | Airframe VTOL ↔ Modular Payload Bay | Fisica meccanica | VTOL Airframe (JOUAV CW-30E o eq.) | Payload Module (EO/IR/telecom) | Bidirezionale (statica) | Bay 250×180×120 mm; massa payload ≤ 3 kg + 0.5 kg buffer; CG shift ≤ 2% MAC; mount quick-release tipo Picatinny-like + vibration isolation MIL-STD-810H Cat 4 (5-2000 Hz, 7.7 grms) | MIL-STD-810H §514.8 (vibration); ISO 9022-2:2016 (mechanical mounting); vendor-specific dovetail mount | Avionics Integration Lead (Firmamento) + JOUAV Liaison | Inspection + analisi CG calc + shake table test | Preliminary | medium | Sub-interface di INT-01 Cap.4. Critica per modularità payload. Falsifying: se vendor non fornisce CAD interfacce → re-engineering custom +€15-25k.
INT-6A-PHY-002 | Payload Power Rail 28 VDC | Fisica elettrica | VTOL Power Distribution Unit (PDU) | Payload Module (load fino a 100 W) | Unidirezionale (PDU → Payload) | 28 VDC ±5%; ripple ≤ 200 mV pk-pk; transient response per DO-160G §16; protezione corto-circuito 5 A fuse; connector MIL-DTL-38999 Series III shell size 11; ground-return isolato | MIL-STD-704F (aircraft electrical power); DO-160G §16 (Power Input); MIL-STD-1377 (28 VDC) | Power Management SE + Avionics Lead | Lab bench test + transient injection + load step | Preliminary | high | Standard aerospace consolidato. Verificare in datasheet JOUAV se PDU eroga 28 VDC stabilizzato (alcuni vendor cinesi forniscono 24 VDC nominale).
INT-6A-PHY-003 | Payload Data Port Ethernet | Fisica elettrica + dati | Payload Module (camera/sensor) | Mission Computer (MC) VTOL | Bidirezionale full-duplex | 1000BASE-T Gigabit Ethernet su cavo Cat6 schermato; max 100 m; PoE+ opzionale (IEEE 802.3at, fino a 25.5 W); MTU 9000 jumbo frame supportato; latency end-to-end < 5 ms | IEEE 802.3 (Ethernet); IEEE 802.3at (PoE+); ANSI/TIA-568 (cabling) | Avionics Lead + Payload SE | Cable certification (Fluke DSX) + ping test + throughput iPerf3 | Preliminary | high | Standard COTS. Camera GigE Vision (Phase One iXM 100 supporta GigE).
INT-6A-PHY-004 | Ground Antenna Mount (parabolica 1.2 m) | Fisica meccanica | GS fissa Pentema (container) | Antenna parabolica RF 2.4 GHz | Statica (mount) | Mount mast h ≥ 6 m AGL; antenna parabolica D=1.2 m, peso ≈ 8 kg; vento sopravvivenza 200 km/h (Liguria estremo); azimuth/elevazione motorizzati ±180°/0-90°; preset pointing automatic via GPS UAV feedback | EIA-222-H (structural standards for steel antenna supports); IEC 60721 (environmental conditions) | RF Systems Engineer + Civil Works Lead | Inspection + load calc + alignment test | Preliminary | high | Sito Pentema esposto a vento di valle: verifica anemometrica preliminare M+4-M+6. Sub-interface di INT-04 Cap.4.
INT-6A-PHY-005 | Airborne RF Antenna Whip (2.4 GHz) | Fisica meccanica + RF | VTOL airframe (ventral) | Whip antenna 5 dBi omni vertical polarization | Bidirezionale (RF) | Antenna L=120 mm whip rigid; gain 5 dBi omni; VSWR ≤ 1.5 @ 2.4-2.485 GHz; connector SMA female; cavo LMR-240 max 1.5 m fino a transceiver | MIL-STD-348B (RF connectors); MIL-C-39012 (SMA family) | RF Systems Engineer | VNA sweep (VSWR + gain pattern) + range test | Preliminary | medium | Verifica pattern in presenza fusoliera (effetti reflection/null). Pre-installation EM compatibility test.
INT-6A-PHY-006 | Battery Pack ↔ Power Distribution (LiPo 6S 22.2V) | Fisica elettrica | Battery Pack 6S LiPo 22.2V 16000 mAh (≈ 356 Wh) | Power Distribution Unit (PDU) | Unidirezionale (Bat → PDU) + telemetry (BMS → MC) | XT90-S connector (max 90 A continuous); cella balanced JST-XH 6-pin; BMS integrato con telemetry CAN; SOC sense via Coulomb counter ±1% accuracy; max discharge 30C burst; max charge 3C | RTCA DO-311A (Rechargeable Lithium Battery); UN 38.3 (transport); IEC 62133 (safety) | Power Management SE + Battery Specialist | Capacity test + thermal runaway test + cycle test | Preliminary | high | Sub-interface di INT-08 Cap.4. Inverno Pentema -10°C: capacità derating ~15-20% → autonomia ridotta. Batteria self-heating opzionale.
INT-6A-PHY-007 | Thermal Interface Payload-Airframe | Fisica termica | Payload (heat generation 50-100 W) | Airframe (heat sink, ambient air) | Unidirezionale (heat flow) | Operating range payload -10°C / +50°C; conduction path via mounting plate (Al 6061); thermal pad K = 1.5 W/m·K; airflow cooling natural via NACA inlet 30×30 mm; storage range -25°C / +60°C | DO-160G §4 (Temperature); MIL-STD-810H §501.7 (High Temp), §502.7 (Low Temp) | Thermal Engineer + Payload SE | Thermal vacuum chamber test (per HALE) + thermal cycle (per VTOL) | Preliminary | medium | Per VTOL 6A range climatico Pentema gestibile. Per HALE 6B (-65°C @ 20 km) richiede heater + insulation attiva.
INT-6A-PHY-008 | VTOL Landing Gear ↔ Helipad Surface | Fisica meccanica | VTOL landing gear (skid o quad) | Helipad/touchdown surface (Pentema/mobile) | Contatto meccanico transitorio | Vertical landing speed ≤ 1.5 m/s; touchdown footprint 1.5×1.5 m max; superficie piana ±2° slope max; resistenza load 100 kg/m² distribuited; superficie min FOD-safe (no gravel) | FAA AC 150/5390-2D (Heliport Design); EASA CS-HPT (Heliport Design Manual) — applicabile per drone heliports | Operations Lead + Civil Works | Site survey + load calc + landing test | Concept | high | Pentema: scegliere area pianeggiante a quota 1100-1200 m AMSL, distanza ≥ 50 m da edifici. Coordinamento con Comune Torriglia.
INT-6A-PHY-009 | GS Power Supply (230 VAC mains) | Fisica elettrica | Rete elettrica Pentema (Enel Distribuzione) | GS fissa container + GS mobile veicolo | Unidirezionale (mains → GS) | 230 VAC ±10% 50 Hz; potenza richiesta GS 2.5 kW peak / 1.2 kW average; UPS online 3 kVA con autonomy ≥ 30 min; generator backup diesel 5 kVA per outage estesi | CEI 64-8 (impianti elettrici utilizzatori); IEC 61000-4 (EMC immunity) | Civil Works Lead + IT Operations | Load test + outage simulation + UPS autonomy test | Concept | medium | Pentema: verifica capacity allaccio Enel; possibile upgrade trasformatore di cabina. UPS obbligatorio per business continuity.
INT-6A-PHY-010 | Backhaul Internet Connection (GS → Cloud) | Fisica + dati | GS fissa Pentema | Backhaul WAN (FWA Linkem/Open Fiber/Starlink) | Bidirezionale | Throughput ≥ 25 Mbps uplink / ≥ 50 Mbps downlink; latency RTT ≤ 50 ms verso datacenter; uptime SLA ≥ 99.0% (single link), ≥ 99.5% (dual provider); media: fibra ottica primaria + LTE/5G backup + Starlink LEO fallback | ITU-T G.983 (PON); IEEE 802.3ah (Ethernet First Mile); 3GPP TS 23.501 (5G architecture) | IT Operations + Cloud Architect | iPerf3 throughput + ping latency + outage test | Concept | medium | Sub-interface di INT-05 Cap.4. Pentema area montana: probabile fibra non disponibile → FWA + Starlink dual. Verifica con Comune.
INT-6B-PHY-001 | HALE Airframe ↔ Solar Panel Array | Fisica meccanica + termica | HALE Wing structure (CFRP + lino secondario) | Solar Panel Array (GaAs multi-junction Spectrolab XTJ Prime) | Statica (bonded) | Area pannelli ≥ 25 m² (worst-case calc); panel mass density 0.5-0.8 kg/m²; encapsulation Honeywell Aclar (UV resistant); bonding film 3M VHB structural; thermal CTE matching critical | ECSS-Q-ST-70-71 (Materials and Processes for spacecraft); ASTM E1980 (solar reflectance) | Aerodynamics-Structures Engineer + Solar Cell Specialist | Bonding strength test (lap shear) + thermal cycling + UV exposure | Concept | low | Sub-interface di INT-01 Cap.4 per 6B. R&D dedicato. FALSIFYING (RSK-TEC-001): se peso pannelli > 0.8 kg/m² o efficienza < 28% → energy balance inverno deficit aggravato.
INT-6B-PHY-002 | HALE Wing Spar ↔ Fuselage Structural Joint | Fisica meccanica + strutturale | Wing spar carry-through (CFRP unidirezionale) | Fuselage frame ring (CFRP woven) | Statica (bolted + bonded) | Bolted joint M6 titanium x 16 + bonded film Hysol EA9394; load transfer max ±50 kN tension/compression (limit load) + 75 kN ultimate (factor 1.5); flutter clearance margin ≥ 20% | ECSS-E-ST-32-08 (Materials); MIL-HDBK-17 (Composite Materials); ASTM D5868 (lap shear) | Aerodynamics-Structures Engineer | FEA analysis + GVT (Ground Vibration Test) + structural test article | Concept | low | Critico per RSK-TEC-002 (aeroelasticità ala high-AR). Wing flexibility >20% apertura tipica HALE → joint deve sostenere fatigue + load reversal.
INT-6B-PHY-003 | HALE Battery Pack Thermal Management | Fisica termica | LiS Battery Pack (target 350 Wh/kg, 100+ kWh capacity) | Thermal control system (passive + active heater) | Bidirezionale (heat flow + control) | Battery operating range +5°C / +45°C optimal; @ 20 km ambient -65°C → heater 50 W continuous + phase-change material insulation; charge inhibit se T < 0°C; thermal mass 5 kg PCM | DO-311A; UN 38.3; IEC 62133; ECSS-E-ST-31C (Thermal Control) | Thermal Engineer + Battery Specialist | Thermal vacuum chamber simulation + heater verification | Concept | low | Thermal mass penalty in MTOW. FALSIFYING: se heater richiede > 80 W continuous → impatta energy balance notturno → showstopper RSK-TEC-001 aggravato.
INT-6B-PHY-004 | HALE Antenna Aperture (Ka-band 31 GHz) | Fisica meccanica + RF | HALE underbelly antenna mount | Ka-band feeder antenna (steerable phased array) | Statica + steerable | Phased array 256-element @ 31 GHz; aperture 30×30 cm; mass ≤ 3 kg; beam steering ±60° azimuth/elevation; gimbal opzionale per coarse pointing; mount struttura CFRP isolata termicamente | ITU-R F.1500 (HAPS RF specs); RTCA DO-262C (airborne SATCOM) | Telecom-NTN Payload Expert + RF Engineer | Pattern measurement (compact range) + thermal cycling | Concept | low | AESA Ka-band 2026: maturità TRL 6 component, TRL 3-4 integrato HALE. Costo €150-300k unit (R&D).

## Data_Interfaces
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-6A-DATA-001 | Payload EO RGB → Mission Computer | Funzionale data | Camera Phase One iXM 100 (100 MP, 11608×8708 px) | Mission Computer (MC) airborne | Unidirezionale (Camera → MC) | GigE Vision 2.1 protocol; image RAW IIQ 16-bit ≈ 100 MB/frame; trigger frequency 1-5 fps; geotagging via NTP time sync + GPS PPS pulse 1 PPS ±100 ns | GigE Vision 2.1 (AIA standard); GenICam 3.x; NTP v4 RFC 5905; PPS NMEA 0183 | Payload SE + Avionics Lead | Image capture test + geotag accuracy verification + throughput test | Preliminary | high | Sub-interface di INT-02 Cap.4. Standard consolidato per camera industrial.
INT-6A-DATA-002 | Payload IR LWIR → Mission Computer | Funzionale data | Camera termica FLIR Vue Pro R / WIRIS Pro (640×512 px LWIR 7.5-13.5 μm) | Mission Computer airborne | Unidirezionale | USB 3.0 SuperSpeed; image radiometric 16-bit (T °C per pixel); NEdT ≤ 50 mK; frame rate 9 Hz; trigger via TTL line; calibration NUC ogni 30 min auto | USB 3.0 specification; FLIR Atlas SDK; ASTM E1862-97 (IR camera calibration) | Payload SE | Radiometric accuracy test (calibrazione blackbody) + frame rate verification | Preliminary | high | Hotspot detection antincendio: target threshold 50°C su pixel risoluzione ground ≈ 0.7 m @ 500 m AGL.
INT-6A-DATA-003 | Mission Data Storage (onboard NVMe SSD) | Funzionale data | Mission Computer (MC) | NVMe SSD storage 2 TB ruggedized (industrial) | Bidirezionale (R/W) | PCIe Gen3 x4; sequential write ≥ 1.5 GB/s; capacity 2 TB (≈ 10 missioni 6h con EO RGB full); MTBF ≥ 2M hours; operating temp -40°C / +85°C industrial grade | NVMe 1.4 specification; PCIe Gen3 (PCI-SIG) | Avionics Lead + Mission Computer SE | Throughput benchmark + power-off recovery + thermal cycling | Preliminary | high | Storage capacity dimensionata per copertura 6-10h volo + 100 MB/frame RGB.
INT-6A-DATA-004 | Mission Data Upload GS → Cloud | Funzionale data | GS post-flight ingest (NVMe rimovibile o WiFi 6) | Cloud Object Storage (S3-compatible, Aruba/OVH) | Unidirezionale (GS → Cloud) | HTTPS REST API multipart upload; AES-256 in transit (TLS 1.3); object size avg 5-50 GB per missione; throughput ≥ 25 Mbps target; resumable upload (S3 Multipart o Tus.io) | AWS S3 API v4; TLS 1.3 RFC 8446; Tus.io resumable upload spec | Cloud Architect + DevOps | Upload time vs object size benchmark + interrupted resume test | Preliminary | high | Sub-interface di INT-05 Cap.4. Backhaul fibra/FWA Pentema fondamentale (INT-6A-PHY-010).
INT-6A-DATA-005 | Telemetry Real-time Stream (UAV → GS) | Funzionale data | VTOL FCS (Flight Computer System) | GS Telemetry Dashboard (operator UI) | Unidirezionale (UAV → GS) | MAVLink v2.0 over UDP; freq 10 Hz nominale; payload telemetry: GPS lat/lon/alt, attitude RPY, airspeed, GS SOC, motor RPM, system status; bandwidth ≈ 20 kbps; encryption AES-256-GCM | MAVLink Protocol v2.0 (Dronecode); AES-256-GCM (NIST SP 800-38D) | Avionics Lead + GCS UX Developer | Packet capture + decode + latency measurement (link tester) | Preliminary | high | Sub-interface di INT-03 Cap.4 (downlink). MAVLink v2.0 standard industria UAS commerciali.
INT-6A-DATA-006 | Video Downlink Preview (Low-bitrate) | Funzionale data | Payload EO RGB (preview pipeline) | GS Operator Display | Unidirezionale (UAV → GS) | H.265 HEVC encoded 720p @ 5 fps; bitrate target 0.5-1.5 Mbps; latency end-to-end ≤ 500 ms; RTSP/RTP protocol over UDP; backup degraded mode 320p @ 2 fps @ 200 kbps | ITU-T H.265 / ISO/IEC 23008-2 (HEVC); RFC 3550 (RTP); RFC 7826 (RTSP 2.0) | Payload SE + GCS Developer | Latency measurement (timestamp injection) + decoder compatibility test | Preliminary | medium | Sub-interface di INT-03 Cap.4 (video). Critico per situational awareness pilota + Protezione Civile monitoring.
INT-6A-DATA-007 | Photogrammetry Pipeline (Cloud) | Funzionale data | Cloud Object Storage (raw images) | Photogrammetry Engine (Pix4D/Agisoft/OpenDroneMap) | Bidirezionale | REST API trigger via webhook post-upload; input GeoTIFF + EXIF; output: orthomosaic GeoTIFF (EPSG:32632 WGS84/UTM 32N), DSM/DTM, point cloud LAS; processing time ≈ 30-120 min per missione | OGC GeoTIFF; ASPRS LAS 1.4; EXIF 2.32; OGC WMTS | GIS Engineer + Cloud Architect | Pipeline test end-to-end + output validation | Preliminary | medium | Sub-interface di INT-06 Cap.4. Possibile outsourcing pipeline (Pix4Dcloud SaaS) per Y1; in-house dal Y2.
INT-6A-DATA-008 | Audit Log + Operational Telemetry → SIEM | Funzionale data + sicurezza | GS + Cloud + Mission Computer (log producers) | SIEM (Security Information & Event Management) | Unidirezionale (producers → SIEM) | Syslog over TLS RFC 5425; CEF format (Common Event Format); retention 90 giorni hot + 1 anno cold; events/sec peak 100, average 10 | RFC 5424 (Syslog); RFC 5425 (Syslog over TLS); ArcSight CEF; ISO/IEC 27037 (digital evidence) | Cybersecurity Engineer + DPO | Log ingestion test + correlation rule verification + retention check | Concept | medium | Necessario per NIS2 compliance (D.Lgs. 138/2024) + GDPR Art. 32 accountability. Sub-interface di INT-12 Cap.4.

## C2_Interfaces
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-6A-C2-001 | C2 Uplink Primary (RF 2.4 GHz ISM) | Funzionale control | GS RF Transceiver (Microhard pMDDL2450 o eq.) | UAV RF Transceiver (FCS-side) | Unidirezionale (GS → UAV) per comandi | Frequenza 2400-2483.5 MHz ISM; modulazione OFDM adaptive; bitrate 0.5-9 Mbps; EIRP ≤ 100 mW (20 dBm) per AGCOM ISM o ≤ 1 W con licenza individuale; latency one-way ≤ 100 ms; fade margin ≥ 12 dB | EN 300 328 (ISM 2.4 GHz harmonized standard EU); RED 2014/53/EU; AGCOM PNRF | RF Systems Engineer + AGCOM Liaison | Range test campo aperto + fade margin verification + spectrum analyzer | Preliminary | medium | Sub-interface di INT-03 Cap.4 (uplink). FALSIFYING: in valle Pentema shadow zones probabili → switch automatico a SATCOM L-band (INT-6A-C2-003) entro 5 s.
INT-6A-C2-002 | C2 Downlink Telemetry (RF 2.4 GHz) | Funzionale control | UAV FCS + Telemetry Aggregator | GS Telemetry Receiver | Unidirezionale (UAV → GS) | Same RF link di INT-6A-C2-001 (TDD time-division duplex); telemetry frame size ≈ 256 byte @ 10 Hz; CRC-32 error detection; AES-256-GCM encryption end-to-end; auto-throttle se BER > 1e-4 | MAVLink v2.0; CRC-32 IEEE 802.3; AES-256-GCM NIST SP 800-38D | Avionics Lead + RF Systems Engineer | BER test + encryption verification + replay attack test | Preliminary | high | Sub-interface di INT-03 Cap.4 (downlink).
INT-6A-C2-003 | C2 Secondary SATCOM (Iridium Certus L-band) | Funzionale control | UAV Iridium Certus 100 modem (Cobham/Honeywell) | Iridium NEXT constellation + GS Hub Iridium | Bidirezionale | L-band 1616-1626.5 MHz uplink, 1616-1626.5 MHz downlink; throughput 22 kbps Certus 100 / 88 kbps Certus 200 / 700 kbps Certus 700; latency one-way ≈ 200-400 ms (LEO ~780 km); coverage globale; antenna L-band patch 70×70 mm conformal | ITU-R RR Article 22 (MSS L-band); Iridium Certus service specification; DO-262C (airborne SATCOM) | Avionics Lead + SATCOM Vendor Liaison | Link test + handover test + latency measurement | Concept | medium | Sub-interface di INT-03 Cap.4 (SATCOM fallback). FALSIFYING: in valle Pentema con elevation angle satellite ≥ 8° quasi continuo grazie a 66 satelliti LEO Iridium → coverage OK. Costo: ~€800-1200/mese per piano dati.
INT-6A-C2-004 | C2 Lost-Link Procedure (Autonomous RTH) | Funzionale control + safety | FCS Flight Computer | Autopilot State Machine | Internal logic | Trigger lost-link > 5 s consecutivi senza heartbeat MAVLink; primary action: RTH (Return-To-Home) verso ultimo home point GPS; secondary action se RTH fail: loiter + emergency land alla quota minima sicura; alert SMS PC + pilot | RTCA DO-377 (C2 link); JARUS SORA 2.5 Annex F (lost-link procedure); EUROCAE ED-269 | Avionics Lead + Safety Engineer | Simulation HIL + flight test (in autorizzazione condizionata) | Concept | medium | Critico per SORA SAIL III BVLOS authorization. FALSIFYING: se RTH path attraversa shadow zone GPS o ostacolo orografico → emergency land può atterrare in area non sicura. Mitigazione: 3 RTH waypoint intermedi pre-pianificati.
INT-6A-C2-005 | Cybersecurity C2 Link (Mutual TLS + JWT) | Funzionale control + sicurezza | GS Operator (authenticated user) | UAV C2 endpoint | Bidirezionale (handshake) | Mutual TLS 1.3 con X.509 certificates (CA Firmamento proprietary); session JWT (RFC 7519) signed RS256, validity 4h; rate limit 100 req/min per session; intrusion detection via anomaly behavior | TLS 1.3 RFC 8446; X.509 v3 RFC 5280; JWT RFC 7519; DO-326A (Airworthiness Security) | Cybersecurity Engineer + Avionics Lead | Penetration test (selettivo) + certificate validation test + JWT replay test | Concept | medium | DO-326A compliance richiesta per certificazione futura. Per Y1 PoC sufficiente.
INT-6A-C2-006 | ADS-B IN Receiver (Cooperative DAA) | Funzionale control + safety | UAV ADS-B IN receiver (e.g. PingRX Pro by uAvionix) | FCS Conflict Manager | Unidirezionale (Air Traffic → UAV) | ADS-B 1090 MHz Extended Squitter receiver; range 50+ NM line-of-sight; reporting period 1 Hz nominal; output: traffic list (ICAO 24-bit address, lat/lon/alt/velocity) per FCS conflict detection | RTCA DO-260C (ADS-B MOPS); ICAO Annex 10 Vol IV; EUROCAE ED-102B | Avionics Lead + DAA Specialist | Reception test in area aerea attiva (e.g. vicino aeroporto) + range verification | Concept | high | Standard per SORA SAIL III in EU. ADS-B IN sufficiente per traffico cooperativo (aviazione commerciale). Per non-cooperativo (GA leggera, paracadutisti) NON sufficiente → INT-6A-C2-007 radar/EO.
INT-6A-C2-007 | Non-Cooperative DAA (Visual EO or Acoustic) | Funzionale control + safety | UAV onboard EO camera + AI inference engine | FCS Conflict Manager | Unidirezionale (Sensor → FCS) | Camera RGB orientata azimuth ±90° + elevation ±30°; inference YOLO-based detection aircraft @ 1-2 Hz; range detection target ≥ 1 NM (target aircraft 3 m wingspan); false alarm rate ≤ 0.01/h | RTCA DO-365B (DAA MOPS); ASTM F3442/F3442M-23 (DAA Performance) | Avionics Lead + AI/ML Engineer | Detection range test (vs target ULM) + false alarm verification | Concept | low | Necessario per SORA SAIL IV o quando ADS-B insufficiente. R&D dedicato. Per Y1 6A focus su mitigazione operativa (NOTAM, geofencing aree non interferenti). FALSIFYING: se ENAC richiede DAA non-cooperativo certificato per Pentema BVLOS, e tecnologia COTS non disponibile → Hold SORA submission.
INT-6A-C2-008 | Geofence Boundary (No-Fly Zone enforcement) | Funzionale control | GS Mission Planner (waypoint validator) | UAV FCS (geofence enforcer) | GS pre-flight upload; FCS runtime check | Geofence polygon GeoJSON (max 100 vertices); altitude ceiling AGL + AMSL; soft boundary (warning) + hard boundary (auto-return); buffer ≥ 100 m da no-fly zone (es. aerea D-flight U-Space) | OGC GeoJSON RFC 7946; ASD-STAN prEN 4709 (UAS direct remote identification) | GCS UX Developer + Avionics Lead | Mission rejection test (waypoint in NFZ) + runtime breach test | Preliminary | high | Standard COTS in MAVLink mission planner.

## GS_Interfaces
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-6A-GS-001 | GS Control Room HMI | Funzionale + operativa | Pilot/Operator + Observer | GS Workstation (3 monitor: map + telemetry + video) | Bidirezionale (HMI) | 3 monitor 27" 4K; input dual workstation (pilot + observer); HOTAS hardware joystick + keyboard/mouse; intercom system pilot-observer-PC; logging session full screen + audio | ISO 9241 (Ergonomics of HCI); MIL-STD-1472H (Human Engineering); EUROCAE ED-269 §4 (Remote Pilot Station) | GCS UX Developer + Human Factors Engineer | Usability test + workflow validation + cognitive workload assessment | Concept | medium | Standard JOUAV include workstation. Customizzazione per dual-operator Pentema.
INT-6A-GS-002 | GS Mobile Vehicle Integration | Fisica + funzionale | Veicolo (Fiat Ducato L3H2 o eq.) outfitted GS | GS portable rack + antenna telescopic | Hosting | Rack 19" 12U fisso al pianale veicolo; antenna telescopica h max 6 m AGL deployable; 12V/230V power dual; aria condizionata; setup time ≤ 30 min sul sito | ISO 16750 (automotive electrical); IEC 60529 IP54 (rack protection) | Civil Works + Operations Lead | Deploy time test + vibration test + thermal test in cabina | Concept | medium | Mobile GS per Protezione Civile rapid deployment scenarios.
INT-6A-GS-003 | Cooperative Dashboard (Web App) | Funzionale data | Cooperative User (browser HTTPS) | Cloud Dashboard backend (SaaS Firmamento) | Bidirezionale (HTTPS) | Web app responsive (desktop + tablet); login via SPID (SAML 2.0) + JWT session 8h; map viewer Leaflet/OpenLayers; download GeoTIFF / GeoJSON / PDF report; RBAC per area geografica polygon | SAML 2.0 (OASIS); SPID (AgID Linee Guida); OWASP ASVS 4.0; WAI-ARIA (accessibility) | Cloud Architect + Frontend Developer + DPO | Functional test + RBAC verification + accessibility audit (WCAG 2.1 AA) | Concept | medium | Sub-interface di INT-06 Cap.4. SPID obbligatorio per accesso PA + cooperative. AgID compliance check.
INT-6A-GS-004 | Protezione Civile Emergency Trigger | Operativa + contrattuale | Sala Operativa PC Regione Liguria (operatore) | Firmamento GCS On-Call Pilot | Bidirezionale (PC → Firmamento richiesta; Firmamento → PC stato) | Trigger via: (1) SMS gateway dedicato +39 numero unico, (2) email PEC priority, (3) webform dashboard. Acknowledge entro 5 min; launch decision entro 15 min TTR; ortofoto live entro 30 min (target nominale) | SOP standard tabletop tested M+6-M+7; D.Lgs. 1/2018 Codice Protezione Civile; convenzione operativa ex art. 15 L. 241/90 | Operations Lead + PC Liaison Officer (Regione) | Tabletop exercise + scenario simulation + response time measurement | Concept | medium | Sub-interface di INT-11 Cap.4. SLA TTR ≤ 4h nominale; emergency ≤ 30 min target. FALSIFYING: in caso meteo avverso (vento > 17 m/s) la launch può non essere possibile → SLA degraded a 'best effort'.
INT-6A-GS-005 | Flight Authorization Workflow (Internal) | Operativa | Mission Planner (pre-flight check) + Pilot | Operations Manager (approval) + Safety Officer (oversight) | Workflow approval | Checklist pre-flight: meteo, NOTAM, geofence, payload OK, battery OK, ENAC permission OK; signing digital (e-Sign) da 2 figure (pilot + ops manager); log workflow audit trail completo | EUROCAE ED-269; SOP Firmamento (DEL-PFTE-04 ConOps); JARUS SORA 2.5 OSO #19 | Operations Manager + Safety Officer | Workflow walk-through + audit trail verification | Concept | medium | Necessario per OSO #19 (Operator's safety culture). Compliance SORA SAIL III.
INT-6A-GS-006 | GS Maintenance Console (Health Monitoring) | Funzionale data + operativa | UAV onboard Health Monitoring System (HMS) | GS Maintenance Console + remote alerts | Unidirezionale (UAV → GS) | Telemetry per: motor bearings vibration, battery cell SOH (State Of Health), servo current consumption, GPS HDOP/VDOP, IMU calibration drift; auto-alert se metric fuori soglia; data retention 1 anno per trend analysis | ARINC 624 (Onboard Maintenance System); MIL-HDBK-2155 (Logistic Support Analysis) | Maintenance Manager + Avionics Lead | Fault injection test + alert verification | Concept | medium | Critico per Reliability-Centered Maintenance (RCM). Output al Piano di Manutenzione (Vol. 2 Allegato A.10).
INT-6A-GS-007 | Data Anonymization Pipeline (GDPR) | Funzionale data + regolatoria | Cloud Raw Image Storage | Anonymized Public Dataset Repository | Pipeline (Raw → Anonymized) | AI inference: face blurring + license plate blurring; processing time ≤ 5 min per ortofoto; quality check: false negative rate ≤ 1%; opt-out registry per cittadini che richiedono erasure (DSAR Art. 17 GDPR) | GDPR Reg. UE 2016/679 Art. 17 + Art. 25 (privacy by design); ISO/IEC 27701 (privacy info management) | DPO + Data Engineer + AI/ML Engineer | Anonymization quality test + DSAR workflow test + audit | Concept | medium | Sub-interface di INT-12 Cap.4. Necessario per DPIA approvazione. FALSIFYING: se Garante rileva residual identifiability nelle ortofoto pubbliche → workflow esteso o restrizione accesso.
INT-6A-GS-008 | Backup & Disaster Recovery | Funzionale data + operativa | Cloud Primary (Aruba IT) | Cloud Backup (OVH IT EU separate region) | Replication scheduled | Backup incremental ogni 4h; full backup settimanale; retention 30 giorni hot + 1 anno cold; RPO ≤ 4h; RTO ≤ 24h; encryption at rest AES-256 | ISO/IEC 27031 (ICT readiness for business continuity); NIST SP 800-34 Contingency Planning | Cloud Architect + DevOps | Restore test (mensile) + DR drill (semestrale) | Concept | medium | Necessario per NIS2 compliance art. 21. GAIA-X compliance preserva sovranità dati.

## Regulatory_Interfaces
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-6A-REG-001 | ENAC SORA Authorization (SAIL III BVLOS) | Regolatoria | Firmamento Technologies (operatore UAS) | ENAC Ufficio RPAS | Bidirezionale (application + authorization) | Application: Operations Manual + SORA worksheet + Operator Declaration + insurance + DAA mitigation; iter: pre-application meeting M+3-M+6, application formal M+15-M+18 (Fase 1), authorization expected M+18-M+22; categoria Specific SAIL III stimato per BVLOS Pentema | Reg. UE 2019/947 art. 12 + AMC Amendment 3 (Sett 2025) SORA 2.5 EU; ENAC Reg. APR Ed. 3 | Aviation Regulatory Counsel + ENAC Liaison | Documentation review + pre-application feedback | Concept | medium | Sub-interface di INT-13 Cap.4. FALSIFYING: se ENAC valuta Pentema come area sensibile (zona ad alta protezione naturale es. Aveto) e richiede SAIL IV → costi +€200-400k + tempo +6 mesi → review business case.
INT-6A-REG-002 | AGCOM Spectrum Authorization (2.4 GHz + L-band) | Regolatoria | Firmamento Technologies | AGCOM (Autorità Garante Comunicazioni) | Bidirezionale (application + authorization) | Spettro primario: ISM 2.4-2.4835 GHz (EIRP ≤ 100 mW unlicensed; ≤ 1 W con autorizzazione individuale); fallback L-band Iridium 1616-1626.5 MHz già licenziato a Iridium; EIRP/coexistence verificato per area Pentema | D.Lgs. 207/2021 Codice Comunicazioni Elettroniche art. 11; PNRF (Piano Nazionale Ripartizione Frequenze); EN 300 328 | Aviation Regulatory Counsel + RF Systems Engineer + AGCOM Liaison | Documentation review + AGCOM response | Concept | medium | Sub-interface di INT-07 Cap.4. ISM unlicensed fattibile ma EIRP basso → range limitato. Per range 50 km richiede licenza individuale (lead time 4-8 mesi).
INT-6A-REG-003 | ENAV/D-Flight U-Space Coordination | Regolatoria + operativa | Firmamento GCS | ENAV / D-Flight USSP (U-Space Service Provider) | Bidirezionale (flight authorization + network ID) | Network Identification: broadcast UAS ID + position via D-Flight API; flight authorization request per area U-Space (se istituita su Pentema); geo-awareness: pre-flight check NFZ | Reg. UE 2021/664 (U-Space framework); ENAC LG-2023/006; D-Flight USSP+CISP API | Aviation Regulatory Counsel + GCS Developer | API integration test + USSP coordination | Concept | medium | Sub-interface di INT-14 Cap.4. U-Space su Pentema non ancora istituito (2026). Engagement con ENAV per anticipare requirement.
INT-6A-REG-004 | Garante Privacy DPIA + DSAR Procedure | Regolatoria | Firmamento (titolare + co-titolare con Regione) | Garante per la Protezione Dati Personali | Notifica + audit | DPIA Art. 35 GDPR completata + signed DPO; workshop pubblico Pentema con DPIA pubblicata; DSAR procedure: response entro 30 gg, erasure entro 30 gg; provider audit annuale | GDPR Reg. UE 2016/679 Art. 35 + Art. 17; D.Lgs. 196/2003 novellato; Provv. Garante 1.8.2013 (videosorveglianza) | Data Privacy Counsel + DPO Firmamento + DPO Regione | DPIA review + DSAR drill test | Preliminary | medium | Sub-interface di INT-15 Cap.4. DPIA firma DPO M+5. FALSIFYING: se Garante richiede notifica preventiva Art. 36 → lead time +3-6 mesi.
INT-6A-REG-005 | Assicurazione Aviation Third-Party Liability | Regolatoria + contrattuale | Firmamento (insured) | Insurance Broker + Carrier (Lloyd's / AON / Marsh) | Polizza contrattuale | Massimale third-party liability obbligatorio Reg. UE 785/2004: MTOW 38 kg → massimale 750.000 DSP ≈ €870k; option upgrade a €1.5M-3M per servizi PA; hull insurance opzionale; war risk exclusion | Reg. UE 785/2004 (insurance requirements air carriers); ENAC LRA 25/2023 (UAS insurance) | CFO Firmamento + Insurance Broker | Polizza review + claim simulation | Concept | medium | Mercato assicurativo UAS in evoluzione 2026 (post-incidenti BVLOS UK 2024-25). Premi stimati €15-40k/anno per copertura €1.5M.
INT-6A-REG-006 | NIS2 Cybersecurity Notification (D.Lgs. 138/2024) | Regolatoria | Firmamento (entità essenziale o importante TBD) | ACN (Agenzia Cybersicurezza Nazionale) | Notifica incident + reporting | Notifica incident significativo entro 24h initial + 72h detailed + 1 mese final report; misure tecniche obbligatorie art. 21 (risk mgmt, incident response, supply chain, awareness training) | D.Lgs. 138/2024 (recepimento Dir. UE 2022/2555 NIS2); ENISA Threat Landscape report 2025 | Cybersecurity Engineer + Legal Counsel | Incident response drill + notification workflow test | Concept | medium | Status NIS2 (essenziale/importante) da chiarire: aviation civil è 'essenziale' Allegato I, ma UAS commerciale potrebbe rientrare in 'importante' Allegato II. Engagement ACN preliminare.

## HALE_Specific
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-6B-PHY-001 | HALE Airframe ↔ Solar Panel Array | Fisica meccanica + termica | HALE Wing structure (CFRP + lino secondario) | Solar Panel Array (GaAs multi-junction Spectrolab XTJ Prime) | Statica (bonded) | Area pannelli ≥ 25 m² (worst-case calc); panel mass density 0.5-0.8 kg/m²; encapsulation Honeywell Aclar (UV resistant); bonding film 3M VHB structural; thermal CTE matching critical | ECSS-Q-ST-70-71 (Materials and Processes for spacecraft); ASTM E1980 (solar reflectance) | Aerodynamics-Structures Engineer + Solar Cell Specialist | Bonding strength test (lap shear) + thermal cycling + UV exposure | Concept | low | Sub-interface di INT-01 Cap.4 per 6B. R&D dedicato. FALSIFYING (RSK-TEC-001): se peso pannelli > 0.8 kg/m² o efficienza < 28% → energy balance inverno deficit aggravato.
INT-6B-PHY-002 | HALE Wing Spar ↔ Fuselage Structural Joint | Fisica meccanica + strutturale | Wing spar carry-through (CFRP unidirezionale) | Fuselage frame ring (CFRP woven) | Statica (bolted + bonded) | Bolted joint M6 titanium x 16 + bonded film Hysol EA9394; load transfer max ±50 kN tension/compression (limit load) + 75 kN ultimate (factor 1.5); flutter clearance margin ≥ 20% | ECSS-E-ST-32-08 (Materials); MIL-HDBK-17 (Composite Materials); ASTM D5868 (lap shear) | Aerodynamics-Structures Engineer | FEA analysis + GVT (Ground Vibration Test) + structural test article | Concept | low | Critico per RSK-TEC-002 (aeroelasticità ala high-AR). Wing flexibility >20% apertura tipica HALE → joint deve sostenere fatigue + load reversal.
INT-6B-PHY-003 | HALE Battery Pack Thermal Management | Fisica termica | LiS Battery Pack (target 350 Wh/kg, 100+ kWh capacity) | Thermal control system (passive + active heater) | Bidirezionale (heat flow + control) | Battery operating range +5°C / +45°C optimal; @ 20 km ambient -65°C → heater 50 W continuous + phase-change material insulation; charge inhibit se T < 0°C; thermal mass 5 kg PCM | DO-311A; UN 38.3; IEC 62133; ECSS-E-ST-31C (Thermal Control) | Thermal Engineer + Battery Specialist | Thermal vacuum chamber simulation + heater verification | Concept | low | Thermal mass penalty in MTOW. FALSIFYING: se heater richiede > 80 W continuous → impatta energy balance notturno → showstopper RSK-TEC-001 aggravato.
INT-6B-PHY-004 | HALE Antenna Aperture (Ka-band 31 GHz) | Fisica meccanica + RF | HALE underbelly antenna mount | Ka-band feeder antenna (steerable phased array) | Statica + steerable | Phased array 256-element @ 31 GHz; aperture 30×30 cm; mass ≤ 3 kg; beam steering ±60° azimuth/elevation; gimbal opzionale per coarse pointing; mount struttura CFRP isolata termicamente | ITU-R F.1500 (HAPS RF specs); RTCA DO-262C (airborne SATCOM) | Telecom-NTN Payload Expert + RF Engineer | Pattern measurement (compact range) + thermal cycling | Concept | low | AESA Ka-band 2026: maturità TRL 6 component, TRL 3-4 integrato HALE. Costo €150-300k unit (R&D).
INT-6B-NTN-001 | 5G NR-NTN Service Link Downlink (HAPS → UE) | Funzionale + RF | HAPS gNodeB regenerative payload | User Equipment 5G NTN-capable (smartphone, IoT) | Unidirezionale (DL) | Frequency S-band 2010-2025 MHz (n255) o 1980-2010 MHz (n256); bandwidth 5-20 MHz per beam; modulation up to 256-QAM; coverage cell 30-50 km diameter @ 20 km altitude; capacity per beam 50-200 Mbps | 3GPP TS 38.211/.212/.213/.214 (NR L1); TS 38.811 (NTN study); TS 38.821 (NTN solutions); ITU-R M.2150 | Telecom-NTN Payload Expert | Link budget simulation + over-the-air test (vs UE simulator) | Concept | low | Per 6B HALE. Service link S-band ideale per copertura aree interne 5G NTN. Spettro contestato con MNO terrestri TIM/Vodafone n255 → accordi spectrum sharing necessari.
INT-6B-NTN-002 | 5G NR-NTN Service Link Uplink (UE → HAPS) | Funzionale + RF | User Equipment 5G NTN-capable | HAPS gNodeB receiver | Unidirezionale (UL) | Frequency S-band paired UL; UE EIRP max 23 dBm (handheld) o 33 dBm (vehicular); link budget challenging due to UE low power; modulation up to 64-QAM (UL) | 3GPP TS 38.101-5 (NR-NTN UE requirements); ITU-R M.2150 | Telecom-NTN Payload Expert | Link budget verification + UL throughput test | Concept | low | UL è il collo di bottiglia in NTN: UE handheld 23 dBm a 20 km distance richiede HAPS antenna G/T > 5 dB/K → AESA G ≥ 30 dBi necessario.
INT-6B-NTN-003 | NTN Doppler Compensation | Funzionale RF | HAPS gNodeB onboard | UE (Doppler offset compensation) | Bidirezionale signaling | HAPS station-keeping ±5 km nominal; ground speed effective 10-30 km/h (wind drift) → Doppler @ S-band ≈ 50-200 Hz; pre-compensation HAPS-side + UE-side residual ≤ 50 Hz | 3GPP TS 38.811 §6.4 (Doppler); TS 38.821 §6.4.2 (Doppler shift compensation) | Telecom-NTN Payload Expert + 5G Algorithm Specialist | Simulation OFDM Doppler vs SINR + lab test | Concept | medium | Doppler HAPS molto inferiore vs LEO (~50 kHz) → gestibile con compensation standard 3GPP Rel-17.
INT-6B-NTN-004 | Inter-Beam Handover (intra-HAPS) | Funzionale | HAPS gNodeB multi-beam (16-32 beam) | UE in motion (cross-beam boundary) | Bidirezionale signaling | Beam ID broadcast via SIB1; UE measurement RSRP/RSRQ per beam neighbor; handover trigger via A3 event (neighbor > serving + threshold); HO interruption time < 50 ms | 3GPP TS 38.331 (RRC); TS 38.300 (NR overall); TR 38.821 §7.4 (mobility NTN) | Telecom-NTN Payload Expert | Simulation handover + measurement campaign | Concept | medium | Per HAPS quasi-stazionario, handover intra-HAPS è rare (UE muove più della cella). HO inter-HAPS quando flotta dispiegata.
INT-6B-FEEDER-001 | Ka-band Feeder Link Downlink (HAPS → Gateway) | Funzionale + RF | HAPS AESA Ka-band antenna | Gateway HAPS ground station (parabola 3-5 m) | Unidirezionale (DL HAPS → Gateway) | Frequency 31-31.3 GHz (HAPS dedicated post-WRC-19); bandwidth 200-500 MHz; modulation DVB-S2X up to 64-APSK; capacity 1-10 Gbps; EIRP HAPS ≥ 60 dBW; rain fade margin Italia Zona K ≥ 15 dB | ITU-R F.1500/F.1891 (HAPS specs); ETSI EN 302 307-2 (DVB-S2X); ITU-R P.618-14 (rain fade) | Telecom-NTN Payload Expert + Ka-band RF Engineer | Link budget calculation + rain fade simulation + outage analysis | Concept | low | Ka-band 31 GHz HAPS-dedicated. Rain fade Genova Zona K ~25 dB @ 99.9% → margine richiesto significativo. ACM (Adaptive Coding & Modulation) mandatory.
INT-6B-FEEDER-002 | Ka-band Feeder Link Uplink (Gateway → HAPS) | Funzionale + RF | Gateway HAPS ground station transmitter | HAPS AESA Ka-band receiver | Unidirezionale (UL Gateway → HAPS) | Frequency 27.9-28.2 GHz (HAPS UL band post-WRC-19); EIRP Gateway 70-80 dBW (parabola 5 m + HPA 100W); UL capacity 100 Mbps - 1 Gbps | ITU-R F.1500; ITU RR Appendix 30B | Telecom-NTN Payload Expert | Link budget + interference analysis vs FSS | Concept | low | Coexistence con Fixed Satellite Service (FSS) GEO → coordination ITU. AGCOM autorizzazione individuale per gateway.
INT-6B-FEEDER-003 | Gateway HAPS ↔ Core Network 5G | Funzionale data | Gateway HAPS ground station | 5G Core Network (5GC) operator partner | Bidirezionale | N2/N3 interface SBA (Service Based Architecture); transport IP over MPLS; latency one-way ≤ 5 ms; throughput aggregato 10+ Gbps; integration AMF/SMF/UPF operator-side | 3GPP TS 23.501 (5G architecture); TS 29.281 (GTP-U); IETF RFC 3031 (MPLS) | Telecom-NTN Payload Expert + 5G Core Specialist | Integration test (lab + field) + interop testing | Concept | low | Richiede partnership con MNO italiano (TIM/Vodafone/WindTre) o operatore wholesale (Open Fiber). Modello business: capacity wholesale → operator delivers to UE.
INT-6B-OPS-001 | HALE Air Traffic Coordination (ENAV) | Regolatoria + operativa | Firmamento HALE Operations Center | ENAV ACC (Area Control Center) Milano | Bidirezionale (clearance + position reporting) | Flight plan ICAO IFR FL590-650 (18-20 km altitude); cleared corridor permanent (e.g. Genova FIR); ADS-B OUT transmission obbligatoria; latency reporting ≤ 60 s | ICAO Annex 11 (Air Traffic Services); ICAO Doc 4444 (PANS-ATM); Reg. UE 923/2012 SERA | Aviation Regulatory Counsel + HALE Operations Manager | Flight plan submission test + ATC coordination drill | Concept | low | Sub-interface di INT-14 Cap.4 per HALE. FL650 = 19.8 km, sopra controlled airspace UK ma in Italia tutto controlled space. Special arrangement con ENAV per HAPS-dedicated corridor.
INT-6B-OPS-002 | EUROCONTROL Cross-Border Coordination | Regolatoria | Firmamento HALE Operations Center | EUROCONTROL Network Manager (Brussels) | Bidirezionale (flight plan + slot) | Flight plan submission via IFPS (Initial Flight Plan Processing System); slot allocation se attraversa boundaries FIR; coordination con ANSP confinanti (Switzerland, France) se applicable | EUROCONTROL FPL format; ICAO Doc 7030 (Regional Supplementary Procedures) | Aviation Regulatory Counsel | Flight plan test + EUROCONTROL coordination | Concept | low | Sub-interface long-term per Percorso 6B operativo. HAPS station-keeping non attraversa boundaries → IFPS submission singola.
INT-6B-OPS-003 | HALE Launch & Recovery Site (Glider-style) | Operativa + fisica | HALE airframe | Launch site (runway grass ≥ 800 m oppure aerotraino con winch) | Operativa (singolo evento per missione) | Decollo: aerotraino con winch o motopropulsore singolo; quota cruise raggiunta dopo 6-8h salita; recovery: glide approach senza motore + grass runway; weather window stringente (wind ≤ 5 m/s @ ground, no rain) | FAA AC 91-79 (Mitigating Risks Associated with Approach and Landing); EASA AMC1 SPA.SPO (Specialised Operations) | HALE Operations Manager + Civil Works | Site survey + weather window analysis + recovery drill (subscale) | Concept | low | Pentema NON adatto come launch site (terreno montano). Site candidato: ex aeroporto Sarzana-Luni o aeroporto Albenga. Lead time site permitting ≥ 12 mesi.

## Trasversali
ID | Nome | Tipo | Parte A | Parte B | Direzione | Caratteristiche Tecniche | Standard / Protocollo | Owner | Test Method | Status | Confidence | Note
INT-X-CLOUD-001 | Cloud Hosting GAIA-X Compliant | Funzionale + regolatoria + contrattuale | Firmamento Cloud Workload (data + apps) | Cloud Provider GAIA-X compliant (Aruba/OVH/IONOS) | Contrattuale | Provider GAIA-X Label Level 2+ (data sovereignty); region IT or EU; SLA uptime ≥ 99.9% (Tier 3); RPO ≤ 4h; data residency garantita; subprocessor list GDPR Art. 28 | GAIA-X Compliance Framework v22.10; ISO/IEC 27001; SOC 2 Type II; CSA STAR Level 2 | Cloud Architect + Procurement + DPO | Provider audit + GAIA-X attestation review + data residency test | Concept | high | Sub-interface di INT-20 Cap.4. Aruba ha label GAIA-X confermato 2025. OVH Italia/IONOS pari opportunità. Hyperscaler USA (AWS/Azure/GCP) NON GAIA-X compliant per default.
INT-X-PRIVACY-001 | Data Subject Access Request (DSAR) Workflow | Regolatoria + operativa | Data Subject (cittadino, cooperativo, dipendente) | DPO Firmamento + Customer Support | Bidirezionale (request + response) | Channels: email PEC dpo@firmamento.tech, web form, postal mail; response 30 gg max (extension +60 gg motivata); right: access, rectification, erasure (Art. 15-17 GDPR), portability (Art. 20), restriction (Art. 18), objection (Art. 21) | GDPR Reg. UE 2016/679 Art. 12-22; EDPB Guidelines 01/2022 (Data Subject Rights) | DPO + Customer Support | DSAR drill (semestrale) + response time audit | Concept | high | Workflow standard GDPR. Necessario tooling (es. OneTrust o open-source) per scale Y2+.
INT-X-CYBER-001 | Penetration Testing + Vulnerability Management | Regolatoria + sicurezza | Firmamento attack surface (apps + infra + UAS) | Pentest Provider (TÜV / DNV / Yarix) | Servizio professionale | Pentest annuale: external + internal + web app + API; CVE scanning monthly (Nessus/Qualys); patch SLA Critical 7gg / High 30 gg / Medium 90 gg; bug bounty Y3+ opzionale | OWASP Testing Guide v4.2; PTES (Penetration Testing Execution Standard); ISO/IEC 27001 A.12.6 | Cybersecurity Engineer + CISO (Y3+) | Pentest report + remediation tracking + retest | Concept | high | Necessario per NIS2 art. 21 misure tecniche. Costo annuale stimato €15-30k per pentest semplice; €50-100k per Red Team esercizio completo.
INT-X-LOGGING-001 | Centralized Logging + Audit Trail | Funzionale + regolatoria | All system components (UAS + GS + Cloud + Apps) | SIEM Central (e.g. Elastic SIEM, Wazuh, Splunk) | Unidirezionale (components → SIEM) | Log levels: INFO + WARN + ERROR + AUDIT (security events); format JSON structured; correlation rules pre-built; retention 90 gg hot + 1 anno cold + 5 anni legal hold | RFC 5424 Syslog; CEF Common Event Format; NIST SP 800-92 (Log Management); GDPR Art. 32 (accountability) | DevOps + Cybersecurity Engineer + DPO | Log ingestion test + retention verification + audit | Concept | high | Sub-interface di INT-12 Cap.4. ELK stack open-source consigliato per Y1-Y2 budget.
INT-X-VENDOR-001 | Vendor SLA Framework (UAS Manufacturer) | Contrattuale | Firmamento Technologies (buyer) | UAS Vendor (JOUAV / Tekever / Quantum / FlyingBasket) | Contratto fornitura | Delivery lead time ≤ 12 settimane post-PO; warranty 24 mesi parts + 12 mesi service; spare parts availability 5+ anni; training 5 gg incluso; technical support 24h response; supplier audit AS/EN 9100 | AS/EN 9100D (Quality Mgmt Aerospace); ICAO Annex 19 (Safety Mgmt); contratto fornitura ex artt. 1470-1547 c.c. | Procurement Lead + Quality Manager | Vendor audit + warranty claim simulation + SLA monitoring | Concept | medium | Sub-interface di INT-16 Cap.4. Pre-RFQ engagement M+1-M+6. Selezione finale post-Trade Study M+8. FALSIFYING: vendor cinese (JOUAV) potrebbe avere export control issues post-evoluzione geopolitica → necessario vendor alternativo EU (Tekever PT, Quantum Systems DE).

## Compatibility_Matrix
Compatibility Matrix (interfacce critiche 6A)
| INT-6A-PHY-001 | INT-6A-PHY-005 | INT-6A-PHY-007 | INT-6A-PHY-009 | INT-6A-PHY-010 | INT-6A-DATA-006 | INT-6A-DATA-007 | INT-6A-DATA-008 | INT-6A-C2-001 | INT-6A-C2-003
INT-6A-PHY-001 | — | OK | Check (mass+thermal) | OK | OK | OK | OK | OK | OK | OK
INT-6A-PHY-005 | OK | — | OK | OK | OK | OK | OK | OK | OK | OK
INT-6A-PHY-007 | Check (mass+thermal) | OK | — | OK | OK | OK | OK | OK | OK | OK
INT-6A-PHY-009 | OK | OK | OK | — | OK (power dependency) | OK | OK | OK | OK | OK
INT-6A-PHY-010 | OK | OK | OK | OK (power dependency) | — | OK | OK | OK | OK | OK
INT-6A-DATA-006 | OK | OK | OK | OK | OK | — | OK | OK | OK | OK
INT-6A-DATA-007 | OK | OK | OK | OK | OK | OK | — | OK | OK | OK
INT-6A-DATA-008 | OK | OK | OK | OK | OK | OK | OK | — | OK | OK
INT-6A-C2-001 | OK | OK | OK | OK | OK | OK | OK | OK | — | OK
INT-6A-C2-003 | OK | OK | OK | OK | OK | OK | OK | OK | OK | —
Legenda
— | Self (diagonal)
OK | Compatibile (nessun conflitto rilevato)
Check | Richiede verifica multi-dominio (es. mass+thermal+EMC)
Conflict | Conflitto identificato → mitigation richiesta

## Test_Plan
ID Interfaccia | Nome | Test Method | Test Phase | Test Environment | Pass/Fail Criteria | Owner | Timing (M+)
INT-6A-PHY-001 | Airframe ↔ Payload Bay | Inspection + CG analysis + shake table | DDT (Design + Devel Test) | Vendor facility (JOUAV) + lab | CG shift ≤ 2% MAC; vibration spectrum within MIL-STD-810H Cat 4 envelope; no payload bay damage 100h cumulative | Avionics Integration Lead | M+10-M+12
INT-6A-PHY-002 | Payload Power Rail 28 VDC | Lab bench + transient injection + load step | DDT | Lab elettronica Firmamento | Voltage 28 VDC ±5%; ripple ≤ 200 mV pk-pk; transient recovery < 50 ms; load step 0→100 W stable | Power Mgmt SE | M+10
INT-6A-DATA-001 | Payload EO RGB → MC | Image capture + geotag + throughput | DDT | Lab + outdoor test | 5 fps stable; geotag accuracy ±5m horizontal; throughput ≥ 500 MB/s sustained | Payload SE | M+11
INT-6A-C2-001 | C2 Uplink Primary RF | Range test + fade margin + spectrum analyzer | DDT + Field Test | Campo aperto Pentema (M+11 limitato) | Range LOS ≥ 50 km; fade margin ≥ 12 dB; BER ≤ 1e-5 @ nominal range | RF Systems Engineer | M+11 (limited) + Fase 1
INT-6A-C2-003 | SATCOM Iridium L-band | Link test + handover + latency | Integration Test | Vendor lab + field | Throughput ≥ 22 kbps continuous; handover seamless; latency one-way ≤ 400 ms | Avionics Lead | Fase 1 M+13-M+15
INT-6A-C2-004 | Lost-Link Procedure | HIL simulation + flight test | Verification | HIL bench + flight test (autorizzato) | RTH triggered within 5 s lost-link; emergency land if RTH fail; SMS alert delivered | Avionics Lead + Safety | Fase 1 M+16-M+18
INT-6A-GS-004 | PC Emergency Trigger | Tabletop exercise + scenario sim | Validation | GCS Pentema + Sala Operativa PC | Acknowledge ≤ 5 min; launch decision ≤ 15 min; ortofoto live ≤ 30 min | Operations Lead + PC | M+6-M+9 (tabletop) + Fase 1 (flight)
INT-6A-REG-001 | ENAC SORA Authorization | Documentation review + ENAC feedback | Regulatory Compliance | Sede ENAC + remote | Pre-application meeting completato M+6; SORA application accepted; SAIL III authorization issued | Aviation Regulatory Counsel | M+3-M+6 (pre-app) + Fase 1 (final)
INT-6A-REG-002 | AGCOM Spectrum Auth | Doc review + AGCOM response | Regulatory Compliance | Sede AGCOM + remote | Consultazione AGCOM response ≤ M+4; spectrum allocation confirmed (or fallback ISM accepted) | Aviation Reg Counsel + RF SE | M+1-M+4
INT-6A-REG-004 | Garante DPIA | DPIA review + DSAR drill | Regulatory Compliance | Internal + Garante (se notifica preventiva) | DPIA signed DPO M+5; DSAR drill PASS (response ≤ 30 gg simulated) | Data Privacy Counsel + DPO | M+4-M+5 + ongoing
INT-6A-GS-003 | Cooperative Dashboard | Functional + RBAC + accessibility | Validation | Cloud staging + browser test | All functional tests PASS; RBAC correct per polygon; WCAG 2.1 AA compliance | Cloud Architect + DPO | Fase 1 M+14-M+16
INT-6A-GS-007 | Data Anonymization | AI inference quality test | Validation | Cloud + dataset test | Face/plate blurring false negative rate ≤ 1%; processing ≤ 5 min/ortofoto | DPO + AI/ML Engineer | Fase 1 M+15-M+17
INT-6B-PHY-001 | HALE Solar Array Bonding | Lap shear + thermal cycling + UV | Subscale Test | Lab subscale + thermal chamber | Bonding strength ≥ 5 MPa; 100 thermal cycles -65/+40°C no delamination; UV 1000h no degradation | Aero-Struct Engineer | Fase 3 M+36-M+42
INT-6B-PHY-002 | HALE Wing-Fuselage Joint | FEA + GVT + structural test | Subscale + Component Test | FEA bench + GVT facility (CIRA / DLR) | Joint ultimate load 75 kN factor 1.5; flutter clearance ≥ 20% margin VD | Aero-Struct Engineer | Fase 3 M+36-M+44
INT-6B-NTN-001 | 5G NR-NTN Service DL | Link budget sim + OTA test | Lab Test | 5G NTN testbed (TIM/Vodafone partnership) | Capacity per beam ≥ 50 Mbps; coverage 50 km diameter @ 20 km altitude | Telecom-NTN Expert | Fase 3 M+40-M+46
INT-6B-FEEDER-001 | Ka-band Feeder DL | Link budget + rain fade sim | Lab + Simulation | Lab RF + ITU-R simulation | EIRP ≥ 60 dBW; rain fade margin ≥ 15 dB Zona K Italia | Ka-band RF Engineer | Fase 3 M+40-M+45
INT-X-CLOUD-001 | Cloud GAIA-X | Provider audit + attestation review | Procurement Validation | Remote audit | GAIA-X Label Level 2+ confirmed; data residency IT/EU verified; SLA SLA met during baseline measurement | Cloud Architect + Procurement | M+5-M+9
INT-X-PRIVACY-001 | DSAR Workflow | DSAR drill + audit | Validation | Internal + simulated user | Response ≤ 30 gg; all rights operational (access, erasure, portability); audit log complete | DPO + Customer Support | Fase 1 M+15-M+17
INT-X-CYBER-001 | Pentest + Vuln Mgmt | External pentest annuale | Verification | Production + staging | No Critical CVE unpatched > 7 gg; pentest report no Critical findings unmitigated | Cybersecurity Engineer | Fase 1 M+16-M+18 + annuale
INT-X-VENDOR-001 | Vendor SLA UAS | Vendor audit + SLA monitoring | Procurement Validation | Vendor site visit + ongoing monitoring | AS/EN 9100 cert verified; lead time ≤ 12 wk; warranty terms confirmed; reference customer verified ≥ 2 | Procurement Lead + QM | M+1-M+6 (pre-engagement) + Fase 1 (contract)

## Risk_Register_Interfacce
RISK-ID | Interfaccia coinvolta | Descrizione rischio | Probabilità (1-5) | Impatto (1-5) | P×I | Mitigazione | Owner | Closure target
RSK-INT-001 | INT-6A-C2-001 | Shadow zones C2 RF 2.4 GHz in valle Pentema → loss link | 4 | 4 | 16 | Doppio link RF + SATCOM Iridium (INT-6A-C2-003); RTH automatico < 5 s | Avionics Lead | Fase 1 M+18
RSK-INT-002 | INT-6A-REG-001 | ENAC valuta Pentema 'area sensibile' (parco Aveto) → SAIL IV richiesto | 3 | 5 | 15 | Pre-application early M+3; alternative site analysis; coordination Comune+Regione+ENAC | Aviation Reg Counsel | M+6
RSK-INT-003 | INT-6A-REG-002 | AGCOM rifiuta licenza individuale 2.4 GHz EIRP > 100 mW → range limitato | 3 | 4 | 12 | Fallback ISM 100 mW + SATCOM Iridium; alternative spectrum L-band Iridium primario | Aviation Reg Counsel + RF SE | M+4
RSK-INT-004 | INT-6B-PHY-001 | Solar array bonding fail thermal cycling stratosfera → delamination | 3 | 5 | 15 | R&D dedicato Fase 3; test panel qualification ECSS | Aero-Struct Engineer | Fase 3 M+42
RSK-INT-005 | INT-6B-PHY-003 | Battery thermal mgmt heater > 80W → energy balance inverno deficit | 4 | 5 | 20 | Showstopper RSK-TEC-001 cross-reference; design alternativi (E5 Seasonal-only) | Thermal Eng + Battery Specialist | Fase 3 M+38
RSK-INT-006 | INT-6B-NTN-001 | Spettro S-band n255 contestato MNO terrestri → no spectrum sharing | 4 | 4 | 16 | Engagement TIM/Vodafone partnership; alternative banda HAPS dedicata C-band 6.4 GHz | Telecom-NTN Expert + Reg | Fase 3 M+40
RSK-INT-007 | INT-X-VENDOR-001 | Vendor JOUAV (CN) blocked by export control EU post-tensione geopolitica | 3 | 4 | 12 | Vendor alternativi EU (Tekever PT, Quantum DE, FlyingBasket IT); RFQ multi-vendor | Procurement Lead | M+6 (alternativa identificata)
RSK-INT-008 | INT-6A-C2-007 | Non-cooperative DAA non maturo TRL → SORA SAIL III non autorizzato senza | 3 | 4 | 12 | Mitigazione operativa (geofencing, NOTAM, ore volo limitate); R&D DAA EO Fase 1+ | Avionics Lead + DAA Spec | Fase 1 M+18
RSK-INT-009 | INT-6A-REG-004 | Garante richiede notifica preventiva Art. 36 → lead time +3-6 mesi | 2 | 4 | 8 | DPIA early M+4-M+5; engagement Garante preliminary se possibile | Data Privacy Counsel + DPO | M+5
RSK-INT-010 | INT-6A-GS-007 | Data anonymization quality insufficiente → Garante audit fail | 3 | 4 | 12 | AI inference quality threshold strict; manual review pipeline; opt-in workflow | DPO + AI/ML Engineer | Fase 1 M+17
RSK-INT-011 | INT-6A-PHY-010 | Backhaul fibra Pentema non disponibile → Starlink-only inadeguato per SLA | 3 | 3 | 9 | Dual provider FWA + Starlink; engagement Open Fiber/Linkem early; UPS + buffering | IT Operations + Cloud Architect | Fase 1 M+15
RSK-INT-012 | INT-6A-REG-005 | Mercato assicurativo UAS BVLOS hardened post-incidenti UK 2024-25 → premi 5-10x | 3 | 3 | 9 | Broker engagement early; multi-quote; possibili captive arrangement Y3+ | CFO + Insurance Broker | Fase 1 M+15-M+18

## Versioning_Roadmap
Versione | Milestone | Data target | Scope | Numero interfacce | Status target | Owner approval
v0.5 | Cap. 4 §4.4 baseline | M+3 (Mag 2026) | 20 interfacce primarie identificate (ICD preliminary nel Capitolo 4) | 20 | Concept + Preliminary mix | PMO Firmamento
v1.0 | Vol. 2 Allegato A.4 baseline | M+3-M+6 (Mag-Ago 2026) | 50 interfacce dettagliate (current document); 7 categorie + risk register + test plan | 50 | Concept + Preliminary mix; high-confidence sui standard COTS | Senior SE + Integration Lead
v1.5 | Post-pre-engagement vendor + ENAC/AGCOM feedback | M+6-M+8 (Ago-Ott 2026) | Specifications updated post-vendor RFQ responses; INT-6A-REG-001/002 refined post-ENAC/AGCOM response | 50-55 (potenziali nuove) | Preliminary maggioranza; alcune Detailed | SE Lead + Procurement + Reg Counsel
v2.0 | Detailed ICD pre-Phase 1 execution | M+10-M+12 (Dic 2026-Feb 2027) | Byte-level format, latency end-to-end budget, failure mode behaviors, ICD frozen per vendor contracts | 55-65 | Detailed (all 6A); Concept (6B) | SE Lead + Vendor Liaison + Customer
v2.5 | Post-First Flight 6A | M+20-M+24 (Ago-Dic 2027) | Interfacce validate in-flight; lessons learned incorporated; SLA backhaul/cloud measured baseline | 65 | Validated (6A); Preliminary (6B) | Operations Lead + V&V Engineer
v3.0 | HALE 6B Phase B closure | M+48-M+60 (Y4-Y5) | ICD 6B Detailed completo post-subscale flight test; preparazione Phase C-D | 80-100 | Detailed (6A operational); Preliminary-Detailed (6B subscale) | Senior SE + HALE Program Manager