## Cover
A.5 -- VERIFICATION & VALIDATION PLAN v1.0
Firmamento Technologies -- Studio di Fattibilita' HALE / VTOL
Volume 2 -- Allegato A.5 -- Generato 2026-05-17
Scope
Plan di verifica e validazione di tutti i requisiti di sistema (SyR) e
subsystem (SsR) del progetto HALE/VTOL, suddiviso per i due percorsi:
-- Percorso 6A VTOL operativo (Phase A -> Phase B -> Phase C)
-- Percorso 6B HALE R&D (Phase B subscale ground + flight)
Conformita': NASA SE Handbook Rev 2 §5.3 (Verification) + §5.4 (Validation)
Allineamento con cap-03-requisiti §3.7, cap-06-tecnica §6.6, cap-09 Gate.
Metodi V&V standard (4)
I -- Inspection | Verifica documentale/visiva (datasheet, BoM, label, process audit).
A -- Analysis | Calcoli, simulazioni, modeling (link budget, energy balance, FMECA).
D -- Demonstration | Esercizio operativo del sistema (qualitative, no measurement).
T -- Test | Misure quantitative su prototype/articolo di volo.
Fasi V&V (NASA SE V-model)
Pre-Phase A (M+0-3) | Inspection compliance documentale (C series)
Phase A (M+3-12) | Analysis (link budget, energy balance, FMECA, FTA)
Phase B (M+12-24) | Demonstration test bed + Test subscale (6A operativo)
Phase C (M+24+) | Test full-scale + operational validation
Phase B 6B (M+24-48) | Lab + subscale 1:3 + stratospheric subscale flight
Sheets in this workbook
Cover | Documento di copertura
VV_Matrix_SyR | V&V matrix: 71 requisiti SyR/SsR/IR
VV_Methods_Detail | Dettaglio dei 4 metodi I/A/D/T con esempi
Test_Facilities | Test facility catalog (16 facility)
Test_Schedule | Gantt test schedule (21 attivita')
Test_Costs | CapEx + OpEx test (20 voci)
Independent_Verification | Independent verification (9 review)
VV Matrix statistics
Totale requisiti tracciati: 71
Method I (Inspection): 29
Method A (Analysis): 25
Method D (Demonstration): 17
Method T (Test): 37
Distribuzione per fase (req che includono la fase):
Pre-A: 3
A: 24
B: 51
C: 27

## VV_Matrix_SyR
Req-ID | Description | Family | Method | Phase | Owner | Test Facility | Document Evidence | Status | Risk-ID link | Trade Study link | Notes
SyR-F-001 | Sistema esegue missione EO sorvolando Pentema (waypoint-based) | F | D | B | vtol-uas-specialist | Sito Pentema + GS mobile | Test report MIS-F-001 | Planned | – | TS-PLATFORM-6A | Demo end-to-end mission ConOps
SyR-F-002 | Sistema esegue ricognizione area (raster) <=15 km^2 | F | A+D | A,B | aerospace-SE | Simulator + sito Pentema | Mission plan analysis + demo log | Planned | – | TS-PAYLOAD-EO | A: copertura geometrica, D: raster reale
SyR-F-003 | Rileva hotspot >=40 degC, alert + thumbnail in <=5 min | F | D+T | B,C | EO-expert | Test bed fuoco controllato + GS | VR-F-003.1 + VR-F-003.2 | Planned | RSK-OPS-002 | – | Demo scenario fuoco + analysis FAR target <=5%
SyR-F-004 | Genera ortomosaico georef <=8 h dalla landing | F | A+D | B | EO-expert | Pipeline cloud processing | Analysis pipeline + demo timing | Planned | – | – | Catena Pix4D/OpenDroneMap on-premise
SyR-F-005 | Fornisce link voice/dati P2P emergenza durante evento | F | D+T | B | telecom-payload | Site Pentema + LTE emulator | Test report COMMS-F-005 | Planned | – | TS-COMMS | Demo con apparato tactical LTE Athonet/Druid
SyR-P-001 | Autonomia sortie >=4 h con payload 4 kg | P | A+T | A,C | propulsion-energy-engineer | Cella batterie + flight test | Analysis energy + test report | Planned | – | TS-PLATFORM-6A | A: energy balance VTOL, T: flight log timestamp
SyR-P-002 | Velocita' cruise nominale 90-110 km/h | P | A+T | A,C | aerospace-SE | XFLR5 + flight test | Polare + flight log | Planned | – | – | Polare drag preliminary + GNSS speed log
SyR-P-003 | Quota operativa nominale 500-1500 m AGL Appennino | P | A+T | A,C | vtol-uas-specialist | Sito Pentema | Flight log altimeter | Planned | – | – | Verifica autorizzata SAIL III ENAC
SyR-P-004 | Resistenza vento sostenuto <=17 m/s | P | T | C | vtol-uas-specialist | Sito di volo windy + meteo | Flight test wind envelope | Planned | RSK-OPS-001 | – | Demonstrated handling 15-17 m/s gusts
SyR-P-005 | GSD camera EO <=5 cm @ 500 m AGL | P | A+T | A,B | EO-expert | Camera test bench + cal range | Spec sheet + cal report | Planned | – | TS-PAYLOAD-EO | GSD = pixel_size * d / focal_length
SyR-P-006 | NEdT IR sensor <=50 mK | P | A+T | A,B | EO-expert | Blackbody source lab | Calibration cert + lab report | Planned | – | TS-PAYLOAD-EO | Verifica con corpo nero a temperatura controllata
SyR-P-007 | C2 link RF range >=30 km LOS, fade margin >=12 dB | P | A+T | A,C | telecom-payload | Range test ground + flight test | Link budget + RSSI log | Planned | RSK-TEC-005 | TS-COMMS | Analisi: allegato A.7 link budget. Test: RSSI in volo.
SyR-O-001 | Lost-Link Return-to-Base profile <=120 s dall'evento | O | D | B | avionics-gnc-engineer | HIL simulator + flight test | HIL run + flight test trigger | Planned | RSK-TEC-007 | TS-AVI-6A | Demo deliberate link-loss test
SyR-O-002 | Set-up GS deployable in <=30 min (training operator) | O | D | B,C | vtol-uas-specialist | GS mobile in field | Time-motion demo | Planned | – | – | Cronometro setup field di operator trained
SyR-O-003 | Swap payload modulare ground-side <=90 min (target 30) | O | D | B | vtol-uas-specialist | Hangar test | Time-motion demo + cal post-swap | Planned | – | – | Red Team review §6.8 Cap.6: 30 min e' stretch, 60-90 realistic
SyR-S-001 | FMECA preliminary completo con RPN top 5 con mitigation | S | I+A | A | systems-engineer | Office (analysis) | Allegato A.2 Risk Register + FMECA | Done | – | – | Inspection: existence + completeness
SyR-S-002 | FTA top event 'Loss of Vehicle in BVLOS' <= 10^-5/h | S | A | A | systems-engineer | Office (analysis) | FTA report Vol.2 A.2 | Planned | RSK-TEC-007 | – | Target SAIL III ENAC = 10^-5/h
SyR-S-003 | Sistema parachute deploy in <=3 s da trigger | S | T | B | vtol-uas-specialist | Drop test rig | HSC video drop test + log | Planned | – | – | Drop test indoor o esterno, alt 50 m, deployment time on log
SyR-S-004 | Geofence aree residenziali enforced (no overflight built-up) | S | D+I | B,C | avionics-gnc-engineer | HIL + GS | HIL test report + ConOps doc inspection | Planned | RSK-TEC-006 | – | Demo penetration attempt -> auto-redirect
SyR-E-001 | Operazioni in T amb. -10 / +30 degC | E | T | C | vtol-uas-specialist | Climatic chamber + sito Pentema | Cold-soak + hot-soak test | Planned | RSK-OPS-001 | – | Lab climatic chamber + field winter test
SyR-E-002 | Operazioni in pioggia <=10 mm/24h | E | I+T | C | vtol-uas-specialist | Rain test rig + field | IP rating cert + field test | Planned | – | – | IP54 minimum vendor spec + field validation
SyR-E-003 | Storage shelter UAV +/- 5 degC ambient operation | E | I | C | vtol-uas-specialist | Hangar Pentema | Spec sheet hangar + thermal log | Planned | – | – | Walkthrough hangar + datalogger 30 giorni
SyR-C-001 | UAS classified Class C5 + tipo Specific Category | C | I | Pre-A,A | aviation-regulatory-counsel | Doc review | DoC + EASA UAS class label | Planned | – | – | Inspection: vendor DoC + EU Reg 2019/945
SyR-C-002 | ConOps SORA SAIL <=III Pentema BVLOS approved ENAC | C | I | Pre-A,A | aviation-regulatory-counsel | ENAC office (paper) | ENAC autorizzazione + GRC computation | Open | RSK-REG-002 | – | Pre-application meeting M+3-6, full sub M+6
SyR-C-003 | Spettro radio C2 conforme AGCOM/PNRF | C | I | Pre-A,A | telecom-payload | AGCOM (paper) | ETSI EN 300 328 DoC + license se >100mW | Planned | – | TS-COMMS | Inspection: EN 300 328 + EIRP measurement
SyR-C-004 | DPIA per missioni con immagini privacy compliant | C | I | A,B | data-privacy-counsel | Office | DPIA + audit Garante | Planned | RSK-TEC-006 | – | Pubblica DPIA + workshop comunita' Pentema
SyR-C-005 | Insurance per BVLOS coverage TPL >=10 M EUR | C | I | B | program-manager | Broker office | Insurance policy doc | Planned | – | – | Verifica polizza con specific endorsement BVLOS
SyR-C-006 | Cybersecurity compliance NIS2 Article 21 | C | I+A | A,B | aerospace-SE | Audit ACN-compliant | NIS2 self-assessment + 3rd-party audit | Planned | – | – | ACN reference framework + ENISA guidelines
SyR-Cost-001 | CapEx Y1 <=1.2 M EUR (target 900k) | Cost | I+A | A,B | financial-cfo-analyst | Office | Quadro Economico + Allegato Financial Model | Planned | RSK-FIN-001 | – | Inspection budget + Analysis sensitivity
SyR-Cost-002 | OpEx Y2 run-rate <=600k EUR (incl. regulatory FTE) | Cost | I | B,C | financial-cfo-analyst | Office | Financial report Y1+Y2 | Planned | RSK-FIN-001 | – | Post audit DR-014 OpEx aggiornato +600k personnel reg.
SyR-Cost-003 | Revenue Y1 cumulato >=200 k EUR (cf. Cap.7) | Cost | I | C | business-model-strategist | Office | Revenue ledger Y1 | Planned | – | – | Tracking commercial pipeline pilot
SsR-AERO-001 | L/D cruise >=15 (HALE) o aerod. envelope VTOL | P | A+T | A,B | aero-structures-engineer | XFLR5 + wind tunnel subscale | CFD report + wind tunnel test | Planned | – | TS-MATERIAL | Phase A CFD + Phase B wind tunnel 1:5
SsR-AERO-002 | Limit load factor n=+3.8/-1.5 (CS-23 equivalent) | S | A+T | A,B | aero-structures-engineer | FEA + structural test | FEA report + test rig | Planned | – | TS-MATERIAL | Structural test ad ultimate load + 50%
SsR-AERO-003 | Flutter speed margin >=20% rispetto VD | S | A+T | B | aero-structures-engineer | GVT + aeroelastic analysis | GVT report + p-k analysis | Planned | RSK-TEC-002 | – | Ground Vibration Test prima del flight test
SsR-PROP-001 | Energy balance HALE inverno 44N margine >=20% | P | A | A | propulsion-energy-engineer | Sim. solar + DLR data | Allegato A.7 Energy Balance Report | Done | RSK-TEC-001 | TS-PROP-6B | Sim. completa M+10 (gate G3)
SsR-PROP-002 | Pannello solare efficienza modulo >=24% | P | I+T | B | propulsion-energy-engineer | Solar simulator lab | IEC 60904 test cert | Planned | – | TS-PROP-6B | Verifica con flash solar simulator AM1.5
SsR-PROP-003 | Batteria pack-level energy density >=350 Wh/kg (LiS) | P | I+T | B,C | propulsion-energy-engineer | Battery cycler lab | Discharge curve + spec | Planned | RSK-TEC-001 | TS-PROP-6B | Test pack-level a C/3 discharge 0-100%
SsR-PROP-004 | Engine VTOL hybrid runtime >=4 h, fuel <=8 kg | P | T | C | propulsion-energy-engineer | Engine test cell + flight test | Bench run + flight log | Planned | – | – | Cell test 4h continuous + correlate flight
SsR-AVI-001 | Autopilota FCS DAL-C (DO-178C objectives lvl C) | S | I+A | B | avionics-gnc-engineer | Test bed + audit DO-178C | DAL-C cert + verification trace | Planned | – | TS-AVI-6A | If commercial autopilot, check vendor DAL cert
SsR-AVI-002 | GNSS spoofing/jamming detection + alert | S | T | B | avionics-gnc-engineer | GNSS sim. + RF chamber | Spoof test + alert log | Planned | RSK-TEC-005 | – | GNSS simulator with replay/spoofing scenarios
SsR-AVI-003 | IMU redundancy 2 of 3 voting active | S | D | B | avionics-gnc-engineer | HIL test | HIL fault injection report | Planned | – | TS-AVI-6A | Fault injection con IMU disabled
SsR-AVI-004 | Lost-Link auto-RTB profile loaded + tested | O | D | B,C | avionics-gnc-engineer | HIL + flight test | HIL + flight trigger test | Planned | RSK-TEC-007 | TS-AVI-6A | OSO #9 SORA compliance
SsR-PAY-001 | Camera RGB 24 MP rolling/global shutter <=1/2000s | P | I+T | B | EO-expert | Cal range optical bench | Spec + MTF measurement | Planned | – | TS-PAYLOAD-EO | MTF and motion-blur lab measurement
SsR-PAY-002 | IR LWIR 640x512 NEdT <=50 mK GSD <=5 m @500 m AGL | P | I+T | B | EO-expert | Blackbody lab + cal range | Cal cert + lab report | Planned | – | TS-PAYLOAD-EO | NUC + crosscheck con RGB (cf. FMECA item RPN 48)
SsR-PAY-003 | Onboard storage redundant RAID, >=1 TB sortie capacity | P | I+T | B | EO-expert | Bench test rig | Spec + IOPS log | Planned | – | – | Storage cycle test + fault injection
SsR-PAY-004 | Edge AI hotspot detection FAR <=5% per 1k events | F | A+T | B,C | EO-expert | Synthetic dataset + field trial | ROC curve + field test | Planned | RSK-OPS-002 | – | Algorithm pre-training su dataset Italia
SsR-COMMS-001 | C2 link RF + SATCOM fade margin >=12 dB | P | A+T | A,C | telecom-payload | Range test + flight test | Allegato A.7 LB + RSSI log | Planned | RSK-TEC-005 | TS-COMMS | Link budget A.7 + measured fade margin in flight
SsR-COMMS-002 | Data downlink throughput >=50 Mbps EO 20 km LOS | P | A+T | A,B | telecom-payload | Range test + spectrum analyser | LB + measured throughput | Planned | – | TS-COMMS | 5 GHz UHF licensed; verifica con iperf in volo
SsR-COMMS-003 | Encryption AES-256 + auth on C2 link | S | I+T | B | telecom-payload | Crypto bench + penetration test | Crypto cert + pen-test report | Planned | RSK-TEC-005 | – | Verifica FIPS 140-2 module + pen-test
SsR-COMMS-004 | HAPS service link C/N0 >=80 dB-Hz @25 km nadir | P | A | A | telecom-payload | Office (analysis) | Allegato A.7 LB ServiceLink | Done | – | TS-COMMS | Riferimento allegato A.7 -- LB_ServiceLink_6B
SsR-COMMS-005 | HAPS feeder link Ka 31 GHz availability 99.9% | P | A | A,B | telecom-payload | Office + range test Phase B | LB Ka + site coordination doc | Planned | – | TS-COMMS | Site diversity gateway secondary >10 km
SsR-GS-001 | GS riceve alert + push interfaccia PC in <=60 s | P | D | B,C | aerospace-SE | GS test bed + PC interface | Latency test report | Planned | – | – | Demo end-to-end con stopwatch
SsR-GS-002 | GS 24/7 monitoring CPU/storage health auto-alert | O | I+D | B,C | aerospace-SE | GS Pentema | Monitoring dashboard + drill | Planned | – | – | Walkthrough check NOC + simulated outage
SsR-GS-003 | Data export PA (Regione/PC) standard INSPIRE WMS/WFS | O | I | C | EO-expert | Cloud server | Endpoint test + INSPIRE compliance | Planned | – | – | WMS/WFS endpoints accessible to clients
SsR-HALE-001 | HALE subscale 1:3 prototype TRL 5 by M+36 | P | D+T | B | aero-structures-engineer | Test site Sardegna / EuroHAPS analog | Subscale flight test | Open | RSK-TEC-002 | – | Phase B 6B exit criterion gate G6
SsR-HALE-002 | HALE stratospheric flight >=24 h continuous | P | T | C | aero-structures-engineer | Test site + chaser | Flight test perennial >24h | Open | RSK-TEC-001 | – | Out-of-scope studio attuale (Phase C+ HALE)
SsR-HALE-003 | HALE controllo posizione +/- 10 km vento strato | P | A+T | B,C | avionics-gnc-engineer | HIL strat + flight test | HIL strat sim + flight log | Open | – | – | Modello vento stratosferico WMO climatology
IR-PAY-001 | Payload power interface 28 VDC +/- 5%, 200 W max | C | I+T | B | aerospace-SE | Bench power supply test | ICD inspection + test report | Planned | – | – | ICD allegato A.4 + test bench measurement
IR-PAY-002 | Payload data interface Ethernet 1 GbE | C | I+T | B | aerospace-SE | Bench test | ICD + iperf test | Planned | – | – | Verify connector, pinout, throughput
IR-GS-001 | GS-Cloud upload bandwidth >=100 Mbps shared | P | I+T | B | aerospace-SE | Pentema connectivity test | Speedtest + ISP SLA | Planned | – | – | Verifica connettivita' Open Fiber/TIM Pentema
SyR-O-004 | Pilota UAS certificato STS-01 SORA dedicated | O | I | A,B | vtol-uas-specialist | Doc review | ENAC pilot certificate | Planned | – | – | Verifica certificazione operatore + pilot
SyR-O-005 | Maintenance interval pre-flight check <=30 min | O | D | B,C | vtol-uas-specialist | Hangar | Checklist run + timing | Planned | – | – | Manuale MM allegato A.X
SyR-O-006 | Mission planner GS automatizza waypoint + no-fly check | O | D | B | avionics-gnc-engineer | GS test bench | Demo planning + no-fly enforcement | Planned | – | – | Auto-check NOTAMs + restricted areas
SyR-S-005 | Lithium battery thermal runaway containment box | S | T | B | propulsion-energy-engineer | Battery abuse test cell | Nail penetration + thermal test | Planned | – | – | UN 38.3 + JEDEC battery abuse tests
SyR-E-004 | Operazioni soggette a finestra meteo nominale (no temporali) | E | I | B,C | vtol-uas-specialist | Meteo forecast service | ConOps doc + go/no-go decision tree | Planned | RSK-OPS-001 | – | ARPA Liguria forecast feed integration
SyR-E-005 | EMI/EMC compliance EN 55032 + DO-160G section 20 | C | I+T | B | avionics-gnc-engineer | EMC chamber accredited | EMC test report | Planned | – | – | Conducted + radiated emissions
SyR-F-006 | Generazione DEM 3D area >=10 km^2 con precisione <=20 cm | F | A+T | B,C | EO-expert | Cloud processing + GCP cal | DEM accuracy report | Planned | – | – | Confronto con GCPs noti misurati GPS RTK
SyR-F-007 | Trasmissione live video bassa risoluzione 720p<=3s latency | F | T | B,C | telecom-payload | Range test + GS | Latency test report | Planned | – | TS-COMMS | Critical per PC use case real-time
SyR-F-008 | Logging black-box flight data + payload data on landing | F | I+D | B | avionics-gnc-engineer | Bench + flight test | Black-box dump + replay | Planned | – | – | Crash-survivable enclosure spec
SsR-HALE-004 | Aeroelastic analysis HALE wing nonlineare | S | A | A,B | aero-structures-engineer | CFD/CSD coupled solver | Aeroelastic analysis report | Open | RSK-TEC-002 | – | Phase B exit criterion gate G6
SsR-HALE-005 | Solar panel encapsulation UV-degradation <2% / year | E | T | B | propulsion-energy-engineer | UV chamber lab | Accelerated UV test report | Planned | – | TS-PROP-6B | ASTM G154/G155 standard

## VV_Methods_Detail
V&V Methods Detail
Reference: NASA SE Handbook Rev 2 §5.3-5.4 + INCOSE SE Handbook v5
Method | Code | Definition | Esempio progetto HALE/VTOL | Tipico per | Limiti | Documentazione output | Tipico per | Limiti | Documentazione output
Inspection | I | Verifica documentale / visiva: lettura di datasheet, BoM, label, processo, contract. | SyR-C-001 Class UAS via vendor DoC, SyR-C-005 polizza assicurativa. | Compliance requirements, contract terms, statici. | Non valida prestazioni operative; sufficiente per requisiti documentali. | Inspection record + signed-off checklist.
Analysis | A | Calcoli, simulazioni, modeling. Verifica per analytical proof. | Allegato A.6 Energy Balance HALE 44N; Allegato A.7 Link Budget; FMECA; FTA. | Requisiti di prestazione misurabili pre-test; design verification. | Validita' dipende da assunzioni modello; richiede V&V del modello stesso. | Analysis report + assumption list + uncertainty quantification.
Demonstration | D | Esercizio del sistema (qualitativo): functional demonstration end-to-end. | SyR-F-001 mission EO Pentema; SyR-O-001 lost-link RTB; SsR-AVI-003 IMU fault injection. | Functional + operational requirements; ConOps validation. | Qualitativo: no measurement of margin/accuracy. | Demo log + video record + sign-off da test director.
Test | T | Misure quantitative su prototype/articolo di volo. | SsR-PROP-003 battery cycle test; SyR-P-004 wind envelope test; SsR-COMMS-001 RSSI flight. | Performance + safety requirements con margin quantification. | Costoso; richiede facility qualificata; test asset. | Test plan + procedure + data sheet + test report + uncertainty budget.

## Test_Facilities
Facility | Category | Owner | CapEx [k EUR] | OpEx/year [k EUR] | Availability | Purpose | Phase | Notes
GS test bed Firmamento (Pentema o Genova HQ) | Ground Segment | In-house | 35 | 20 | Q3 2026 | GS integration + walkthrough + maintenance training | A,B | Container 20'' attrezzato
HIL simulator Avionics | Avionics/GNC | In-house (build) o partner DiPSIM | 80 | 30 | Q4 2026 | Hardware-In-The-Loop FCS fault injection | A,B | PIL/HIL setup with ARINC 818 / MIL-STD-1553
Range test ground RF (Pentema o Albenga) | Comms | Field deployment | 20 | 10 | Q3 2026 | C2 + payload link measurement | A,C | Antenna tracking + spectrum analyzer Rohde&Schwarz
Wind tunnel subscale (IIT Genova o UniGE DICCA) | Aero | Partner academic | 0 (rental) | 50 | Q2 2027 | Subscale wind tunnel test 1:5 | B | Subscale 1:5 dimensions ~ 1.5 m; testing Re ~ 5e5
Wind tunnel POLITO (CIRA / POLITO partnership) | Aero | Partner academic | 0 (rental) | 80 | Q4 2027 | HALE subscale 1:3 test | B (Phase B 6B) | Solo Phase B 6B; budget Phase B
GVT (Ground Vibration Test) -- POLITO DIMEAS o CIRA | Structures | Partner academic | 0 | 60 | 2028 (subscale) | Modal analysis full vehicle | B (6A subscale), C (6B) | Multi-axis shaker rig + accelerometers
Solar simulator lab | Energy | Partner ENEA Casaccia o EURAC Bolzano | 0 | 20 | Q1 2027 | Panel efficiency cert AM1.5 | B | IEC 60904 / ASTM E948 flash + steady-state
Battery cycler lab | Energy | In-house o Partner CNR-ICMATE | 40 | 15 | Q2 2027 | LiS/SS-Li discharge curve + cycle life | B,C | Multi-channel cycler 0-5V, ±10A
Climatic chamber (env. test) | Environmental | External lab (Pavia / Milano) | 0 | 20 | Always | -40/+85 degC + humidity + thermal cycling | B,C | MIL-STD-810 / DO-160G qualified facility
EMC chamber accredited (Test House) | EMC | External lab (IMQ, ICIM) | 0 | 30 | Always | EN 55032 + DO-160G section 20 EMI | B | Anechoic chamber accreditata 17025
Blackbody source IR cal lab | Payload | External (INRIM Torino) | 0 | 10 | Always | NEdT cert IR sensor | A,B | Calibrazione INRIM con corpo nero standard
Drop test rig (parachute) | Safety | In-house build | 15 | 5 | Q3 2026 | Parachute deploy time test | B | 50 m drop rig + HSC video
GNSS simulator (spoofing / multipath) | GNC | External (RegoLab Genova o vendor demo) | 0 (rental) | 15 | Q2 2027 | GNSS spoofing detection test | B | Spirent / Skydel sim
Battery abuse test cell | Safety | External (CNR-ITAE Messina) | 0 | 20 | Q2 2027 | Thermal runaway containment test | B | UN 38.3 + nail penetration
Flight test sites (Pentema + GATB Grottaglie) | Flight Test | Partner DTA Puglia + Comune Torriglia | 20 setup | 30 | 2026-2027 | VLOS + BVLOS flight test | C | GATB Grottaglie certified for BVLOS test
Stratospheric test site (Sardegna o ESRANGE Kiruna) | HALE Flight Test | Partner ESRANGE / ASI | 0 (rental, plan B) | 200 | 2028+ | Stratospheric subscale + perennial flight | C (Phase B 6B HALE) | EuroHAPS-adjacent partnership

## Test_Schedule
V&V Test Schedule -- Gantt aligned to Gates G2/G3/G4/G5/G6
Activity | Start (M+) | End (M+) | Duration [m] | Phase | Gate | Owner | Output / deliverable | M+0 | M+3 | M+6 | M+9 | M+12 | M+15 | M+18 | M+21 | M+24 | M+27 | M+30 | M+33 | M+36 | M+39 | M+42 | M+45 | M+48
Inspection compliance docs (C series) | 0 | 3 | 3 | Pre-A | G1 | aviation-regulatory | Compliance matrix C-001..C-006 + RTM update | bar: M+0 to M+3
Stakeholder workshop + Stakeholder Needs collection | 0 | 3 | 3 | Pre-A | G1 | snai-funding-expert | StNeeds-001..017 + provenance log | bar: M+0 to M+3
Link budget analysis (Allegato A.7) | 3 | 6 | 3 | A | G2 | telecom-payload | A.7 Link Budget Report + Excel | bar: M+3 to M+6
Energy balance analysis HALE 44N (Allegato A.6) | 3 | 10 | 7 | A | G3 | propulsion-energy-engineer | A.6 Energy Balance Report + Sim model | bar: M+3 to M+9
FMECA preliminary (Allegato A.2) | 3 | 9 | 6 | A | G2 | systems-engineer | A.2 Risk Register + FMECA + FTA | bar: M+3 to M+9
Trade Studies TS-PLATFORM-6A, TS-MATERIAL, TS-PROP-6B | 3 | 9 | 6 | A | G2 | aerospace-SE | TS reports A.3 DOCFAP | bar: M+3 to M+9
ENAC pre-application + SORA stima | 3 | 9 | 6 | A | G3 | aviation-regulatory | SORA pre-app feedback + GRC computation | bar: M+3 to M+9
AGCOM spectrum consultation | 6 | 10 | 4 | A | G3 | telecom-payload | Spectrum allocation plan + license roadmap | bar: M+6 to M+9
DPIA preliminary + Garante engagement | 3 | 9 | 6 | A | G3 | data-privacy-counsel | DPIA preliminary doc | bar: M+3 to M+9
GS test bed setup + walkthrough | 12 | 15 | 3 | B | G4 | aerospace-SE | GS Pentema operational + checklists | bar: M+12 to M+15
HIL simulator FCS fault injection | 13 | 20 | 7 | B | G4 | avionics-gnc-engineer | HIL test report + AVI-002 IMU + AVI-003 IMU fault test | bar: M+15 to M+18
Range test ground RF + payload swap test | 14 | 18 | 4 | B | G4 | telecom-payload | RF range test + payload swap timing | bar: M+15 to M+18
Climatic chamber test (E series) | 15 | 18 | 3 | B | G4 | vtol-uas-specialist | -10/+30 degC operational env. + thermal cycle | bar: M+15 to M+18
Solar panel + battery lab test | 24 | 30 | 6 | B (6B) | G6 | propulsion-energy-engineer | Panel cert IEC 60904 + battery cycle curve | bar: M+24 to M+30
Wind tunnel subscale 1:5 + 1:3 (POLITO/CIRA) | 24 | 30 | 6 | B (6B) | G6 | aero-structures-engineer | WT report + aeroelastic correlation | bar: M+24 to M+30
Subscale prototype 1:3 ground tests | 30 | 36 | 6 | B (6B) | G6 | aero-structures-engineer | Subscale prototype TRL 5 | bar: M+30 to M+36
Flight test BVLOS Pentema + GATB Grottaglie | 9 | 12 | 3 | C (6A) | G4 | vtol-uas-specialist | Flight test log + ENAC operational auth | bar: M+9 to M+12
Operations validation Y1 (50+ missioni) | 10 | 24 | 14 | C (6A) | G5 | program-manager | Operations Y1 report + customer feedback | bar: M+12 to M+24
Subscale HALE stratospheric flight test | 36 | 48 | 12 | C (6B) | post-G6 | aero-structures-engineer | Stratospheric flight test report TRL 6 | bar: M+36 to M+48
Independent verification audit (RINA / DNV) | 9 | 11 | 2 | A | G3 | program-manager | Third-party feasibility audit report | bar: M+9
V&V documentation deliverables consolidation | 9 | 11 | 2 | A | G3 | aerospace-SE | V&V plan v1.0 + qualification matrix v1.0 | bar: M+9

## Test_Costs
Item | Category | Phase | Cost [k EUR] | Source / vendor
GS test bed setup (Pentema) | CapEx | A,B | 35 | vendor quote container + radio + UPS
HIL simulator hardware + software | CapEx | B | 80 | vendor quote NI/DiPSIM
Range test ground RF equipment | CapEx | B | 20 | vendor quote antenna tracking + analyzer
Battery cycler lab in-house | CapEx | B | 40 | vendor quote Arbin/Maccor 4-channel
Drop test rig (parachute) | CapEx | B | 15 | in-house build
Flight test sites setup (Pentema + GATB hospital fee) | CapEx | C | 20 | GATB Grottaglie fee + Pentema setup
Wind tunnel rental (UniGE DICCA or POLITO) | OpEx | B | 50 | POLITO/UniGE rental sheet
Wind tunnel HALE subscale 1:3 (CIRA) | OpEx Phase B 6B | B | 80 | CIRA rate card
GVT external (POLITO DIMEAS / CIRA) | OpEx Phase B 6B | B | 60 | POLITO partnership quote
Solar simulator (ENEA Casaccia / EURAC) | OpEx Phase B 6B | B | 20 | ENEA rate card
Climatic chamber (external lab) | OpEx | B,C | 20 | lab rate
EMC chamber accredited | OpEx | B | 30 | IMQ ICIM rate
Blackbody IR cal (INRIM Torino) | OpEx | B | 10 | INRIM accreditation fees
GNSS simulator rental | OpEx | B | 15 | Spirent/Skydel rental
Battery abuse test cell (CNR-ITAE) | OpEx | B | 20 | CNR partnership rate
Flight test operations Y1 (fuel + pilot + travel) | OpEx | C | 30 | estimate 30 missioni @1k each
Stratospheric test site (Phase B 6B) | OpEx Phase B 6B | C | 200 | ESRANGE / partner rate (estimate)
RINA / DNV feasibility audit | OpEx | A | 35 | RINA quote feasibility audit aerospace
Cybersecurity audit (NIS2) | OpEx | B | 18 | ACN-compliant cyber audit firm
DPIA + GDPR audit | OpEx | A | 12 | data privacy counsel + 3rd party
TOTAL CapEx Test (6A Phase A/B/C) |  |  | 210
TOTAL OpEx Test (6A Phase A/B/C) Y1+Y2 |  |  | 240
TOTAL Phase B 6B (HALE R&D) |  |  | 360
GRAND TOTAL (test V&V budget complete) |  |  | 810

## Independent_Verification
Scope | Body | Phase / Timing | Deliverable | Cost [k EUR] | Mandatory? | Note
Feasibility audit overall (volumi 1+2+3) | RINA (preferred) o DNV / SGS | A (M+9-11) | Independent feasibility statement | 35 | Recommended (not mandatory by bando) | Gate G3 'investment-grade' upgrade. Increase confidence dei finanziatori.
ConOps SORA + GRC validation | ENAC (pre-application) | A (M+3-9) | ENAC feedback letter + SAIL stima | 0 | Necessary for SORA submission | Pre-application meeting non vincolante; full application formal.
Cybersecurity NIS2 audit | ACN-accredited audit firm | B (M+12-18) | NIS2 compliance audit report | 18 | Necessary for operations (NIS2 enters force) | Verifica Article 21 NIS2 misure tecniche.
DPIA + GDPR audit | 3rd-party data privacy counsel (external) | A (M+3-9) | DPIA report + Garante engagement | 12 | Required for personal data processing | Pubblicazione DPIA + workshop comunita' Pentema.
Wind tunnel test report validation (subscale) | POLITO DIMEAS / UniGE DICCA | B (M+24-30) | Wind tunnel certified report | 0 | Required for Phase B 6B aerodynamic baseline | Phase B 6B; budget Phase B.
GVT (Ground Vibration Test) certification | POLITO / CIRA | B (M+30-36) | GVT modal analysis report | 0 | Required for flight test clearance | Phase B 6B; flutter margin verification.
Solar panel efficiency cert (IEC 60904) | ENEA Casaccia / EURAC Bolzano (TUV cert) | B (M+24) | IEC 60904 cert + flash test data | 0 | Required for energy budget compliance | Phase B 6B.
Battery thermal runaway (UN 38.3) | CNR-ITAE / accredited lab | B (M+24-30) | UN 38.3 test cert | 20 | Required for transport + flight clearance | Phase B 6B + 6A if Li-S pack.
EMC compliance (EN 55032 + DO-160G) | IMQ / ICIM / TUV | B (M+15-18) | EMC test report | 30 | Required for ENAC operational authorization | Phase B 6A operational pre-requisite.
TOTAL Independent Verification budget |  |  |  | 115