## Cover
Allegato A.2 - Risk Register v1.0 - Firmamento Technologies HALE/VTOL
Documento | Allegato A.2 - Risk Register completo v1.0
Volume | Volume 2 - Allegati tecnici dello Studio di Fattibilita
Studio di riferimento | Studio di Fattibilita Piattaforma Aerea HALE/VTOL per Aree Interne
Bando | Cooding Prototypes - Coopfond/Legacoop
Soggetto proponente | Firmamento Technologies srl coop
Versione | v1.0
Data | 2026-05-17
Stato | Bozza M+3 consolidata
Metodologia
Framework primario | NASA NPR 8000.4A - Continuous Risk Management (CRM)
Failure analysis | FMECA - MIL-STD-1629A / IEC 60812
Safety assessment | ARP4761 - Aerospace Recommended Practice
Fault Tree Analysis | ARP4761 + NUREG-0492 + IEC 61025
ISO standard | ISO 31000:2018 - Risk Management Principles and Guidelines
Conformita italiana | D.Lgs. 36/2023 art. 41 (analisi di rischio ingegneristico)
Conformita aviation | EASA SORA 2.5 (ED Decision 2025/018/R) + Part-IS (Reg.UE 2023/203)
Conformita cyber | NIS2 (D.Lgs. 138/2024) + ISO/IEC 27001 + Part-IS
Sistema di scoring
Probabilita P (1-5) | 1=VeryLow (<5%) ¦ 2=Low (5-20%) ¦ 3=Medium (20-50%) ¦ 4=High (50-80%) ¦ 5=VeryHigh (>80%)
Impatto I (1-5) | 1=Negligible ¦ 2=Minor ¦ 3=Moderate ¦ 4=Major ¦ 5=Severe (showstopper/catastrofe)
Risk Score | P x I (range 1-25)
Color coding | GREEN 1-7 (accettabile, monitor) ¦ YELLOW 8-14 (mitigation richiesta) ¦ RED 15-25 (showstopper, response immediata)
Response options | Avoid ¦ Mitigate ¦ Transfer ¦ Accept (NASA + ISO 31000)
Residual risk | P x I post-mitigation; richiesto <= GREEN o YELLOW per closure
Struttura del Risk Register
Totale rischi tracciati | 116
Categorie | TEC (tecnici) ¦ REG (regolatori) ¦ FIN (finanziari) ¦ MKT (mercato) ¦ OPS (operativi) ¦ SUP (supply chain) ¦ PRV (privacy/legale) ¦ SEC (cybersecurity) ¦ HR (risorse umane) ¦ REP (reputazionali) ¦ GEO (geopolitici - RESERVED)
Fogli del workbook | 22 sheet (Cover, Top-25, 11 categorie, 3 FMECA, 2 FTA, Mitigation Plan, Residual Matrix, EWI, Audit Trail)
Boundary conditions | B1: service-only + cooperative Legacoop ¦ B2: EU sovereign stratospheric layer / complementare IRIS2
Documenti correlati (cross-reference)
Cap. 6.4 | Top-10 rischi tecnici + FMECA Payload + FTA preliminare
Cap. 5.16 | 15 showstopper regolatori RSK-REG-016..030
Cap. 10.2 | Risk residuo aggregato + 5 showstopper formali
RESERVED-rischi-geopolitici.md | 5 RSK-GEO-001..005 (accesso ristretto - NO contenuto sensibile in questo file pubblico)
Skill .claude/skills/risk-register-builder/SKILL.md | Metodologia operativa
AUDIT-REDTEAM-VOLUME-1.md | Audit Red Team M+3 + falsifying observations
AUDIT-REGULATORY-VOLUME-1.md | Audit Regulatory Adversary M+3 (15 showstopper REG)
AUDIT-COMPETITOR-VOLUME-1.md | Audit Competitor Intelligence M+3
Disciplina epistemica
Confidence levels | high / medium-high / medium / medium-low / low per ogni claim P e I
Falsifying observations | Documentate per top-10 rischi - condizioni che falsificherebbero stima rischio
Source provenance | Tutti i rischi tracciati a Cap. 5/6/10 dello Studio o audit M+3 dedicati
Re-assessment | Trimestrale + dopo ogni gate review + trigger eventi esterni
Owner principale
Risk Manager | TBD (CISO + Head of Regulatory Affairs joint fino assunzione)
Approval gate review | Steering Committee Firmamento + Coopfond observer + Legacoop
Esterno (gate G4 M+12) | Auditor esterno terzo + advisory aerospace senior

## Top-25 Risks
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-TEC-001 | Tecnico | Energy balance HALE inverno 44N - deficit -50% confermato da simulazione (vs +0-15% stima a mano) | Simulazione 365gg M+3 mostra -50.1% margin solstizio dic; perennial flight NON fattibile baseline 2026-28 | 5 | 5 | 25 | RED | Showstopper | propulsion-energy-engineer | Mitigate | Plan A obbligato E5 'Seasonal-only mar-ott' (~7 mesi). Plan B Y6+: migrazione SS Li 450 Wh/kg o PEM+LH2. Plan C: ridimensionamento R&D-only fino tech 2030+ | 5 | 4 | 20 | Y3-Y5 (Phase B 6B) | high | 2026-05-17 | Sim. allegato A.7 + monthly clear-sky variability + LiS pack TRL update trimestrale
RSK-REG-001 | Regolatorio | Mancanza framework HAPS EASA/ENAC - no Special Condition aperto HALE solare civile | EASA non apre RMT HAPS nel calendario 2026-2028; ENAC non rilascia AMC HAPS | 5 | 4 | 20 | RED | Showstopper | aviation-regulatory + sovereign-strategist | Mitigate | Engagement EASA Innovation Network + consortium CIRA/TAS per Special Condition collettiva; partecipazione ASD-Eurospace HAPS WG; lobby DG MOVE/DG DEFIS | 4 | 4 | 16 | Y3-Y6 (Phase B/C) | high | 2026-05-17 | EASA RMT calendar (semestrale) + Special Condition published + ASD-Eurospace minutes
RSK-FIN-001 | Finanziario | Mancanza commitment funding Phase B 6B - 5.5-13.5M EUR mix EDF+Horizon+PNRR+equity | Gate G5 M+24 mostra funding mix Phase B < 30% | 4 | 5 | 20 | RED | Showstopper | financial-cfo + sovereign-strategist | Mitigate | Mix funding: EDF (DG DEFIS) + Horizon Europe + PNRR Aerospazio + Series B equity (CDP, EIB); fasi graduali; partnership prime per cost sharing | 3 | 4 | 12 | Y2-Y3 (gate G5) | medium-high | 2026-05-17 | Calendar bandi EDF/Horizon + Series B pipeline + LoI investitori
RSK-TEC-003 | Tecnico/Regolatorio | Type Certification HALE timeline > 5 anni - no precedente HALE solare civile EU con TC emesso | EASA non apre RMT HAPS o Special Condition path entro 2028 | 4 | 4 | 16 | RED | Showstopper | aviation-regulatory + sovereign-strategist | Mitigate+Accept | Parallel approach: ops 6A genera revenue + esperienza mentre TC HALE matura. Engagement EASA Innovation Network + consortium CIRA/TAS per Special Condition collettiva | 4 | 3 | 12 | Y4-Y8 | medium-high | 2026-05-17 | EASA RMT HAPS calendar + advisory bodies pubblicazioni + AALTO/Skydweller TC progress
RSK-HR-002 | Risorse Umane | Reclutamento CISO + DPO + Head Regulatory - 3 ruoli senior in mercato compresso | Tempo hire > 9 mesi (vs target 3-6 mesi) | 4 | 4 | 16 | RED | Open-Critical | HR + CEO | Mitigate | Headhunter specializzati; contratti competitivi (180-220k EUR/anno per CISO senior); part-time fractional CISO/DPO M+0-6; partnership consulting Legal/Cyber | 3 | 3 | 9 | Y0-Y1 | medium | 2026-05-17 | Hire pipeline weekly + headhunter pipeline status
RSK-REG-008 | Regolatorio | EASA Part-21 design organisation approval (DOA) - richiesto per HALE Phase C | Transition Phase B->C richiede DOA accreditata o partner con DOA | 4 | 4 | 16 | RED | Open-High | aviation-regulatory + systems-engineer | Mitigate | Partnership con DOA esistente (Leonardo, Tekever, AALTO) per Phase C; preparazione DOA Firmamento Y5+ | 3 | 3 | 9 | Y5+ | medium | 2026-05-17 | DOA holders pubblicati EASA + partnership negotiation status
RSK-REG-018 | Regolatorio | EUROCONTROL Network Manager - coordinamento ATM-ANS HAPS FL400+ EU airspace | EUROCONTROL non rilascia procedure operative HAPS perennial entro Y4-Y5 | 4 | 4 | 16 | RED | Open-Critical | avionics-gnc-engineer + aviation-regulatory | Mitigate | Engagement EUROCONTROL precocemente (Y2-Y3); partecipazione workshop UAM/HAPS Network Manager; contributo definizione procedure | 3 | 3 | 9 | Y3+ | medium | 2026-05-17 | EUROCONTROL Network Manager workplan + HAPS procedure pubblicate
RSK-REG-019 | Regolatorio | Part-IS EASA Reg.UE 2023/203 - ISMS obbligatorio da feb 2026, CISO assente | Audit ENAC Part-IS rileva non-conformita sostanziali ISMS | 4 | 4 | 16 | RED | Open-Critical | aviation-regulatory + CISO (new) | Mitigate | Assunzione CISO entro M+6; ISMS implementazione entro M+9; certificazione ISO/IEC 27001 entro M+12; audit interno + pre-audit ENAC | 3 | 3 | 9 | Y1 (M+0 → M+12) urgente | high | 2026-05-17 | CISO hire date + ISMS gap analysis + ISO 27001 cert progress
RSK-REG-025 | Regolatorio | Affidamento PA art.50 D.Lgs.36/2023 - contratto Regione > 140k EUR richiede gara | Regione Liguria contratto pluriennale > 300k EUR bocciato fase amministrativa | 4 | 4 | 16 | RED | Open-Critical | snai-funding + legal + business-model | Mitigate | Pre-engagement Regione + accordo quadro (art.59 D.Lgs.36); partnership Coopfond come veicolo non-gara; accordi di programma SNAI; gara con specificita tecniche Firmamento-friendly | 3 | 3 | 9 | Y0+ | high | 2026-05-17 | Bando Regione pubblicato + legal review procedura
RSK-REG-030 | Regolatorio | ENAV procedure FL400+ - HAPS perennial sopra FL400/FL650 senza procedure dedicate | ENAV declina procedure HAPS perennial entro Y4 | 4 | 4 | 16 | RED | Open-Critical | avionics + sovereign-strategist + aviation-regulatory | Mitigate | Engagement ENAV precoce (Y2); contributo definizione procedure standard EUROCONTROL; testing spazio aereo segregato (Sardinia, GATB Apulia) | 3 | 3 | 9 | Y3+ | medium-high | 2026-05-17 | ENAV operational instruction + AIP Italy SUP HAPS
RSK-SUP-003 | Supply Chain | Batterie LiS - capacity allocation Northvolt/Italvolt incerta | Northvolt bankruptcy o Italvolt ritardo > 2 anni production | 4 | 4 | 16 | RED | Open-High | propulsion-energy-engineer + supply-chain | Mitigate | Multi-vendor LiS pipeline (Oxis Energy heir, Lyten, NexTech); custom pack assembly con cell suppliers diversi | 3 | 3 | 9 | Y3+ | medium | 2026-05-17 | Battery vendors financials + production timelines
RSK-TEC-016 | Tecnico | NTN payload winter unsustainable - margin -58.9% con P_payload 500 W (scenario E5) | Simulazione M+3 (DR-014) conferma deficit anche con payload pulse-mode | 4 | 4 | 16 | RED | Open-Critical | propulsion-energy-engineer + telecom-ntn-payload-expert | Mitigate | NTN seasonal-only + payload pulse-mode duty-cycle < 30% + dedicated battery bank NTN | 3 | 3 | 9 | Y4-Y5 | medium-high | 2026-05-17 | Sim. allegato A.7 update; product roadmap 5G NTN bypass requirements
RSK-REG-021 | Regolatorio | AgID/PSN hosting dati PA - cloud non qualificato blocca contratti Regione/PC | Verifica AgID al M+9 rivela cloud Aruba/OVH non PSN-qualified per livello criticita | 4 | 4 | 16 | RED | Open-Critical | data-privacy + IT + DPO | Mitigate | Migrazione provider PSN-qualified (TIM Enterprise, Polo PSN, CDP Cloud) o cloud qualificato AgID (Aruba qualified, Engineering, Reply, Almaviva); audit AgID compliance | 2 | 3 | 6 | Y1+ | high | 2026-05-17 | AgID qualifica list update + audit compliance internal
RSK-REG-027 | Regolatorio | NIS2 D.Lgs.138/2024 - registrazione ACN omessa, sanzioni fino 10M EUR / 2% fatturato | Firmamento classificata 'soggetto essenziale' senza registrazione entro 30gg | 4 | 4 | 16 | RED | Open-Critical | CISO (new) + legal | Mitigate | Registrazione preventiva ACN entro M+1; ISMS Part-IS allineato; notifica incidenti 24h procedure | 2 | 3 | 6 | Y0+ immediato | high | 2026-05-17 | ACN classification notice + sanction publications
RSK-TEC-015 | Tecnico | Riduzione TRL gap M+24 - integrato HALE subsystem critici < TRL 5 | Gate G5 review M+24 mostra TRL integrato propulsione/avionica/payload < 5 | 3 | 5 | 15 | RED | Open-Critical | systems-engineer + propulsion-energy-engineer | Mitigate | Roadmap TRL puntuale per sottosistema + milestone trimestrali + partnership prime per acceleration TRL (DR-013 finding) | 3 | 4 | 12 | Y3 (gate G5) | medium | 2026-05-17 | TRL milestone tracker + subsystem demo report + partnership signed
RSK-FIN-004 | Finanziario | OpEx Y1 underestimato - +450-800k EUR per 3 FTE regulatory (CISO+DPO+Head Reg.Aff) | Audit regulatory M+3 rivela 3 FTE addizionali non-budget | 5 | 3 | 15 | RED | Open-Critical | financial-cfo | Mitigate | Aggiornamento Cap.8 OpEx Y1 con +450-800k EUR fixed cost; revisione mix funding equity Series A; cost sharing su CISO/DPO via partnership cooperative | 4 | 2 | 8 | Y0-Y1 | high | 2026-05-17 | FTE hire pipeline + payroll forecast
RSK-TEC-002 | Tecnico | Aeroelasticita ala high-AR (AR>=25) - flutter, divergenza, instabilita non lineare | Analisi aeroelastica preliminare M+12 mostra flutter speed < 1.3x Vdive o divergenza < 1.5x Vc | 3 | 5 | 15 | RED | Showstopper | aero-structures-engineer | Mitigate | Aeroelastic analysis non-lineare (NASTRAN+ZAERO o MSC.Nastran SOL145) + GVT (Ground Vibration Test) + flight test subscale + winglet/passive damping design. Tilted spar caps + balance mass. | 2 | 4 | 8 | Y3-Y4 (Phase B 6B) | medium-high | 2026-05-17 | Output FEA aeroelastico subscale + risultati GVT + base rate Helios/PHASA flutter events
RSK-MKT-001 | Mercato | Adozione lenta PA - cicli appalti pubblici 12-24 mesi vs piano 6-9 mesi | Contratti pluriennali Regione Liguria non firmati entro M+12 | 4 | 3 | 12 | YELLOW | Open-High | snai-funding + business-model | Mitigate | Anchor customer Regione + LoI pre-formale; contratti pluriennali quadro; partnership cooperative come veicolo di servizi | 3 | 3 | 9 | Y1-Y2 | high | 2026-05-17 | Bandi Regione publication + LoI tracking
RSK-MKT-002 | Mercato | Competitor Tier 1 AALTO-Leonardo JV - cattura 2-3 Regioni SNAI con pricing aggressivo | AALTO-Leonardo annuncia JV o pilota multi-regionale entro Y2 | 3 | 4 | 12 | YELLOW | Open-High | competitive-intelligence + business-model | Mitigate | Differenziazione cooperativa + sovranita IT; speed to market 6A; partnership CIRA/POLITO; lock-in cooperative Legacoop | 3 | 3 | 9 | Y2-Y3 | medium | 2026-05-17 | AALTO press releases + Leonardo strategy update
RSK-MKT-004 | Mercato | Pricing pressure - PA italiana clienti price-sensitive vs servizi premium | Tender Regione cost ceiling < 50k EUR/anno per servizio EO/SAR | 4 | 3 | 12 | YELLOW | Open-High | business-model + financial-cfo | Mitigate | Bundle servizi multipli (EO+IR+NTN+monitoring) per economia scale; cost-shared infrastruttura cooperative; modello canone vs ore-volo | 3 | 3 | 9 | Y1-Y3 | medium-high | 2026-05-17 | Tender history pricing + benchmark drone services market IT
RSK-MKT-005 | Mercato | Single-customer concentration Liguria - alternanza politica regionale evapora anchor | Elezioni Regione Liguria 2025+ portano cambio amministrazione + scope revision | 3 | 4 | 12 | YELLOW | Open-High | business-model + sovereign-strategist | Mitigate | Espansione 2-3 regioni SNAI Y3 (Piemonte, Marche, Calabria, Basilicata); LoI pre-formalizzata multi-region; contratti pluriennali con clausole continuita amministrative | 2 | 4 | 8 | Y2-Y3 | medium | 2026-05-17 | Elezioni regionali calendar + cambio assessori Liguria
RSK-TEC-012 | Tecnico | FCS DAL-C HALE custom - mancanza track record civile + costo qualification ~2-5M EUR | Vendor FCS DAL-C EU rifiuta development partnership o costo > budget | 3 | 4 | 12 | YELLOW | Open-High | avionics-gnc-engineer | Mitigate | Engagement early vendor EU (UAVOS, MicroPilot, Honeywell EU); partnership con CIRA su FCS Italian sovereign; budget riservato 2-3M EUR R&D | 2 | 4 | 8 | Y3-Y4 | medium | 2026-05-17 | Quotation vendor FCS + RMT EASA on autonomy
RSK-FIN-005 | Finanziario | Slittamento grant FESR/PNRR - tempi PA italiani median 18-30 mesi | Grant FESR Liguria comunicato slittato > 12 mesi vs piano | 4 | 3 | 12 | YELLOW | Open-High | financial-cfo + snai-funding | Mitigate | Bridge financing (banca + founder); pipeline grant multiple parallele; flessibilita timeline progetto | 3 | 2 | 6 | Y1-Y3 | high | 2026-05-17 | Grant decisional timeline tracking + Regione comunicazioni
RSK-FIN-006 | Finanziario | WACC effettivo > 18% se grant mix < 30% - NPV diventa negativo (sensitivity Cap.8) | Grant mix committed < 30% al M+12 | 3 | 4 | 12 | YELLOW | Open-High | financial-cfo | Mitigate | Pricing premium servizi + cost optimization OpEx; renegotiate equity terms; cost-shared infrastructure con cooperative | 2 | 3 | 6 | Y1-Y3 | medium-high | 2026-05-17 | Grant commitment % monthly + NPV sensitivity update
RSK-FIN-008 | Finanziario | Cash flow gap Y2-Y3 - revenue ramp lento vs OpEx fixed | Revenue Y2 < 500k EUR (50% target) | 3 | 4 | 12 | YELLOW | Open-High | financial-cfo + business-model | Mitigate | Bridge financing Series A; cost flex su FTE variable; contratti pluriennali Regione anticipated payment | 2 | 3 | 6 | Y2-Y3 | medium | 2026-05-17 | Revenue actuals monthly + cash burn rate

## RSK-TEC
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-TEC-001 | Tecnico | Energy balance HALE inverno 44N - deficit -50% confermato da simulazione (vs +0-15% stima a mano) | Simulazione 365gg M+3 mostra -50.1% margin solstizio dic; perennial flight NON fattibile baseline 2026-28 | 5 | 5 | 25 | RED | Showstopper | propulsion-energy-engineer | Mitigate | Plan A obbligato E5 'Seasonal-only mar-ott' (~7 mesi). Plan B Y6+: migrazione SS Li 450 Wh/kg o PEM+LH2. Plan C: ridimensionamento R&D-only fino tech 2030+ | 5 | 4 | 20 | Y3-Y5 (Phase B 6B) | high | 2026-05-17 | Sim. allegato A.7 + monthly clear-sky variability + LiS pack TRL update trimestrale
RSK-TEC-003 | Tecnico/Regolatorio | Type Certification HALE timeline > 5 anni - no precedente HALE solare civile EU con TC emesso | EASA non apre RMT HAPS o Special Condition path entro 2028 | 4 | 4 | 16 | RED | Showstopper | aviation-regulatory + sovereign-strategist | Mitigate+Accept | Parallel approach: ops 6A genera revenue + esperienza mentre TC HALE matura. Engagement EASA Innovation Network + consortium CIRA/TAS per Special Condition collettiva | 4 | 3 | 12 | Y4-Y8 | medium-high | 2026-05-17 | EASA RMT HAPS calendar + advisory bodies pubblicazioni + AALTO/Skydweller TC progress
RSK-TEC-016 | Tecnico | NTN payload winter unsustainable - margin -58.9% con P_payload 500 W (scenario E5) | Simulazione M+3 (DR-014) conferma deficit anche con payload pulse-mode | 4 | 4 | 16 | RED | Open-Critical | propulsion-energy-engineer + telecom-ntn-payload-expert | Mitigate | NTN seasonal-only + payload pulse-mode duty-cycle < 30% + dedicated battery bank NTN | 3 | 3 | 9 | Y4-Y5 | medium-high | 2026-05-17 | Sim. allegato A.7 update; product roadmap 5G NTN bypass requirements
RSK-TEC-002 | Tecnico | Aeroelasticita ala high-AR (AR>=25) - flutter, divergenza, instabilita non lineare | Analisi aeroelastica preliminare M+12 mostra flutter speed < 1.3x Vdive o divergenza < 1.5x Vc | 3 | 5 | 15 | RED | Showstopper | aero-structures-engineer | Mitigate | Aeroelastic analysis non-lineare (NASTRAN+ZAERO o MSC.Nastran SOL145) + GVT (Ground Vibration Test) + flight test subscale + winglet/passive damping design. Tilted spar caps + balance mass. | 2 | 4 | 8 | Y3-Y4 (Phase B 6B) | medium-high | 2026-05-17 | Output FEA aeroelastico subscale + risultati GVT + base rate Helios/PHASA flutter events
RSK-TEC-015 | Tecnico | Riduzione TRL gap M+24 - integrato HALE subsystem critici < TRL 5 | Gate G5 review M+24 mostra TRL integrato propulsione/avionica/payload < 5 | 3 | 5 | 15 | RED | Open-Critical | systems-engineer + propulsion-energy-engineer | Mitigate | Roadmap TRL puntuale per sottosistema + milestone trimestrali + partnership prime per acceleration TRL (DR-013 finding) | 3 | 4 | 12 | Y3 (gate G5) | medium | 2026-05-17 | TRL milestone tracker + subsystem demo report + partnership signed
RSK-TEC-012 | Tecnico | FCS DAL-C HALE custom - mancanza track record civile + costo qualification ~2-5M EUR | Vendor FCS DAL-C EU rifiuta development partnership o costo > budget | 3 | 4 | 12 | YELLOW | Open-High | avionics-gnc-engineer | Mitigate | Engagement early vendor EU (UAVOS, MicroPilot, Honeywell EU); partnership con CIRA su FCS Italian sovereign; budget riservato 2-3M EUR R&D | 2 | 4 | 8 | Y3-Y4 | medium | 2026-05-17 | Quotation vendor FCS + RMT EASA on autonomy
RSK-TEC-018 | Tecnico | Calibrazione IR sensor persa - false positive antincendio o missed hotspot | Validation post-deploy mostra false alarm rate > 5% o missed detection > 2% | 3 | 4 | 12 | YELLOW | Open-High | earth-observation-expert | Mitigate | NUC (Non-Uniformity Correction) frequente + cross-check RGB + validation periodica vs ground truth (VVF, satellite) | 2 | 3 | 6 | Y1+ | medium-high | 2026-05-17 | FAR/MDR weekly metrics + IR cal report mensile
RSK-TEC-008 | Tecnico | Batterie thermal runaway - LiPo 6A o LiS 6B - propagation cell-to-cell | Incidente settore (Boeing 787, Tesla, drone delivery) o test interno cella defect | 2 | 5 | 10 | YELLOW | Open-High | propulsion-energy-engineer + safety | Mitigate+Transfer | Cell-level fuse + intumescent barriers + BMS multi-sensor + hangar dedicato ATEX + assicurazione casco con clausola batteria | 1 | 4 | 4 | Y1+ continuous | high | 2026-05-17 | Reports thermal events FAA/EASA + cell vendor recall
RSK-TEC-004 | Tecnico | Integrazione payload modulare 6A - incompatibilita elettrica/SW vs ICD payload bay JOUAV CW-30E | Test bench pre-deploy M+7 rivela mismatch power budget o data bus payload-FCS | 3 | 3 | 9 | YELLOW | Open-High | systems-engineer | Mitigate | ICD rigoroso e validato pre-quotation; test bed integrazione hardware-in-the-loop entro M+6; vendor compatibility matrix | 2 | 3 | 6 | Y1 (M+6 → M+9) | medium | 2026-05-17 | Esiti test bench HIL trimestrale + vendor response time tickets ICD
RSK-TEC-010 | Tecnico | GNSS spoofing/jamming Liguria - prossimita conflict zones Mar Mediterraneo | Incidenti GPS reportati Mar Ligure o esercitazioni NATO area | 3 | 3 | 9 | YELLOW | Open-High | avionics-gnc-engineer | Mitigate | Multi-constellation (GPS+Galileo+GLONASS+BeiDou) + RAIM + IMU dead-reckoning + opzione Galileo PRS Phase B | 2 | 3 | 6 | Y1+ | medium | 2026-05-17 | Report EASA GPS interference + UK CAA bulletin spoofing
RSK-TEC-014 | Tecnico | Single Event Upset (SEU) avionica stratosferica - aumentato flusso particelle 20 km | FCS reboot rate > 1/100h in flight test stratosferico | 3 | 3 | 9 | YELLOW | Open-Medium | avionics-gnc-engineer | Mitigate | FPGA rad-tolerant (Microchip RTPolarFire o Xilinx Versal AI Edge) + 2oo3 voting + watchdog timer + memory ECC | 2 | 2 | 4 | Y3-Y5 | medium | 2026-05-17 | Flight test stratosferico subscale + heritage SEU dataset Zephyr
RSK-TEC-005 | Tecnico | Cybersecurity link C2 - jamming, spoofing GNSS, command injection | Eventi jamming GNSS regione (Mar Ligure ports) o report incidenti UAS via | 2 | 4 | 8 | YELLOW | Open-High | avionics-gnc-engineer + CISO (new) | Mitigate | Frequency hopping (FHSS) + crypto authentication AES-256 + multi-GNSS L1/L5 + dead-reckoning IMU fallback + Lost-Link procedure DAL-C | 1 | 4 | 4 | Y1+ continuous | medium-high | 2026-05-17 | Report GPS interference EASA bulletin + NOTAM jamming Mediterraneo
RSK-TEC-006 | Tecnico/Privacy | Privacy by design fail (DPIA bocciata Garante per sorveglianza territoriale) | Garante Privacy emette provvedimento negativo o richiesta integrazione DPIA | 2 | 4 | 8 | YELLOW | Open-High | data-privacy-counsel + DPO (new) | Mitigate | Edge anonymization (blur on-board obbligatorio); geofence aree residenziali; DPIA preliminare entro M+6; consultazione preventiva Garante | 1 | 3 | 3 | Y1 (M+0 → M+9) | medium-high | 2026-05-17 | Comunicati Garante AI Act/UAS + precedenti DPIA aerei
RSK-TEC-007 | Tecnico/Regolatorio | Lost-Link behaviour mismatch SORA OSO #9 - mancata RtB automatica | ENAC in pre-application richiede dimostrazione Lost-Link Profile + RtB testato | 2 | 4 | 8 | YELLOW | Open-High | avionics-gnc-engineer | Mitigate | Lost-Link Profile documentato + Return-to-Base testato in flight test pre-deploy + procedura GS notifica + safety case ARP4761 | 1 | 3 | 3 | Y1 (M+6) | medium-high | 2026-05-17 | Test report RtB + ENAC pre-app feedback
RSK-TEC-017 | Tecnico | Ground Station single point of failure - GS fissa Pentema unica fonte C2 | Power outage o danno infrastruttura GS Pentema durante volo BVLOS | 2 | 4 | 8 | YELLOW | Open-High | vtol-uas-specialist + ops | Mitigate | GS mobile ridondante + UPS GS fissa + SATCOM fallback + procedura RtB Lost-Link | 1 | 3 | 3 | Y1+ | high | 2026-05-17 | Live GS uptime + UPS test mensile
RSK-TEC-009 | Tecnico | Materiali compositi - delaminazione/fatica lino in strutture secondarie (cicli umidita) | Test panel POLIMI/POLITO mostra degradazione > soglia dopo 1000h ciclica umido | 3 | 2 | 6 | GREEN | Open-Medium | aero-structures-engineer | Mitigate | Lino solo in strutture secondarie con coating idrorepellente; longherone primario CFRP; LCA + qualification path posticipato | 2 | 2 | 4 | Y3-Y4 | medium | 2026-05-17 | Pubblicazioni Pinato/Biogear test cicli umidi + qualification panel internal
RSK-TEC-011 | Tecnico | Solar cell degradation in stratosfera - UV + thermal cycling ridotta efficienza GaAs | Test cell exposure stratosferico (Sahara HALE program) mostra > 5%/year degradation | 2 | 3 | 6 | GREEN | Monitor | propulsion-energy-engineer | Mitigate | Margine design 30% su energy budget; cell qualification per ambiente stratosferico; vendor Spectrolab/Azur Space datasheet flight heritage | 2 | 2 | 4 | Y4+ | medium | 2026-05-17 | Vendor flight heritage data + EuroHAPS testbed reports
RSK-TEC-013 | Tecnico | Link budget HAPS service link rain fade - storm scenario 1% time supera margin | Simulazione ITU-R P.618-14 stormy day worst-case mostra margin < 6 dB | 2 | 3 | 6 | GREEN | Monitor | telecom-ntn-payload-expert | Mitigate | Adaptive coding modulation (ACM) + site diversity gateway Ka-band + buffer queue + scheduled re-transmission | 1 | 2 | 2 | Y4+ | high | 2026-05-17 | Live link metrics post test integrato

## RSK-REG
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-REG-001 | Regolatorio | Mancanza framework HAPS EASA/ENAC - no Special Condition aperto HALE solare civile | EASA non apre RMT HAPS nel calendario 2026-2028; ENAC non rilascia AMC HAPS | 5 | 4 | 20 | RED | Showstopper | aviation-regulatory + sovereign-strategist | Mitigate | Engagement EASA Innovation Network + consortium CIRA/TAS per Special Condition collettiva; partecipazione ASD-Eurospace HAPS WG; lobby DG MOVE/DG DEFIS | 4 | 4 | 16 | Y3-Y6 (Phase B/C) | high | 2026-05-17 | EASA RMT calendar (semestrale) + Special Condition published + ASD-Eurospace minutes
RSK-REG-008 | Regolatorio | EASA Part-21 design organisation approval (DOA) - richiesto per HALE Phase C | Transition Phase B->C richiede DOA accreditata o partner con DOA | 4 | 4 | 16 | RED | Open-High | aviation-regulatory + systems-engineer | Mitigate | Partnership con DOA esistente (Leonardo, Tekever, AALTO) per Phase C; preparazione DOA Firmamento Y5+ | 3 | 3 | 9 | Y5+ | medium | 2026-05-17 | DOA holders pubblicati EASA + partnership negotiation status
RSK-REG-018 | Regolatorio | EUROCONTROL Network Manager - coordinamento ATM-ANS HAPS FL400+ EU airspace | EUROCONTROL non rilascia procedure operative HAPS perennial entro Y4-Y5 | 4 | 4 | 16 | RED | Open-Critical | avionics-gnc-engineer + aviation-regulatory | Mitigate | Engagement EUROCONTROL precocemente (Y2-Y3); partecipazione workshop UAM/HAPS Network Manager; contributo definizione procedure | 3 | 3 | 9 | Y3+ | medium | 2026-05-17 | EUROCONTROL Network Manager workplan + HAPS procedure pubblicate
RSK-REG-019 | Regolatorio | Part-IS EASA Reg.UE 2023/203 - ISMS obbligatorio da feb 2026, CISO assente | Audit ENAC Part-IS rileva non-conformita sostanziali ISMS | 4 | 4 | 16 | RED | Open-Critical | aviation-regulatory + CISO (new) | Mitigate | Assunzione CISO entro M+6; ISMS implementazione entro M+9; certificazione ISO/IEC 27001 entro M+12; audit interno + pre-audit ENAC | 3 | 3 | 9 | Y1 (M+0 → M+12) urgente | high | 2026-05-17 | CISO hire date + ISMS gap analysis + ISO 27001 cert progress
RSK-REG-021 | Regolatorio | AgID/PSN hosting dati PA - cloud non qualificato blocca contratti Regione/PC | Verifica AgID al M+9 rivela cloud Aruba/OVH non PSN-qualified per livello criticita | 4 | 4 | 16 | RED | Open-Critical | data-privacy + IT + DPO | Mitigate | Migrazione provider PSN-qualified (TIM Enterprise, Polo PSN, CDP Cloud) o cloud qualificato AgID (Aruba qualified, Engineering, Reply, Almaviva); audit AgID compliance | 2 | 3 | 6 | Y1+ | high | 2026-05-17 | AgID qualifica list update + audit compliance internal
RSK-REG-025 | Regolatorio | Affidamento PA art.50 D.Lgs.36/2023 - contratto Regione > 140k EUR richiede gara | Regione Liguria contratto pluriennale > 300k EUR bocciato fase amministrativa | 4 | 4 | 16 | RED | Open-Critical | snai-funding + legal + business-model | Mitigate | Pre-engagement Regione + accordo quadro (art.59 D.Lgs.36); partnership Coopfond come veicolo non-gara; accordi di programma SNAI; gara con specificita tecniche Firmamento-friendly | 3 | 3 | 9 | Y0+ | high | 2026-05-17 | Bando Regione pubblicato + legal review procedura
RSK-REG-027 | Regolatorio | NIS2 D.Lgs.138/2024 - registrazione ACN omessa, sanzioni fino 10M EUR / 2% fatturato | Firmamento classificata 'soggetto essenziale' senza registrazione entro 30gg | 4 | 4 | 16 | RED | Open-Critical | CISO (new) + legal | Mitigate | Registrazione preventiva ACN entro M+1; ISMS Part-IS allineato; notifica incidenti 24h procedure | 2 | 3 | 6 | Y0+ immediato | high | 2026-05-17 | ACN classification notice + sanction publications
RSK-REG-030 | Regolatorio | ENAV procedure FL400+ - HAPS perennial sopra FL400/FL650 senza procedure dedicate | ENAV declina procedure HAPS perennial entro Y4 | 4 | 4 | 16 | RED | Open-Critical | avionics + sovereign-strategist + aviation-regulatory | Mitigate | Engagement ENAV precoce (Y2); contributo definizione procedure standard EUROCONTROL; testing spazio aereo segregato (Sardinia, GATB Apulia) | 3 | 3 | 9 | Y3+ | medium-high | 2026-05-17 | ENAV operational instruction + AIP Italy SUP HAPS
RSK-REG-015 | Regolatorio | Cross-border BVLOS - assenza EU regulation harmonizzata per cross-border ops HAPS | Operazioni cross-border (Liguria-Francia, Liguria-Svizzera) bloccate da MS divergenti | 4 | 3 | 12 | YELLOW | Monitor | aviation-regulatory + sovereign-strategist | Accept+Mitigate | Focus Y1-Y3 su operazioni domestiche IT; engagement EASA cross-border WG Y3+ | 3 | 2 | 6 | Y3+ | medium | 2026-05-17 | EASA cross-border framework calendar
RSK-REG-016 | Regolatorio | AI Act (Reg.UE 2024/1689) - payload IR + biometric classification high-risk Annex III | Garante o AgID classifica sistemi IR onboard come 'alto rischio AI Act' | 3 | 4 | 12 | YELLOW | Open-High | data-privacy-counsel + DPO | Mitigate | Privacy by design hardware (blur on-board obbligatorio); esclusione esplicita riconoscimento biometrico; engagement Garante + AgID pre-clearance; conformity assessment Notified Body se richiesto | 2 | 3 | 6 | Y1+ | medium | 2026-05-17 | Garante delibere AI Act + AgID circolari + EU AI Office guidance
RSK-REG-026 | Regolatorio | Insurance BVLOS - mancata copertura broker aviation o premio > 100k EUR/anno | Tender broker non riceve quotation accettabile per BVLOS Pentema | 4 | 3 | 12 | YELLOW | Open-High | financial-cfo + ops | Transfer+Mitigate | Tender con broker specializzati aviation (Marsh, Aon, Willis Italia); copertura RC+casco+cyber+privacy; piano captive insurance Y3+ | 3 | 2 | 6 | Y0+ | medium | 2026-05-17 | Market hardening aviation insurance + quotation timing
RSK-REG-020 | Regolatorio | Codice Penale art. 432-bis - responsabilita penale PIC + organizzazione D.Lgs.231 | Incidente UAS BVLOS con conseguenze (near-miss vs aviazione manned o danni terzi) | 2 | 5 | 10 | YELLOW | Open-High | aviation-regulatory + ops + legal | Mitigate+Transfer | Assicurazione RC+casco BVLOS adeguata (>=5M EUR); D.Lgs.231 modello organizzativo; SOPs rigorosi; training PIC; safety reporting culture | 1 | 4 | 4 | Y1+ | medium | 2026-05-17 | Incident reports settore UAS BVLOS Italia + near-miss tracking interno
RSK-REG-002 | Regolatorio | SORA SAIL III Pentema BVLOS - richiede percorso Certified Category EASA | ENAC in pre-application valuta SAIL > III per scenario Pentema (popolato + critical) | 3 | 3 | 9 | YELLOW | Open-High | aviation-regulatory | Mitigate | Pre-application meeting ENAC M+3-6 + M1 (operational mitigation) + M2 (technical mitigation, parachute + flight termination) | 2 | 3 | 6 | Y1 (M+3-9) | medium-high | 2026-05-17 | ENAC pre-app feedback + SAIL determination doc
RSK-REG-003 | Regolatorio | AGCOM spettro HAPS Italia - banda S non assegnata per HAPS commercial | AGCOM emette consultazione spettro senza include HAPS service link | 3 | 3 | 9 | YELLOW | Monitor | telecom-ntn-payload-expert + aviation-regulatory | Mitigate | Engagement AGCOM precoce (DR-005); domanda licenza sperimentale L1+L5; partecipazione consultazione ITU-R WP 5C | 2 | 3 | 6 | Y3-Y4 | medium | 2026-05-17 | AGCOM delibera spettro UAS/HAPS + ITU-R WRC outcomes
RSK-REG-009 | Regolatorio | Notified Body shortage - CE marking AI Act + Direttiva Macchine + radio | Mercato NB satura su AI Act 2026-27; tempo attesa > 12 mesi | 3 | 3 | 9 | YELLOW | Monitor | systems-engineer + data-privacy | Mitigate | Engagement early NB (TUV, IMQ, Bureau Veritas); preparazione pre-assessment documentazione | 2 | 2 | 4 | Y2-Y3 | medium | 2026-05-17 | NB capacity report ACCREDIA + waiting time tracking
RSK-REG-013 | Regolatorio | Coordinamento ENAV - manca AIP procedure UAS BVLOS Pentema | ENAV non rilascia procedura AIP entro M+9 | 3 | 3 | 9 | YELLOW | Open-High | aviation-regulatory + vtol-uas-specialist | Mitigate | Engagement ENAV Genova ACC; NOTAM dedicato per ogni missione; coordinamento con CAA militare Mar Ligure | 2 | 3 | 6 | Y1 | medium-high | 2026-05-17 | ENAV response time + AIP Italy SUP
RSK-REG-014 | Regolatorio | Garante Privacy - precedenti negativi su EO/UAS in spazi pubblici | Provvedimento Garante simile (es. sorveglianza droni Comuni) rivela limiti | 3 | 3 | 9 | YELLOW | Open-Medium | data-privacy-counsel | Mitigate | Analisi precedenti Garante (DR-006); DPIA conforme; documentazione necessita/proporzionalita | 2 | 2 | 4 | Y1+ | medium | 2026-05-17 | Garante provvedimenti pubblicati + sentenze Cassazione
RSK-REG-022 | Regolatorio | ATEX (Reg.UE 2014/34) batterie LiS storage - hangar classificato zona 1 | ASL/VVF ispezione hangar Pentema classifica zona ATEX senza protezioni adeguate | 3 | 3 | 9 | YELLOW | Open-Medium | propulsion-engineer + safety + ops | Mitigate | Hangar dedicato con ventilazione anti-esplosione (LEL detection + emergency vent); procedure ATEX; formazione operatori; assicurazione adeguata | 2 | 2 | 4 | Y1+ | medium | 2026-05-17 | Ispezioni ASL/VVF programma + thermal events battery settore
RSK-REG-029 | Regolatorio | Direttiva Macchine Reg.UE 2023/1230 - ground equipment GS+carrelli CE marking obbligatorio | Phase B 6B ground equipment custom non CE-marked | 3 | 3 | 9 | YELLOW | Monitor | systems-engineer | Mitigate | Design CE-compliant fin da concept; collaborazione con ente notificato; risk assessment + DoC | 2 | 2 | 4 | Y3+ | medium | 2026-05-17 | Ground equipment design review + NB engagement
RSK-REG-005 | Regolatorio | GDPR enforcement DPIA - DPA ricorre vs operazioni EO sorveglianza territoriale | Garante apre procedimento o richiede stop attivita | 2 | 4 | 8 | YELLOW | Open-High | data-privacy-counsel + DPO | Mitigate | DPIA pubblica + edge anonymization + consultazione preventiva Garante + geofence + retention policy stringente | 1 | 3 | 3 | Y1+ | medium-high | 2026-05-17 | Comunicati Garante + provvedimenti UAS/EO settore
RSK-REG-010 | Regolatorio | ITAR/EAR US restrictions - componenti US-origin (chip Honeywell/Collins, celle Spectrolab) | US BIS pubblica restrictions su componenti HAPS-related EU | 2 | 4 | 8 | YELLOW | Open-High | supply-chain + sovereign-strategist | Mitigate | Mapping componenti US-origin + EU sovereign alternatives roadmap (Azur Space, ACC, STM) + stock buffer 12 mesi | 2 | 3 | 6 | Y2+ | medium | 2026-05-17 | BIS Entity List update + ITAR notice settore aerospace
RSK-REG-004 | Regolatorio | U-Space transizione 2027 - ENAC procedura USSP italiana non definita | ENAC delay implementazione Reg.UE 2021/664 oltre 2027 | 3 | 2 | 6 | GREEN | Monitor | aviation-regulatory | Mitigate | Engagement ENAC U-Space tavolo nazionale; partecipazione D-Flight pilot Pentema; SORA fallback continua | 2 | 2 | 4 | Y2-Y3 | medium | 2026-05-17 | ENAC U-Space roadmap pubblicato + D-Flight expansion
RSK-REG-006 | Regolatorio | Geographical zones ENAC - Pentema in zona vincolata (parco Antola, ZSC) | Mappa D-Flight aggiornata classifica area Pentema come restricted | 2 | 3 | 6 | GREEN | Monitor | aviation-regulatory | Mitigate | Verifica D-Flight pre-mission; coordinamento Ente Parco Antola; NOTAM dedicato; finestre temporali | 1 | 3 | 3 | Y1+ | high | 2026-05-17 | D-Flight zone update + Ente Parco notice
RSK-REG-007 | Regolatorio | EASA SORA 2.5 transizione - documentazione SORA pre-existente da aggiornare | ENAC richiede re-submission SORA secondo ED Decision 2025/018/R post Sep 2025 | 3 | 2 | 6 | GREEN | Open-Medium | aviation-regulatory | Mitigate | SORA documentation SORA 2.5 compliant fin da prima applicazione; consulenza ENAC pre-app | 2 | 2 | 4 | Y1 | medium-high | 2026-05-17 | EASA AMC update + ENAC circolari implementative
RSK-REG-012 | Regolatorio | Reg.UE 2019/947 evoluzione - revisione 2027 puo cambiare classificazione SORA | EASA NPA pubblicata con revisione SORA framework | 3 | 2 | 6 | GREEN | Monitor | aviation-regulatory | Mitigate | Monitoring NPA EASA; partecipazione consultation; flessibilita design | 2 | 2 | 4 | Y2-Y3 | medium | 2026-05-17 | EASA NPA calendar + ED Decision pubblicazioni
RSK-REG-017 | Regolatorio | EUSPA accreditation downstream services - mancato accesso fondi/GOVSATCOM | EUSPA emette guideline che escludono HAPS dai servizi spaziali downstream | 2 | 3 | 6 | GREEN | Monitor | sovereign-strategist | Mitigate | Engagement EUSPA via CASSINI accelerator; workshop downstream services HAPS; mapping intersezione GOVSATCOM | 2 | 2 | 4 | Y3+ | medium | 2026-05-17 | EUSPA workplan pubblicato + CASSINI HAPS call
RSK-REG-023 | Regolatorio | RoHS (Dir.2011/65/UE) - componenti elettronici cinesi JOUAV potenzialmente non compliant | Audit RoHS BOM rivela componente critico non-RoHS | 3 | 2 | 6 | GREEN | Monitor | systems-engineer + supply-chain | Mitigate | Verifica DoC ogni componente BoM; audit RoHS pre-deployment; sostituzione componenti non-compliant | 2 | 2 | 4 | Y1 | medium-high | 2026-05-17 | BOM audit RoHS quarterly + vendor DoC update
RSK-REG-024 | Regolatorio | Codice Navigazione R.D. 327/1942 - diritti sorvolo proprieta private + aree militari | Contestazione legale da proprietari o sorvolo area militare non mappata | 2 | 3 | 6 | GREEN | Monitor | regulatory + community + ops | Mitigate | Mappa aree militari/sensibili Liguria; consenso proprietari grandi appezzamenti; NOTAM coordinato; engagement comunita Pentema | 1 | 2 | 2 | Y1+ | medium | 2026-05-17 | Mappa NOTAM/restricted aggiornata + community feedback
RSK-REG-028 | Regolatorio | Galileo PRS - dual-use civile-difesa Phase B richiede CASD/Difesa authorization | Phase B 6B dichiara dual-use; CASD richiede clearance personale + tecnologia | 2 | 3 | 6 | GREEN | Monitor | sovereign-strategist + CASD | Mitigate | Y1 usare GNSS standard L1/L5 + Galileo open service + anti-spoofing software-based; engagement CASD solo se dual-use Fase 3+ | 1 | 2 | 2 | Y3+ | medium | 2026-05-17 | Phase B scope clearance + CASD engagement plan
RSK-REG-011 | Regolatorio | VIA (Valutazione Impatto Ambientale) Pentema - hangar + GS in area protetta | ARPA Liguria richiede VIA per infrastruttura ground HALE | 2 | 2 | 4 | GREEN | Monitor | environmental + ops | Mitigate | VIA preliminare M+6; coordinamento con Ente Parco Antola; design infrastruttura minimale + reversibile | 1 | 2 | 2 | Y1 | medium-high | 2026-05-17 | ARPA notice + Ente Parco feedback

## RSK-FIN
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-FIN-001 | Finanziario | Mancanza commitment funding Phase B 6B - 5.5-13.5M EUR mix EDF+Horizon+PNRR+equity | Gate G5 M+24 mostra funding mix Phase B < 30% | 4 | 5 | 20 | RED | Showstopper | financial-cfo + sovereign-strategist | Mitigate | Mix funding: EDF (DG DEFIS) + Horizon Europe + PNRR Aerospazio + Series B equity (CDP, EIB); fasi graduali; partnership prime per cost sharing | 3 | 4 | 12 | Y2-Y3 (gate G5) | medium-high | 2026-05-17 | Calendar bandi EDF/Horizon + Series B pipeline + LoI investitori
RSK-FIN-004 | Finanziario | OpEx Y1 underestimato - +450-800k EUR per 3 FTE regulatory (CISO+DPO+Head Reg.Aff) | Audit regulatory M+3 rivela 3 FTE addizionali non-budget | 5 | 3 | 15 | RED | Open-Critical | financial-cfo | Mitigate | Aggiornamento Cap.8 OpEx Y1 con +450-800k EUR fixed cost; revisione mix funding equity Series A; cost sharing su CISO/DPO via partnership cooperative | 4 | 2 | 8 | Y0-Y1 | high | 2026-05-17 | FTE hire pipeline + payroll forecast
RSK-FIN-005 | Finanziario | Slittamento grant FESR/PNRR - tempi PA italiani median 18-30 mesi | Grant FESR Liguria comunicato slittato > 12 mesi vs piano | 4 | 3 | 12 | YELLOW | Open-High | financial-cfo + snai-funding | Mitigate | Bridge financing (banca + founder); pipeline grant multiple parallele; flessibilita timeline progetto | 3 | 2 | 6 | Y1-Y3 | high | 2026-05-17 | Grant decisional timeline tracking + Regione comunicazioni
RSK-FIN-006 | Finanziario | WACC effettivo > 18% se grant mix < 30% - NPV diventa negativo (sensitivity Cap.8) | Grant mix committed < 30% al M+12 | 3 | 4 | 12 | YELLOW | Open-High | financial-cfo | Mitigate | Pricing premium servizi + cost optimization OpEx; renegotiate equity terms; cost-shared infrastructure con cooperative | 2 | 3 | 6 | Y1-Y3 | medium-high | 2026-05-17 | Grant commitment % monthly + NPV sensitivity update
RSK-FIN-008 | Finanziario | Cash flow gap Y2-Y3 - revenue ramp lento vs OpEx fixed | Revenue Y2 < 500k EUR (50% target) | 3 | 4 | 12 | YELLOW | Open-High | financial-cfo + business-model | Mitigate | Bridge financing Series A; cost flex su FTE variable; contratti pluriennali Regione anticipated payment | 2 | 3 | 6 | Y2-Y3 | medium | 2026-05-17 | Revenue actuals monthly + cash burn rate
RSK-FIN-009 | Finanziario | Series A non chiude (Y2) - valutazione investitori < 8M EUR pre-money | Valutazione Series A < 5M EUR o tempi > 12 mesi | 3 | 4 | 12 | YELLOW | Open-High | financial-cfo + CEO | Mitigate | Investor relations pipeline (CDP Venture, EIC Fund, BPER); milestone-based bridge financing; alternative grant heavy mix | 2 | 3 | 6 | Y2 | medium | 2026-05-17 | Investor meetings pipeline + comparable Series A aerospace IT
RSK-FIN-003 | Finanziario | Sovracosti CapEx 6A - quotation vendor real-world supera baseline 700k-2M EUR +30-50% | Quotation JOUAV/Tekever + payload + GS supera budget +30% | 3 | 3 | 9 | YELLOW | Open-High | financial-cfo + systems-engineer | Mitigate | Quotation parallel vendor multipli; contingency 20% in budget; scope reduction MVP se necessario | 2 | 3 | 6 | Y1 | medium | 2026-05-17 | Quotation report vendor mensile + market index UAS
RSK-FIN-010 | Finanziario | ROI insurance premium + safety provision - +50-150k EUR/anno OpEx ricorrente | Premio assicurativo BVLOS + cyber > 100k EUR/anno | 4 | 2 | 8 | YELLOW | Open-High | financial-cfo + risk | Accept+Transfer | Tender broker + adeguamento periodico; captive insurance scenario Y3+ | 3 | 2 | 6 | Y1+ | high | 2026-05-17 | Premio quote annuale + claims tracking
RSK-FIN-007 | Finanziario | Currency risk - JOUAV CN forniture USD-denominated + EUR weakness | EUR/USD < 0.95 sustained o tariffe import +10% | 3 | 2 | 6 | GREEN | Monitor | financial-cfo + supply-chain | Transfer | Hedging EUR/USD forward per acquisti CapEx; quotation EUR-denominated vendor EU (Tekever, Quantum) come benchmark | 2 | 2 | 4 | Y1 | medium | 2026-05-17 | EUR/USD daily + tariffe USA-CN update
RSK-FIN-002 | Finanziario | Mancato grant Coopfond Cooding (50k EUR seed) | Coopfond non finanzia Firmamento entro M+6 | 2 | 2 | 4 | GREEN | Open-Medium | financial-cfo + snai-funding | Accept | Alternative funding (FESR Liguria, bandi tematici Horizon, equity seed); bridge financing founder | 2 | 2 | 4 | Y0 | medium-high | 2026-05-17 | Coopfond decisione + alternative grant calendar

## RSK-MKT
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-MKT-001 | Mercato | Adozione lenta PA - cicli appalti pubblici 12-24 mesi vs piano 6-9 mesi | Contratti pluriennali Regione Liguria non firmati entro M+12 | 4 | 3 | 12 | YELLOW | Open-High | snai-funding + business-model | Mitigate | Anchor customer Regione + LoI pre-formale; contratti pluriennali quadro; partnership cooperative come veicolo di servizi | 3 | 3 | 9 | Y1-Y2 | high | 2026-05-17 | Bandi Regione publication + LoI tracking
RSK-MKT-002 | Mercato | Competitor Tier 1 AALTO-Leonardo JV - cattura 2-3 Regioni SNAI con pricing aggressivo | AALTO-Leonardo annuncia JV o pilota multi-regionale entro Y2 | 3 | 4 | 12 | YELLOW | Open-High | competitive-intelligence + business-model | Mitigate | Differenziazione cooperativa + sovranita IT; speed to market 6A; partnership CIRA/POLITO; lock-in cooperative Legacoop | 3 | 3 | 9 | Y2-Y3 | medium | 2026-05-17 | AALTO press releases + Leonardo strategy update
RSK-MKT-004 | Mercato | Pricing pressure - PA italiana clienti price-sensitive vs servizi premium | Tender Regione cost ceiling < 50k EUR/anno per servizio EO/SAR | 4 | 3 | 12 | YELLOW | Open-High | business-model + financial-cfo | Mitigate | Bundle servizi multipli (EO+IR+NTN+monitoring) per economia scale; cost-shared infrastruttura cooperative; modello canone vs ore-volo | 3 | 3 | 9 | Y1-Y3 | medium-high | 2026-05-17 | Tender history pricing + benchmark drone services market IT
RSK-MKT-005 | Mercato | Single-customer concentration Liguria - alternanza politica regionale evapora anchor | Elezioni Regione Liguria 2025+ portano cambio amministrazione + scope revision | 3 | 4 | 12 | YELLOW | Open-High | business-model + sovereign-strategist | Mitigate | Espansione 2-3 regioni SNAI Y3 (Piemonte, Marche, Calabria, Basilicata); LoI pre-formalizzata multi-region; contratti pluriennali con clausole continuita amministrative | 2 | 4 | 8 | Y2-Y3 | medium | 2026-05-17 | Elezioni regionali calendar + cambio assessori Liguria
RSK-MKT-008 | Mercato | Window IRIS2 chiude - posizionamento 'complementare' falsificato (vedi §5.16bis) | Y3 Commissione UE/SpaceRISE escludono layer stratosferici da architettura sovrana | 2 | 5 | 10 | YELLOW | Open-High | sovereign-strategist + CEO | Mitigate | Position paper 'Italian Stratospheric Sovereignty' Y1-Y2; engagement DG CNECT + DG DEFIS + SpaceRISE; alternative narrative 'EU sovereign multi-layer' | 2 | 4 | 8 | Y2-Y3 | medium | 2026-05-17 | IRIS2 architecture publications + SpaceRISE workplan + UE press releases
RSK-MKT-003 | Mercato | Sentinel/Copernicus competizione EO - servizi free open data minano pricing premium | Use case Pentema antincendio/SAR realizzabile con Sentinel a costo zero | 3 | 3 | 9 | YELLOW | Open-Medium | earth-observation-expert + business-model | Mitigate | Posizionamento high-resolution + low-latency vs Sentinel weekly + 10m; servizi value-added analytics + report customized | 2 | 3 | 6 | Y1+ | high | 2026-05-17 | Sentinel-2C/3C launch + Copernicus services expansion
RSK-MKT-006 | Mercato | Adozione cooperative lenta - 10 cooperative pilota non confermano partecipazione | M+6 < 6 cooperative confermano partecipazione formale | 3 | 3 | 9 | YELLOW | Open-Medium | business-model + Legacoop | Mitigate | Workshop cooperative Q+1; valore proposto chiaro + canone accessibile; pilot gratuito M+0-3; community engagement | 2 | 3 | 6 | Y0-Y1 | medium-high | 2026-05-17 | Cooperative engagement metrics + LoI signed
RSK-MKT-007 | Mercato | Servizi NTN 6B mercato - 5G NTN adozione lenta vs piano IRIS2/Starlink | 5G NTN deployment commerciale < 10% device EU entro Y4 | 3 | 3 | 9 | YELLOW | Monitor | telecom-ntn-payload-expert + business-model | Mitigate | Servizi NTN target settori dedicated (emergency, IoT rurale) vs mass market; pricing capacity wholesale | 3 | 2 | 6 | Y4+ | medium | 2026-05-17 | 5G NTN device shipments + IRIS2/Starlink Direct-to-Device launches
RSK-MKT-009 | Mercato | Mercato VTOL UAS satura - 50+ vendor commerciali, commoditization pricing | Prezzo medio servizio EO con drone < 5 EUR/ha entro Y3 | 3 | 2 | 6 | GREEN | Monitor | business-model | Mitigate | Differenziazione service-only + cooperative + sovranita; bundling value-added analytics; vertical integration use cases SNAI | 2 | 2 | 4 | Y2+ | medium-high | 2026-05-17 | Mercato benchmark drone services IT/EU pricing
RSK-MKT-010 | Mercato | Cambiamento normativa SNAI - riduzione fondi Aree Interne 2027+ | PSNAI 2027+ riduce dotazione fondi aree interne | 2 | 3 | 6 | GREEN | Monitor | snai-funding | Mitigate | Diversificazione cliente PA (PC, Difesa civile, agricoltura); fondi Horizon + INTERREG | 2 | 2 | 4 | Y3+ | medium | 2026-05-17 | DPCM PSNAI publications + budget aree interne

## RSK-OPS
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-OPS-003 | Operativo | Reclutamento pilota UAS specialist BVLOS - mercato compresso in Italia | Tempo hire pilota BVLOS > 6 mesi | 4 | 3 | 12 | YELLOW | Open-High | HR + business-model | Mitigate | Training in-house pilota junior; partnership con scuole UAS (es. Volandia, scuole Aero IT); contratti competitivi | 3 | 2 | 6 | Y1 | medium-high | 2026-05-17 | Job market UAS pilots IT + scuole UAS graduates
RSK-OPS-002 | Operativo | Incidente UAS BVLOS sul territorio - danno a persone/cose/aviazione manned | Near-miss vs aviazione manned o danno a terzi | 2 | 5 | 10 | YELLOW | Open-Critical | aviation-regulatory + ops + safety | Mitigate+Transfer | SORA M2 mitigation (parachute, flight termination); GRC mitigation (geofence, Lost-Link); assicurazione adeguata; SOPs rigorosi; training continuo | 1 | 4 | 4 | Y1+ | high | 2026-05-17 | Incident reports settore IT/EU + near-miss interno + FAR/MDR drone
RSK-OPS-001 | Operativo | Operazioni invernali Appennino Ligure - neve, ghiaccio, basse temp riducono giorni op. | Inverno 2026-27 mostra < 60% giorni operativi vs piano | 3 | 3 | 9 | YELLOW | Open-High | vtol-uas-specialist + ops | Mitigate | Training pilota inverno; finestre operative meteo-dipendenti; de-icing batterie+celle; planning seasonal | 2 | 3 | 6 | Y1+ | high | 2026-05-17 | Meteo Pentema mensile + giorni op. tracking
RSK-OPS-004 | Operativo | Disponibilita piattaforma - lead time JOUAV/Tekever 6-12 mesi standard | Order placement > M+6 ritarda first flight oltre M+12 | 3 | 3 | 9 | YELLOW | Open-Medium | vtol-uas-specialist + supply-chain | Mitigate | Order placement early M+3; stock spare parts; rental option backup | 2 | 2 | 4 | Y1 | medium-high | 2026-05-17 | Vendor lead time updates + order confirmations
RSK-OPS-005 | Operativo | Manutenzione UAS - downtime non programmato > 20% target | Downtime cumulativo Y1 > 60 giorni | 3 | 3 | 9 | YELLOW | Open-Medium | ops + maintenance | Mitigate | Piano manutenzione preliminare; spare parts kit on-site; vendor support contract; secondo UAV backup Y2 | 2 | 3 | 6 | Y1+ | medium-high | 2026-05-17 | Downtime tracking weekly + MTBF metrics
RSK-OPS-006 | Operativo | Coordinamento PC Liguria - tempi attivazione emergency > target | Test esercitazione PC mostra tempo attivazione > 4h | 3 | 3 | 9 | YELLOW | Monitor | ops + community-engagement | Mitigate | MoU PC Liguria + procedure attivazione 24/7; training congiunto PC+Firmamento; SLA contrattuale | 2 | 2 | 4 | Y1+ | medium | 2026-05-17 | Esercitazioni PC + tempo attivazione actuals
RSK-OPS-009 | Operativo | Scalabilita ops Y2-Y3 - team ops sottodimensionato per 2-3 regioni | Y2 espansione 2 regioni richiede team 2x ma hire delay | 3 | 3 | 9 | YELLOW | Monitor | HR + ops | Mitigate | Pianificazione hire Y2 (3-4 FTE ops); training accelerato; tooling automazione operations management | 2 | 2 | 4 | Y2-Y3 | medium | 2026-05-17 | Hire pipeline + tools deployment
RSK-OPS-007 | Operativo | Meteo estremo - alluvioni Liguria > 100mm/24h blocca operazioni | Frequenza eventi estremi 2026 > 2 vs media | 4 | 2 | 8 | YELLOW | Open-High | ops + business-model | Accept+Mitigate | Buffer giorni operativi piano; UAV ricovero indoor; servizi differiti accettati cliente PA | 3 | 2 | 6 | Y1+ | high | 2026-05-17 | Meteo storico Liguria + ARPAL allerte
RSK-OPS-008 | Operativo | Comunita Pentema - contestazioni rumore/privacy/sicurezza limitano accettazione | Reclami formali residenti > 5/anno o petizione | 2 | 3 | 6 | GREEN | Open-Medium | community-engagement + ops | Mitigate | Workshop comunita pre-deploy M+6; canone partecipazione + benefit locali; trasparenza operazioni; finestre orarie | 1 | 2 | 2 | Y1+ | medium-high | 2026-05-17 | Community feedback monitoring + reclami tracking
RSK-OPS-010 | Operativo | Data pipeline processing latency - target near-real-time vs realta batch | Test pipeline EO data delivery > 1h vs target 15 min | 3 | 2 | 6 | GREEN | Monitor | earth-observation-expert + IT | Mitigate | Edge processing UAV + cloud parallel; ottimizzazione pipeline; SLA realistico con cliente | 2 | 2 | 4 | Y1+ | medium-high | 2026-05-17 | Pipeline latency monitoring + SLA compliance
RSK-OPS-011 | Operativo | Sicurezza personale - DUVRI ops montane + formazione D.Lgs.81/2008 | Audit ASL rivela DUVRI/formazione carente | 2 | 3 | 6 | GREEN | Open-Medium | safety + HR | Mitigate | DUVRI formalizzato M+3; formazione D.Lgs.81 obbligatoria; PPE adeguati; medical surveillance | 1 | 2 | 2 | Y1+ | high | 2026-05-17 | Audit ASL programma + formazione completion
RSK-OPS-012 | Operativo | Hangar Pentema disponibilita - struttura fisica adeguata non disponibile in loco | Survey M+3 non trova hangar suitable Pentema | 2 | 3 | 6 | GREEN | Open-Medium | ops + community | Mitigate | Survey siti alternativi Torriglia/Casella; container temporaneo; partnership cooperative locali per spazi | 1 | 2 | 2 | Y1 | medium-high | 2026-05-17 | Site survey results + lease negotiations

## RSK-SUP
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-SUP-003 | Supply Chain | Batterie LiS - capacity allocation Northvolt/Italvolt incerta | Northvolt bankruptcy o Italvolt ritardo > 2 anni production | 4 | 4 | 16 | RED | Open-High | propulsion-energy-engineer + supply-chain | Mitigate | Multi-vendor LiS pipeline (Oxis Energy heir, Lyten, NexTech); custom pack assembly con cell suppliers diversi | 3 | 3 | 9 | Y3+ | medium | 2026-05-17 | Battery vendors financials + production timelines
RSK-SUP-002 | Supply Chain | Single source celle solari multi-junction GaAs - concentrazione Spectrolab (US) | Spectrolab export restriction o capacity allocation military priority | 3 | 4 | 12 | YELLOW | Open-High | propulsion-energy-engineer + supply-chain | Mitigate | Azur Space (DE) qualification path; engagement Enel 3SUN (IT); EU CRMA Strategic Project status | 2 | 3 | 6 | Y3+ | medium | 2026-05-17 | Spectrolab capacity announcements + Azur Space EU production
RSK-SUP-001 | Supply Chain | Lead time JOUAV (vendor CN) - escalation tariffaria USA-CN blocca import | USA/UE pubblicano restrizioni componenti CN aerospace | 3 | 3 | 9 | YELLOW | Open-High | vtol-uas-specialist + supply-chain | Mitigate | Plan B Tekever (PT) pronto entro M+9; stock spare parts 12 mesi; valutazione Quantum (DE) terzo backup | 2 | 3 | 6 | Y1+ | high | 2026-05-17 | USA BIS notices + UE FDI screening + tariffe announcements
RSK-SUP-004 | Supply Chain | Chip GNC aerospace-grade - Honeywell/Collins concentration + ITAR risk | ITAR application su componenti aerospace-grade per HAPS EU | 2 | 4 | 8 | YELLOW | Open-High | avionics-gnc-engineer + supply-chain | Mitigate | STM (FR-IT) qualification path; engagement Leonardo Elettronica; dual sourcing US+EU | 2 | 3 | 6 | Y3+ | medium | 2026-05-17 | BIS Entity List update + STM/Leonardo capacity
RSK-SUP-005 | Supply Chain | FPGA radhard DAL-B - Microchip RTPolarFire single source EU acquisable | Microchip allocation military priority o delay > 12 mesi | 2 | 3 | 6 | GREEN | Monitor | avionics-gnc-engineer + supply-chain | Mitigate | Xilinx Versal AI Edge alternative; stock buffer 24 mesi; design flessibile FPGA-vendor agnostic | 2 | 2 | 4 | Y3+ | medium | 2026-05-17 | Microchip lead times + Xilinx alternative qualification
RSK-SUP-006 | Supply Chain | Materiali compositi CFRP - Toray (JP) + Hexcel (FR-US) supplier concentration | Disruption shipping Asia-EU o ITAR Hexcel US-derived | 2 | 3 | 6 | GREEN | Monitor | aero-structures-engineer + supply-chain | Mitigate | Solvay (BE) qualification + Italian carbon producers (Mapei, Saati) + stock 12 mesi | 2 | 2 | 4 | Y3+ | medium | 2026-05-17 | Shipping rates + Solvay/Mapei capacity
RSK-SUP-007 | Supply Chain | Lino fibra Italia - capacita produzione artigianale, lead time variabile | Produttore lino IT incapace fornire qualita aeronautica certificata | 3 | 2 | 6 | GREEN | Monitor | aero-structures-engineer + supply-chain | Mitigate | Multi-vendor lino IT (Linificio Canapificio Nazionale, Biogear partner); test qualifica panel; backup vendor BE/NL | 2 | 2 | 4 | Y3+ | medium | 2026-05-17 | Lino vendor capacity + qualifica test results

## RSK-PRV
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-PRV-006 | Privacy/Legale | AI Act conformity assessment - Notified Body bottleneck (cf RSK-REG-016/009) | Conformity assessment AI Act > 12 mesi ritardo | 3 | 3 | 9 | YELLOW | Monitor | data-privacy + systems-engineer | Mitigate | Engagement early NB; pre-assessment documentazione; design AI Act-compliant fin da concept | 2 | 2 | 4 | Y2-Y3 | medium | 2026-05-17 | NB capacity reports + assessment timelines
RSK-PRV-003 | Privacy/Legale | GDPR breach data subject - leak dati EO + biometrici | Cyber incident con esfiltrazione dati sensibili | 2 | 4 | 8 | YELLOW | Open-High | DPO + CISO | Mitigate+Transfer | ISMS Part-IS + ISO 27001; crittografia at-rest + in-transit; incident response plan; assicurazione cyber | 1 | 3 | 3 | Y1+ | medium-high | 2026-05-17 | Security incidents tracking + threat intel feeds
RSK-PRV-005 | Privacy/Legale | Liability contrattuale PA - SLA non rispettato in emergenza (PC, antincendio) | Servizio non disponibile durante emergenza con conseguenze | 2 | 4 | 8 | YELLOW | Open-High | legal + ops | Mitigate+Transfer | SLA realistici con buffer; assicurazione professional indemnity; ridondanza operativa; clausole force majeure | 1 | 3 | 3 | Y1+ | medium | 2026-05-17 | SLA actuals tracking + dispute history
RSK-PRV-007 | Privacy/Legale | IP infringement - patent claim su tecnologia HALE solare o NTN | Cease & desist letter da competitor (AALTO, Skydweller) | 2 | 4 | 8 | YELLOW | Monitor | legal + IP counsel | Mitigate | Freedom-to-Operate analysis pre-Phase B; patent portfolio Firmamento; differenziazione design vs competitor | 1 | 3 | 3 | Y3+ | medium | 2026-05-17 | Patent landscape monitoring + competitor IP filings
RSK-PRV-001 | Privacy/Legale | DPIA blocca casi d'uso sorveglianza territoriale - Garante richiede riduzione scope | DPIA review M+6 da Garante richiede scope reduction | 2 | 3 | 6 | GREEN | Open-Medium | data-privacy-counsel + DPO | Mitigate | Privacy by design fin da concept; edge anonymization; geofence aree residenziali; DPIA consultazione preventiva Garante | 1 | 2 | 2 | Y1 | medium-high | 2026-05-17 | Garante DPIA feedback + provvedimenti settore
RSK-PRV-002 | Privacy/Legale | Contenzioso privacy individuale - cittadino ricorre vs sorvolo proprieta privata | Ricorso TAR/Garante da cittadino Pentema | 2 | 3 | 6 | GREEN | Open-Medium | data-privacy-counsel + legal | Mitigate+Transfer | Trasparenza operazioni; consenso preventivo proprietari grandi appezzamenti; assicurazione legal protection; mediation community | 1 | 2 | 2 | Y1+ | medium | 2026-05-17 | Reclami tracking + comunicazioni TAR
RSK-PRV-004 | Privacy/Legale | Contenzioso cooperative - dispute interno governance/revenue sharing | Cooperative member ricorre vs Firmamento o tra loro | 2 | 3 | 6 | GREEN | Monitor | legal + business-model | Mitigate | Accordo cooperativa formalizzato + statuto chiaro; arbitrato Legacoop; comunicazione trasparente | 1 | 2 | 2 | Y1+ | medium-high | 2026-05-17 | Member feedback + assemblea decisions

## RSK-SEC
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-SEC-004 | Cybersecurity | Supply chain attack - componente HW/SW compromesso fornitore | CVE critico componente in BoM o vendor compromise public | 3 | 3 | 9 | YELLOW | Monitor | CISO + supply-chain | Mitigate | SBOM (Software Bill of Materials) maintained; vendor security assessment; firmware signing; CVE monitoring continuous | 2 | 3 | 6 | Y1+ | medium | 2026-05-17 | CVE feeds + vendor advisory notifications
RSK-SEC-001 | Cybersecurity | Cyber attack ground segment - data breach Pentema (NIS2 incident reportable) | Intrusion detected su GS Pentema o cloud Aruba/OVH | 2 | 4 | 8 | YELLOW | Open-High | CISO (new) + IT | Mitigate | Zero-trust architecture; segregazione rete; NIS2 readiness + ISMS Part-IS; SOC managed service; ISO 27001 | 1 | 3 | 3 | Y1+ | medium-high | 2026-05-17 | SIEM alerts + ACN threat intel + sector incidents
RSK-SEC-003 | Cybersecurity | Ransomware ground segment - servizi PA bloccati + reputazione | Ransomware infection rilevato | 2 | 4 | 8 | YELLOW | Open-High | CISO + IT | Mitigate | Backup offsite 3-2-1; immutable backups; EDR su endpoint; ZTNA su accessi remoti; cyber insurance | 1 | 3 | 3 | Y1+ | medium-high | 2026-05-17 | Ransomware sector trends + EDR alerts
RSK-SEC-007 | Cybersecurity | Compromissione DOA partner - Phase C dependency su DOA esterna | DOA partner compromised o licenza sospesa | 2 | 4 | 8 | YELLOW | Monitor | CISO + sovereign-strategist | Mitigate | Multi-partner DOA option; due diligence partner cybersecurity; contract clauses continuity | 1 | 3 | 3 | Y5+ | medium | 2026-05-17 | Partner security posture review
RSK-SEC-005 | Cybersecurity | Insider threat - dipendente o cooperative member compromette dati o operations | Anomaly access pattern o data exfiltration interno | 2 | 3 | 6 | GREEN | Monitor | CISO + HR | Mitigate | RBAC + least privilege; DLP solution; background check personale critico; offboarding procedure | 1 | 2 | 2 | Y1+ | medium | 2026-05-17 | User behavior analytics + access pattern monitoring
RSK-SEC-006 | Cybersecurity | DDoS service link HAPS - degradazione servizi NTN/EO downlink | DDoS pattern detected su gateway Ka-band o cloud endpoint | 2 | 3 | 6 | GREEN | Monitor | CISO + telecom-ntn | Mitigate | DDoS protection upstream provider (Cloudflare, Akamai); rate limiting; geo-blocking | 1 | 2 | 2 | Y3+ | medium-high | 2026-05-17 | Traffic anomaly detection
RSK-SEC-002 | Cybersecurity | Hijacking C2 link UAV BVLOS - takeover malicious operator | Anomalia command pattern detected su FCS | 1 | 5 | 5 | GREEN | Open-High | CISO + avionics-gnc-engineer | Mitigate | Crypto authentication AES-256 + mutual TLS; rolling keys; flight termination automatica su anomaly; air-gap FCS critical | 1 | 4 | 4 | Y1+ | medium-high | 2026-05-17 | FCS anomaly detection + sector threat reports

## RSK-HR
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-HR-002 | Risorse Umane | Reclutamento CISO + DPO + Head Regulatory - 3 ruoli senior in mercato compresso | Tempo hire > 9 mesi (vs target 3-6 mesi) | 4 | 4 | 16 | RED | Open-Critical | HR + CEO | Mitigate | Headhunter specializzati; contratti competitivi (180-220k EUR/anno per CISO senior); part-time fractional CISO/DPO M+0-6; partnership consulting Legal/Cyber | 3 | 3 | 9 | Y0-Y1 | medium | 2026-05-17 | Hire pipeline weekly + headhunter pipeline status
RSK-HR-001 | Risorse Umane | Difficolta reclutamento pilota UAS specialist BVLOS | Tempo hire pilota > 6 mesi | 4 | 3 | 12 | YELLOW | Open-High | HR + business-model | Mitigate | Training in-house pilota junior; partnership scuole UAS; contratti competitivi + benefits cooperative | 3 | 2 | 6 | Y1 | medium-high | 2026-05-17 | Job market UAS pilots IT + LinkedIn data + scuole UAS
RSK-HR-003 | Risorse Umane | Turnover senior team - exit founder member o key engineer | Member team key fa exit non programmato | 2 | 4 | 8 | YELLOW | Open-High | CEO + HR | Mitigate | Founder agreement con vesting + restrictive covenants; equity incentive plan team; succession planning | 1 | 3 | 3 | Y1+ | medium | 2026-05-17 | Engagement surveys + 1-on-1 reviews + market salary benchmarks
RSK-HR-004 | Risorse Umane | Formazione team Part-IS ISMS NIS2 - mancanza certificazioni interne | Audit Part-IS rivela formazione team carente | 3 | 2 | 6 | GREEN | Open-Medium | HR + CISO | Mitigate | Training plan certificazioni (ISO 27001 LA, CISM, CISSP); budget formazione 10k EUR/FTE/anno; e-learning piattaforma | 2 | 2 | 4 | Y1+ | medium-high | 2026-05-17 | Training completion rates + certifications obtained
RSK-HR-005 | Risorse Umane | Diversita team - female engineering ratio < 20% riduce eligibility bandi EU | Bandi EU Gender Equality Plan richiesto e Firmamento non compliant | 3 | 2 | 6 | GREEN | Monitor | HR + CEO | Mitigate | GEP formalizzato; hire diversificato; partnership universita STEM women; mentoring programma | 2 | 2 | 4 | Y1+ | medium | 2026-05-17 | Team composition tracking + GEP compliance

## RSK-REP
ID | Categoria | Descrizione | Trigger | P (1-5) | I (1-5) | Score (PxI) | Color | Status | Owner | Response | Mitigation actions | Residual P | Residual I | Residual Score | Fase critica | Confidence | Last review | EWI
RSK-REP-005 | Reputazionale | Geopolitical narrative misalignment - linguaggio 'alternativa Starlink' attiva RSK-GEO-001 | Comunicazione interna o esterna usa framing competitive vs Starlink | 3 | 4 | 12 | YELLOW | Open-High | CEO + comms + sovereign-strategist | Mitigate | Communication guidelines: 'complementare a IRIS2' SEMPRE; mai 'vs Starlink'; press training; review pre-publication | 2 | 3 | 6 | Y1+ | high | 2026-05-17 | Communications audit monthly + media coverage analysis
RSK-REP-001 | Reputazionale | Incidente UAS BVLOS pubblico - copertura mediatica nazionale negativa | Incidente con conseguenze + coverage stampa nazionale | 2 | 5 | 10 | YELLOW | Open-Critical | CEO + comms | Mitigate+Transfer | Crisis communication plan; PR specialist on retainer; safety record positive + trasparenza; assicurazione legal protection + comms | 1 | 4 | 4 | Y1+ | medium-high | 2026-05-17 | Settore drone incidents IT/EU + sentiment monitoring
RSK-REP-004 | Reputazionale | Greenwashing accusation - claim ESG/lino contestato come marketing non sostanziale | Articolo investigativo o NGO accusa greenwashing | 3 | 3 | 9 | YELLOW | Open-Medium | CEO + comms + sustainability | Mitigate | LCA (Life Cycle Assessment) entro M+12; claim ESG verificabili + report sostenibilita; certification (B-Corp aspirazionale) | 2 | 2 | 4 | Y1+ | medium | 2026-05-17 | Media monitoring ESG/sustainability + NGO communications
RSK-REP-002 | Reputazionale | Contestazioni comunita Pentema - copertura locale negativa + petizione | Petizione comunita formalmente presentata o coverage giornalismo locale negativo | 2 | 3 | 6 | GREEN | Open-Medium | community-engagement + CEO | Mitigate | Engagement comunita continuo + benefit locali; mediazione Comune Torriglia + ENTE Parco; community advisory board | 1 | 2 | 2 | Y1+ | medium-high | 2026-05-17 | Community sentiment tracking + media monitoring locale
RSK-REP-003 | Reputazionale | Controversie cooperative - conflitto interno reputation rete Legacoop | Cooperative member exit pubblico con motivazioni negative | 2 | 3 | 6 | GREEN | Monitor | business-model + Legacoop | Mitigate | Trasparenza governance; mediazione Legacoop; comunicazione one-voice | 1 | 2 | 2 | Y1+ | medium | 2026-05-17 | Member feedback + Legacoop communications

## RSK-GEO
RSK-GEO - Rischi Geopolitici (RESERVED - reference only)
ATTENZIONE | Questo foglio riassume i 5 RSK-GEO solo come reference. Il dettaglio operativo, mitigation e trigger osservabili sono CLASSIFICATI in riferimenti/RESERVED-rischi-geopolitici.md - accesso ristretto founder team + consulenti NDA + stakeholder istituzionali IT su richiesta motivata.
RSK-ID | Categoria sintetica | P (cond.) | I (cond.) | Score (cond.) | Fase critica | Owner
RSK-GEO-001 | Frizione internazionale - posizione narrativa stratosferica | 3 | 4 | 12 | Y4+ | sovereign-strategist + CEO
RSK-GEO-002 | Classificazione strategica nazionale - governance obblighi | 2 | 4 | 8 | Y3+ | sovereign-strategist + legal + CEO
RSK-GEO-003 | Dipendenza supply chain non-EU | 3 | 4 | 12 | Y2+ | sovereign-strategist + supply-chain
RSK-GEO-004 | Misalignment con architettura sovrana EU multi-orbita | 3 | 4 | 12 | Y2-Y4 | sovereign-strategist + CEO
RSK-GEO-005 | Acquisizione difensiva da incumbent settore | 3 | 4 | 12 | Y3-Y4 | CEO + Board
Documento dettaglio | /home/user/HALE/riferimenti/RESERVED-rischi-geopolitici.md (NON pubblicabile)
Mitigation strategy | Vedi documento RESERVED + Engagement Plan strategico §5 + tavoli istituzionali presidiati (MIMIT, DPE, ACN, ENAC, ESA/DG CNECT, DG DEFIS, NATO DIANA, ASD-Eurospace, ASI/CIRA)
Re-assessment | Trimestrale - owner CEO + sovereign-infrastructure-strategist; review esterna annuale (advisor ex-MAE/MIMIT/Leonardo)

## FMECA_Payload
FMECA - Sottosistema Payload EO (RGB + IR LWIR + storage + downlink)
Metodologia: MIL-STD-1629A + IEC 60812 + ARP4761
Item | Failure Mode | Cause | Local Effect | System Effect | Severity (1-5) | Frequency (1-5) | Detection (1-5) | RPN (SxFxD) | Mitigation
Camera RGB Phase One iXM 100 | No image | Sensor failure (electronic) | Loss EO mission | Mission abort | 3 | 2 | 2 | 12 | Ridondanza dual sensor + healthcheck onboard
Camera RGB Phase One iXM 100 | Blur image | Vibrazioni gimbal / IBIS fail | Quality degradata | Re-fly necessario | 2 | 3 | 3 | 18 | Gimbal damping + IBIS + post-processing deblur
Camera RGB Phase One iXM 100 | Lens fog / cold | Termica + condensa | Quality degradata | Re-fly | 2 | 3 | 2 | 12 | Lens heater + dry-air purge
Gimbal Phase One IXM mount | Stuck position | Motor failure singolo asse | Off-target framing | Reduced area coverage | 3 | 3 | 2 | 18 | Service interval + ridondanza motor 2oo3
Gimbal | Vibration excess | Bearings wear | Image blur | Quality degradata | 2 | 3 | 3 | 18 | Maintenance schedule + bearing monitor
IR sensor WIRIS Pro LWIR | Calibrazione persa | Termica + tempo + drift | False alarm / missed hotspot | False positive antincendio | 4 | 3 | 4 | 48 | NUC frequente + crosscheck con RGB + ground truth
IR sensor | Sensor saturation | Sole diretto / sorgente HOT | Image saturated | Detection persa | 3 | 2 | 3 | 18 | Auto exposure + filter + look-angle planning
Storage on-board SSD aerospace | Corruzione data | Bit flip / temperatura / vibrazione | Loss data missione | Re-fly necessario | 3 | 2 | 3 | 18 | RAID-style ridondanza + ECC + on-line backup
Storage | Write failure full | Capacity exceeded | Mission data partial loss | Reduced data | 2 | 3 | 2 | 12 | Capacity monitoring + auto-purge oldest
Downlink data RF/SATCOM | Interruzione bandwidth | RF interference / weather | Delay delivery | Latency degradata | 2 | 3 | 4 | 24 | Buffer + retry + alt downlink + ACM
Downlink data | Authentication fail | Crypto key error | Loss telemetry/data link | Manual override | 2 | 2 | 2 | 8 | Key rotation + redundant auth + ground backup
LiDAR payload (Y3+) | Range error | Laser drift | GSD inaccurato | Mapping degradato | 2 | 2 | 3 | 12 | Calibration plate + crosscheck
Multispectral MicaSense (Y2+) | Filter mismatch | Filter wheel jam | Banda persa | Index errato | 2 | 2 | 2 | 8 | Pre-flight test + redundant filter
Power conversion DC-DC payload | Voltage drop | Capacitor failure | Power loss sensor | Sensor reset cascade | 3 | 2 | 2 | 12 | Caps redundant + monitor V real-time
Payload interface bus | Data bus corruption | EMI / connector | Wrong telemetry | Data integrity loss | 2 | 3 | 3 | 18 | Shielding + EMI filter + checksum CRC
Legenda RPN
RPN >= 40: mitigation obbligatoria (RED)
RPN 20-39: mitigation raccomandata (YELLOW)
RPN < 20: monitor (GREEN)

## FMECA_Avionica
FMECA - Sottosistema Avionica (FCS DAL-C + IMU triplex + GNSS + C2 + FTS)
Metodologia: MIL-STD-1629A + IEC 60812 + ARP4761
Item | Failure Mode | Cause | Local Effect | System Effect | Severity (1-5) | Frequency (1-5) | Detection (1-5) | RPN (SxFxD) | Mitigation
FCS autopilot DAL-C | Reboot unexpected | SEU / SW exception | Loss FCS momentaneo | Risk loss vehicle | 4 | 2 | 3 | 24 | 2oo3 voting + watchdog + ECC memory
FCS | Software defect runaway | SW bug undetected | Loss FCS control | Loss of vehicle | 5 | 1 | 3 | 15 | DAL-C process + testing + formal verification
IMU primary triplex | Drift gyro out of spec | Aging / temperature | Attitude error | Reduced nav accuracy | 3 | 3 | 2 | 18 | Triplex IMU + crosscheck + Kalman filter
IMU | Single IMU failure | Hardware fault | Reduced redundancy | Continue with 2oo3 | 2 | 3 | 2 | 12 | Triplex + auto-detection + isolation
GNSS dual-frequency | Spoofing detected | Adversary signal | Position error | Risk navigation | 3 | 3 | 3 | 27 | RAIM + IMU dead-reckoning + multi-constellation
GNSS | Jamming sustained | Adversary signal | Position loss | Risk navigation | 3 | 3 | 2 | 18 | Multi-frequency + IMU fallback + Lost-Link
ADS-B IN transponder | Failure no signal | HW fault | Loss traffic awareness | Increased risk collision | 3 | 2 | 1 | 6 | Vendor MTBF + spare + ATC notification
Communication C2 RF primary | Lost-Link | RF interference / range | C2 loss | Trigger Lost-Link Procedure | 3 | 3 | 2 | 18 | FHSS + SATCOM backup + RtB
SATCOM Iridium backup | Latency excessive | Network congestion | Delayed C2 response | Increased pilot reaction time | 2 | 2 | 2 | 8 | SLA Iridium + buffer + critical command priority
Power distribution avionics | Voltage drop | PSU failure | Avionics reset | FCS reboot | 3 | 3 | 2 | 18 | Redundant PSU + battery backup + monitor
Lost-Link procedure logic | Wrong RtB waypoint | Configuration error | Vehicle goes wrong direction | Risk recovery | 2 | 4 | 2 | 16 | Pre-flight check + dual config + simulation
Flight termination system | False trigger | Sensor anomaly | Unintended FTS | Loss vehicle but safe ground | 1 | 5 | 2 | 10 | Multi-sensor confirmation + manual confirm option
FTS | Failure to trigger | HW or logic fault | FTS does not deploy on command | Risk loss vehicle uncontrolled | 1 | 5 | 3 | 15 | Periodic test + dual-channel arming + simulation
Parachute deployment | Failure to deploy | Mechanism jam | Hard landing | Loss vehicle + risk to ground | 2 | 5 | 3 | 30 | Dual pyrotechnic + maintenance + test deployment
Air Data System (Pitot) | Pitot icing / clog | Ice / debris | Wrong airspeed | Aerodynamic stall risk | 3 | 3 | 2 | 18 | Pitot heater + redundant Pitot + alpha-beta sensor
Legenda RPN
RPN >= 40: mitigation obbligatoria (RED)
RPN 20-39: mitigation raccomandata (YELLOW)
RPN < 20: monitor (GREEN)

## FMECA_Propulsione
FMECA - Sottosistema Propulsione/Energia (motori + batterie + solare + thermal)
Metodologia: MIL-STD-1629A + IEC 60812 + ARP4761
Item | Failure Mode | Cause | Local Effect | System Effect | Severity (1-5) | Frequency (1-5) | Detection (1-5) | RPN (SxFxD) | Mitigation
Motor electric brushless 6A | Bearing failure | Wear / contamination | Power loss | Loss propulsion | 3 | 2 | 3 | 18 | Vibration monitor + service interval + spare
Motor electric brushless | Winding short | Insulation degradation | Loss motor | Loss propulsion | 4 | 2 | 3 | 24 | Insulation monitor + thermal cutoff + redundancy
Propeller composite | Blade strike | FOD / bird | Vibration + power loss | Emergency landing | 3 | 3 | 3 | 27 | Inspection pre-flight + replacement schedule + spare
Hybrid engine gasoline 6A | Carburator clog | Fuel quality / debris | Power loss | Emergency landing | 3 | 3 | 4 | 36 | Fuel filter + quality control + maintenance
Hybrid engine | Ignition failure | Spark plug fault | Engine stop | Glide to recovery + battery | 3 | 2 | 3 | 18 | Dual ignition + spare plugs + battery override
Battery LiPo VTOL 6A | Cell unbalance | Cell aging | Reduced capacity | Reduced autonomy | 4 | 2 | 2 | 16 | BMS active balancing + cell monitoring
Battery LiPo | Thermal runaway | Cell defect / overcharge | Fire / explosion | Loss vehicle + ground risk | 2 | 5 | 4 | 40 | Cell-level fuse + intumescent + BMS + ATEX storage
Battery LiS HALE 6B | Capacity fade | Cycle aging | Reduced storage | Reduced endurance | 4 | 3 | 3 | 36 | Cycle monitoring + DoD limit + replacement at 80% SoH
Battery LiS | Thermal runaway HALE | Cell defect stratospheric thermal | Fire / explosion HALE | Loss vehicle | 2 | 5 | 4 | 40 | Cell-level fuse + thermal monitor + emergency vent
Solar cells GaAs HALE | Degradation UV/thermal | Stratospheric environment | Reduced output | Reduced endurance | 3 | 3 | 3 | 27 | Margin design + redundant strings + bypass diodes
Solar cells | Hailstone / impact damage | Atmospheric event ascent/descent | String loss | Reduced output | 2 | 3 | 2 | 12 | Bypass diodes + redundant strings + reinforced surface
MPPT charge controller | MPPT loss tracking | SW defect / sensor | Power output reduced | Reduced storage | 3 | 2 | 2 | 12 | Redundant MPPT + monitoring + fallback fixed point
Thermal management batteries | Heater failure HALE | Heater HW fault | Battery freeze | Loss storage capacity | 3 | 4 | 2 | 24 | Redundant heater + thermal monitor + insulation
Thermal management | Coolant loss payload | Leak | Payload overheat | Payload shutdown | 2 | 3 | 3 | 18 | Closed loop + monitor + payload thermal cutoff
Fuel system 6A (hybrid) | Fuel leak | Connector / hose fail | Fuel loss + fire risk | Emergency landing | 2 | 4 | 3 | 24 | Double-seal + leak detector + emergency cutoff
Legenda RPN
RPN >= 40: mitigation obbligatoria (RED)
RPN 20-39: mitigation raccomandata (YELLOW)
RPN < 20: monitor (GREEN)

## FTA_LossOfVehicle
FTA Top event: Loss of Vehicle in BVLOS
Metodologia: ARP4761 + NUREG-0492 + IEC 61025
Notazione: AND-gate richiede tutti gli eventi; OR-gate richiede almeno uno; cut set = combinazione minima eventi che causa top event
TOP EVENT: Loss of Vehicle in BVLOS (Percorso 6A)
Target: P < 1E-5 / flight hour (compliant SAIL III SORA 2.5)
Loss of Vehicle [TOP, OR-gate]
¦
+--OR--> Lost-Link permanente + RtB fail
¦ ¦
¦ +--AND--> Lost-Link C2 (RF + SATCOM) P ~= 1E-4/h
¦ ¦ ¦
¦ ¦ +--RF link lost (FHSS jam/range) P ~= 1E-3/h
¦ ¦ +--SATCOM Iridium backup lost P ~= 1E-3/h
¦ ¦
¦ +--RtB procedure fail given Lost-Link P ~= 1E-3 cond.
¦ Cut set probability: 1E-4 * 1E-3 = 1E-7/h
¦
+--OR--> Avaria FCS critica
¦ ¦
¦ +--Failure autopilot DAL-C primary P ~= 1E-4/h
¦ +--AND--> IMU1 + IMU2 + IMU3 failure P ~= 1E-9/h
¦ +--GNSS spoofing sustained + no IMU P ~= 1E-5/h
¦ +--Software runaway DAL-C undetected P ~= 1E-6/h
¦ Cut set probability: ~1E-5/h
¦
+--OR--> Avaria propulsione + landing fail
¦ ¦
¦ +--Engine failure 6A (single) P ~= 1E-4/h
¦ +--AND--> Engine fail + parachute fail P ~= 1E-4 * 1E-3 = 1E-7/h
¦ +--Battery thermal runaway P ~= 1E-6/h
¦ +--Fuel exhaustion (planning fail) P ~= 1E-5/h
¦ Cut set probability: ~1E-5/h
¦
+--OR--> Cyber hijack
¦ ¦
¦ +--Crypto key compromise P ~= 1E-6/h
¦ +--Authentication bypass FCS P ~= 1E-6/h
¦ Cut set probability: ~1E-6/h
¦
+--OR--> Mid-air collision aviazione manned
¦ ¦
¦ +--ADS-B IN fail + ATC loss + no DAA P ~= 1E-6/h
¦ Cut set probability: ~1E-6/h
¦
+--OR--> Severe weather encounter
¦ ¦
¦ +--Forecast fail + storm intercept P ~= 1E-5/h
¦ Cut set probability: ~1E-5/h
Total Loss of Vehicle P (top event) ~= 2-3E-5/h
Compliance check vs SAIL III target 1E-5/h:
MARGINAL — necessita ulteriori mitigation per portare a < 1E-5/h:
- Reduce FCS DAL-C failure rate (HW redundancy + formal verification)
- Improve weather forecast integration (NOWCAST + abort)
- Improve GNSS robustness (Galileo PRS opzionale Phase B)
Single points of failure identificati:
SPOF-1: Single autopilot DAL-C primary (mitigation: 2oo3 voting)
SPOF-2: Single parachute system (mitigation: dual pyrotechnic + ballistic backup)
SPOF-3: Single SATCOM provider Iridium (mitigation: Inmarsat dual-provider Phase B)
Falsifying observation: se FTA dettagliato post-DOA mostra SPOF non mitigato
con P > 1E-4/h, design FCS richiede revisione prima del SAIL III approval.

## FTA_LossOfMission
FTA Top event: Loss of Mission EO
Metodologia: ARP4761 + NUREG-0492 + IEC 61025
Notazione: AND-gate richiede tutti gli eventi; OR-gate richiede almeno uno; cut set = combinazione minima eventi che causa top event
TOP EVENT: Loss of Mission EO (Percorso 6A pilota Pentema)
Target: P < 5% per missione (revenue impact)
Loss of Mission EO [TOP, OR-gate]
¦
+--OR--> Payload EO failure
¦ ¦
¦ +--Camera RGB failure P ~= 0.5% / mission
¦ +--AND--> RGB fail + IR fail P ~= 0.05% / mission
¦ +--Gimbal stuck off-target P ~= 1% / mission
¦ +--IR calibration lost critical P ~= 2% / mission
¦ Cut set probability: ~3% / mission
¦
+--OR--> Data downlink/storage failure
¦ ¦
¦ +--On-board storage corruption P ~= 0.5% / mission
¦ +--Downlink bandwidth congestion P ~= 1% / mission
¦ +--Cloud processing pipeline fail P ~= 1% / mission
¦ Cut set probability: ~2% / mission
¦
+--OR--> Operational mission abort
¦ ¦
¦ +--Weather degradation in flight P ~= 5% / mission (high)
¦ +--Lost-Link triggering RtB P ~= 1% / mission
¦ +--ATC restriction in-flight P ~= 1% / mission
¦ Cut set probability: ~7% / mission
¦
+--OR--> Quality below SLA
¦ ¦
¦ +--GSD insufficient P ~= 0.5% / mission
¦ +--Cloud cover > 30% area P ~= 5% / mission
¦ +--Image blur (vibration / motion) P ~= 1% / mission
¦ Cut set probability: ~6% / mission
¦
+--OR--> Permitting / regulatory abort
¦ ¦
¦ +--NOTAM not issued P ~= 0.5% / mission
¦ +--Geographical zone restriction last-min P ~= 0.5% / mission
¦ Cut set probability: ~1% / mission
Total Loss of Mission P (top event) ~= 15-20% / mission
Vs target 5%/mission: NON-CONFORME, needs:
- Weather planning + nowcasting integration (riduzione abort)
- Buffer mission re-scheduling
- Cloud cover prediction model
- SLA realistico con cliente PA (revisione target a 10-15%/mission)
SLA realistico: 80-85% mission success rate (15-20% abort/quality issue)
incluso buffer climatico Liguria + operational margins.
Falsifying observation: se actuals Y1 mostrano < 70% mission success
rate sostenuto, revisione modello operativo + cost structure.

## Mitigation_Plan
ID | Status | Score current | Score residual | Owner | Action ID | Action description | Deadline | Phase | Acceptance criterion
RSK-TEC-001 | Showstopper | 25 | 20 | propulsion-energy-engineer | RSK-TEC-001-A01 | Plan A obbligato E5 'Seasonal-only mar-ott' (~7 mesi). Plan B Y6+: migrazione SS Li 450 Wh/kg o PEM+LH2. Plan C: ridimensionamento R&D-only fino tech 2030+ | TBD per phase | Y3-Y5 (Phase B 6B) | Mitigation deployed + verified by gate review next
RSK-FIN-001 | Showstopper | 20 | 12 | financial-cfo + sovereign-strategist | RSK-FIN-001-A01 | Mix funding: EDF (DG DEFIS) + Horizon Europe + PNRR Aerospazio + Series B equity (CDP, EIB) | TBD per phase | Y2-Y3 (gate G5) | Mitigation deployed + verified by gate review next
RSK-FIN-001 | Showstopper | 20 | 12 | financial-cfo + sovereign-strategist | RSK-FIN-001-A02 | fasi graduali | TBD per phase | Y2-Y3 (gate G5) | Mitigation deployed + verified by gate review next
RSK-FIN-001 | Showstopper | 20 | 12 | financial-cfo + sovereign-strategist | RSK-FIN-001-A03 | partnership prime per cost sharing | TBD per phase | Y2-Y3 (gate G5) | Mitigation deployed + verified by gate review next
RSK-REG-001 | Showstopper | 20 | 16 | aviation-regulatory + sovereign-strategist | RSK-REG-001-A01 | Engagement EASA Innovation Network + consortium CIRA/TAS per Special Condition collettiva | TBD per phase | Y3-Y6 (Phase B/C) | Mitigation deployed + verified by gate review next
RSK-REG-001 | Showstopper | 20 | 16 | aviation-regulatory + sovereign-strategist | RSK-REG-001-A02 | partecipazione ASD-Eurospace HAPS WG | TBD per phase | Y3-Y6 (Phase B/C) | Mitigation deployed + verified by gate review next
RSK-REG-001 | Showstopper | 20 | 16 | aviation-regulatory + sovereign-strategist | RSK-REG-001-A03 | lobby DG MOVE/DG DEFIS | TBD per phase | Y3-Y6 (Phase B/C) | Mitigation deployed + verified by gate review next
RSK-HR-002 | Open-Critical | 16 | 9 | HR + CEO | RSK-HR-002-A01 | Headhunter specializzati | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-HR-002 | Open-Critical | 16 | 9 | HR + CEO | RSK-HR-002-A02 | contratti competitivi (180-220k EUR/anno per CISO senior) | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-HR-002 | Open-Critical | 16 | 9 | HR + CEO | RSK-HR-002-A03 | part-time fractional CISO/DPO M+0-6 | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-HR-002 | Open-Critical | 16 | 9 | HR + CEO | RSK-HR-002-A04 | partnership consulting Legal/Cyber | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-REG-008 | Open-High | 16 | 9 | aviation-regulatory + systems-engineer | RSK-REG-008-A01 | Partnership con DOA esistente (Leonardo, Tekever, AALTO) per Phase C | TBD per phase | Y5+ | Mitigation deployed + verified by gate review next
RSK-REG-008 | Open-High | 16 | 9 | aviation-regulatory + systems-engineer | RSK-REG-008-A02 | preparazione DOA Firmamento Y5+ | TBD per phase | Y5+ | Mitigation deployed + verified by gate review next
RSK-REG-018 | Open-Critical | 16 | 9 | avionics-gnc-engineer + aviation-regulatory | RSK-REG-018-A01 | Engagement EUROCONTROL precocemente (Y2-Y3) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-018 | Open-Critical | 16 | 9 | avionics-gnc-engineer + aviation-regulatory | RSK-REG-018-A02 | partecipazione workshop UAM/HAPS Network Manager | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-018 | Open-Critical | 16 | 9 | avionics-gnc-engineer + aviation-regulatory | RSK-REG-018-A03 | contributo definizione procedure | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-019 | Open-Critical | 16 | 9 | aviation-regulatory + CISO (new) | RSK-REG-019-A01 | Assunzione CISO entro M+6 | TBD per phase | Y1 (M+0 → M+12) urgente | Mitigation deployed + verified by gate review next
RSK-REG-019 | Open-Critical | 16 | 9 | aviation-regulatory + CISO (new) | RSK-REG-019-A02 | ISMS implementazione entro M+9 | TBD per phase | Y1 (M+0 → M+12) urgente | Mitigation deployed + verified by gate review next
RSK-REG-019 | Open-Critical | 16 | 9 | aviation-regulatory + CISO (new) | RSK-REG-019-A03 | certificazione ISO/IEC 27001 entro M+12 | TBD per phase | Y1 (M+0 → M+12) urgente | Mitigation deployed + verified by gate review next
RSK-REG-019 | Open-Critical | 16 | 9 | aviation-regulatory + CISO (new) | RSK-REG-019-A04 | audit interno + pre-audit ENAC | TBD per phase | Y1 (M+0 → M+12) urgente | Mitigation deployed + verified by gate review next
RSK-REG-021 | Open-Critical | 16 | 6 | data-privacy + IT + DPO | RSK-REG-021-A01 | Migrazione provider PSN-qualified (TIM Enterprise, Polo PSN, CDP Cloud) o cloud qualificato AgID (Aruba qualified, Engineering, Reply, Almaviva) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-021 | Open-Critical | 16 | 6 | data-privacy + IT + DPO | RSK-REG-021-A02 | audit AgID compliance | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-025 | Open-Critical | 16 | 9 | snai-funding + legal + business-model | RSK-REG-025-A01 | Pre-engagement Regione + accordo quadro (art.59 D.Lgs.36) | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REG-025 | Open-Critical | 16 | 9 | snai-funding + legal + business-model | RSK-REG-025-A02 | partnership Coopfond come veicolo non-gara | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REG-025 | Open-Critical | 16 | 9 | snai-funding + legal + business-model | RSK-REG-025-A03 | accordi di programma SNAI | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REG-025 | Open-Critical | 16 | 9 | snai-funding + legal + business-model | RSK-REG-025-A04 | gara con specificita tecniche Firmamento-friendly | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REG-027 | Open-Critical | 16 | 6 | CISO (new) + legal | RSK-REG-027-A01 | Registrazione preventiva ACN entro M+1 | M+0-1 | Y0+ immediato | Mitigation deployed + verified by gate review next
RSK-REG-027 | Open-Critical | 16 | 6 | CISO (new) + legal | RSK-REG-027-A02 | ISMS Part-IS allineato | M+0-1 | Y0+ immediato | Mitigation deployed + verified by gate review next
RSK-REG-027 | Open-Critical | 16 | 6 | CISO (new) + legal | RSK-REG-027-A03 | notifica incidenti 24h procedure | M+0-1 | Y0+ immediato | Mitigation deployed + verified by gate review next
RSK-REG-030 | Open-Critical | 16 | 9 | avionics + sovereign-strategist + aviation-regulatory | RSK-REG-030-A01 | Engagement ENAV precoce (Y2) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-030 | Open-Critical | 16 | 9 | avionics + sovereign-strategist + aviation-regulatory | RSK-REG-030-A02 | contributo definizione procedure standard EUROCONTROL | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-030 | Open-Critical | 16 | 9 | avionics + sovereign-strategist + aviation-regulatory | RSK-REG-030-A03 | testing spazio aereo segregato (Sardinia, GATB Apulia) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-003 | Open-High | 16 | 9 | propulsion-energy-engineer + supply-chain | RSK-SUP-003-A01 | Multi-vendor LiS pipeline (Oxis Energy heir, Lyten, NexTech) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-003 | Open-High | 16 | 9 | propulsion-energy-engineer + supply-chain | RSK-SUP-003-A02 | custom pack assembly con cell suppliers diversi | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-TEC-003 | Showstopper | 16 | 12 | aviation-regulatory + sovereign-strategist | RSK-TEC-003-A01 | Parallel approach: ops 6A genera revenue + esperienza mentre TC HALE matura. Engagement EASA Innovation Network + consortium CIRA/TAS per Special Condition collettiva | TBD per phase | Y4-Y8 | Mitigation deployed + verified by gate review next
RSK-TEC-016 | Open-Critical | 16 | 9 | propulsion-energy-engineer + telecom-ntn-payload-expert | RSK-TEC-016-A01 | NTN seasonal-only + payload pulse-mode duty-cycle < 30% + dedicated battery bank NTN | TBD per phase | Y4-Y5 | Mitigation deployed + verified by gate review next
RSK-FIN-004 | Open-Critical | 15 | 8 | financial-cfo | RSK-FIN-004-A01 | Aggiornamento Cap.8 OpEx Y1 con +450-800k EUR fixed cost | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-FIN-004 | Open-Critical | 15 | 8 | financial-cfo | RSK-FIN-004-A02 | revisione mix funding equity Series A | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-FIN-004 | Open-Critical | 15 | 8 | financial-cfo | RSK-FIN-004-A03 | cost sharing su CISO/DPO via partnership cooperative | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-TEC-002 | Showstopper | 15 | 8 | aero-structures-engineer | RSK-TEC-002-A01 | Aeroelastic analysis non-lineare (NASTRAN+ZAERO o MSC.Nastran SOL145) + GVT (Ground Vibration Test) + flight test subscale + winglet/passive damping design. Tilted spar caps + balance mass. | TBD per phase | Y3-Y4 (Phase B 6B) | Mitigation deployed + verified by gate review next
RSK-TEC-015 | Open-Critical | 15 | 12 | systems-engineer + propulsion-energy-engineer | RSK-TEC-015-A01 | Roadmap TRL puntuale per sottosistema + milestone trimestrali + partnership prime per acceleration TRL (DR-013 finding) | TBD per phase | Y3 (gate G5) | Mitigation deployed + verified by gate review next
RSK-FIN-005 | Open-High | 12 | 6 | financial-cfo + snai-funding | RSK-FIN-005-A01 | Bridge financing (banca + founder) | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-005 | Open-High | 12 | 6 | financial-cfo + snai-funding | RSK-FIN-005-A02 | pipeline grant multiple parallele | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-005 | Open-High | 12 | 6 | financial-cfo + snai-funding | RSK-FIN-005-A03 | flessibilita timeline progetto | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-006 | Open-High | 12 | 6 | financial-cfo | RSK-FIN-006-A01 | Pricing premium servizi + cost optimization OpEx | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-006 | Open-High | 12 | 6 | financial-cfo | RSK-FIN-006-A02 | renegotiate equity terms | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-006 | Open-High | 12 | 6 | financial-cfo | RSK-FIN-006-A03 | cost-shared infrastructure con cooperative | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-008 | Open-High | 12 | 6 | financial-cfo + business-model | RSK-FIN-008-A01 | Bridge financing Series A | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-008 | Open-High | 12 | 6 | financial-cfo + business-model | RSK-FIN-008-A02 | cost flex su FTE variable | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-008 | Open-High | 12 | 6 | financial-cfo + business-model | RSK-FIN-008-A03 | contratti pluriennali Regione anticipated payment | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-FIN-009 | Open-High | 12 | 6 | financial-cfo + CEO | RSK-FIN-009-A01 | Investor relations pipeline (CDP Venture, EIC Fund, BPER) | TBD per phase | Y2 | Mitigation deployed + verified by gate review next
RSK-FIN-009 | Open-High | 12 | 6 | financial-cfo + CEO | RSK-FIN-009-A02 | milestone-based bridge financing | TBD per phase | Y2 | Mitigation deployed + verified by gate review next
RSK-FIN-009 | Open-High | 12 | 6 | financial-cfo + CEO | RSK-FIN-009-A03 | alternative grant heavy mix | TBD per phase | Y2 | Mitigation deployed + verified by gate review next
RSK-GEO-001 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-001-A01 | [RESERVED] Linguaggio 'complementare IRIS2' | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-GEO-001 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-001-A02 | diversification supply | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-GEO-001 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-001-A03 | dialogo Atlantico NATO DIANA | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-GEO-001 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-001-A04 | avoid US dependency core | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-GEO-003 | Open-High | 12 | 6 | sovereign-strategist + supply-chain | RSK-GEO-003-A01 | [RESERVED] Supply chain mapping | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-GEO-003 | Open-High | 12 | 6 | sovereign-strategist + supply-chain | RSK-GEO-003-A02 | EU sovereign suppliers roadmap | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-GEO-003 | Open-High | 12 | 6 | sovereign-strategist + supply-chain | RSK-GEO-003-A03 | stock buffer | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-GEO-003 | Open-High | 12 | 6 | sovereign-strategist + supply-chain | RSK-GEO-003-A04 | EU CRMA Strategic Project | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-GEO-004 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-004-A01 | [RESERVED] Position paper complementarita | TBD per phase | Y2-Y4 | Mitigation deployed + verified by gate review next
RSK-GEO-004 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-004-A02 | engagement DG CNECT + DG DEFIS | TBD per phase | Y2-Y4 | Mitigation deployed + verified by gate review next
RSK-GEO-004 | Open-High | 12 | 6 | sovereign-strategist + CEO | RSK-GEO-004-A03 | joint workshop | TBD per phase | Y2-Y4 | Mitigation deployed + verified by gate review next
RSK-GEO-005 | Open-High | 12 | 6 | CEO + Board | RSK-GEO-005-A01 | [RESERVED] Capital structure resistente | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-GEO-005 | Open-High | 12 | 6 | CEO + Board | RSK-GEO-005-A02 | anchor investors non-ostili | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-GEO-005 | Open-High | 12 | 6 | CEO + Board | RSK-GEO-005-A03 | speed to value | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-GEO-005 | Open-High | 12 | 6 | CEO + Board | RSK-GEO-005-A04 | pluralismo cooperative | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-HR-001 | Open-High | 12 | 6 | HR + business-model | RSK-HR-001-A01 | Training in-house pilota junior | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-HR-001 | Open-High | 12 | 6 | HR + business-model | RSK-HR-001-A02 | partnership scuole UAS | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-HR-001 | Open-High | 12 | 6 | HR + business-model | RSK-HR-001-A03 | contratti competitivi + benefits cooperative | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-MKT-001 | Open-High | 12 | 9 | snai-funding + business-model | RSK-MKT-001-A01 | Anchor customer Regione + LoI pre-formale | TBD per phase | Y1-Y2 | Mitigation deployed + verified by gate review next
RSK-MKT-001 | Open-High | 12 | 9 | snai-funding + business-model | RSK-MKT-001-A02 | contratti pluriennali quadro | TBD per phase | Y1-Y2 | Mitigation deployed + verified by gate review next
RSK-MKT-001 | Open-High | 12 | 9 | snai-funding + business-model | RSK-MKT-001-A03 | partnership cooperative come veicolo di servizi | TBD per phase | Y1-Y2 | Mitigation deployed + verified by gate review next
RSK-MKT-002 | Open-High | 12 | 9 | competitive-intelligence + business-model | RSK-MKT-002-A01 | Differenziazione cooperativa + sovranita IT | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-002 | Open-High | 12 | 9 | competitive-intelligence + business-model | RSK-MKT-002-A02 | speed to market 6A | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-002 | Open-High | 12 | 9 | competitive-intelligence + business-model | RSK-MKT-002-A03 | partnership CIRA/POLITO | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-002 | Open-High | 12 | 9 | competitive-intelligence + business-model | RSK-MKT-002-A04 | lock-in cooperative Legacoop | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-004 | Open-High | 12 | 9 | business-model + financial-cfo | RSK-MKT-004-A01 | Bundle servizi multipli (EO+IR+NTN+monitoring) per economia scale | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-004 | Open-High | 12 | 9 | business-model + financial-cfo | RSK-MKT-004-A02 | cost-shared infrastruttura cooperative | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-004 | Open-High | 12 | 9 | business-model + financial-cfo | RSK-MKT-004-A03 | modello canone vs ore-volo | TBD per phase | Y1-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-005 | Open-High | 12 | 8 | business-model + sovereign-strategist | RSK-MKT-005-A01 | Espansione 2-3 regioni SNAI Y3 (Piemonte, Marche, Calabria, Basilicata) | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-005 | Open-High | 12 | 8 | business-model + sovereign-strategist | RSK-MKT-005-A02 | LoI pre-formalizzata multi-region | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-005 | Open-High | 12 | 8 | business-model + sovereign-strategist | RSK-MKT-005-A03 | contratti pluriennali con clausole continuita amministrative | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-OPS-003 | Open-High | 12 | 6 | HR + business-model | RSK-OPS-003-A01 | Training in-house pilota junior | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-003 | Open-High | 12 | 6 | HR + business-model | RSK-OPS-003-A02 | partnership con scuole UAS (es. Volandia, scuole Aero IT) | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-003 | Open-High | 12 | 6 | HR + business-model | RSK-OPS-003-A03 | contratti competitivi | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-015 | Monitor | 12 | 6 | aviation-regulatory + sovereign-strategist | RSK-REG-015-A01 | Focus Y1-Y3 su operazioni domestiche IT | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-015 | Monitor | 12 | 6 | aviation-regulatory + sovereign-strategist | RSK-REG-015-A02 | engagement EASA cross-border WG Y3+ | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-016 | Open-High | 12 | 6 | data-privacy-counsel + DPO | RSK-REG-016-A01 | Privacy by design hardware (blur on-board obbligatorio) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-016 | Open-High | 12 | 6 | data-privacy-counsel + DPO | RSK-REG-016-A02 | esclusione esplicita riconoscimento biometrico | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-016 | Open-High | 12 | 6 | data-privacy-counsel + DPO | RSK-REG-016-A03 | engagement Garante + AgID pre-clearance | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-016 | Open-High | 12 | 6 | data-privacy-counsel + DPO | RSK-REG-016-A04 | conformity assessment Notified Body se richiesto | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-026 | Open-High | 12 | 6 | financial-cfo + ops | RSK-REG-026-A01 | Tender con broker specializzati aviation (Marsh, Aon, Willis Italia) | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REG-026 | Open-High | 12 | 6 | financial-cfo + ops | RSK-REG-026-A02 | copertura RC+casco+cyber+privacy | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REG-026 | Open-High | 12 | 6 | financial-cfo + ops | RSK-REG-026-A03 | piano captive insurance Y3+ | M+0-3 | Y0+ | Mitigation deployed + verified by gate review next
RSK-REP-005 | Open-High | 12 | 6 | CEO + comms + sovereign-strategist | RSK-REP-005-A01 | Communication guidelines: 'complementare a IRIS2' SEMPRE | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-005 | Open-High | 12 | 6 | CEO + comms + sovereign-strategist | RSK-REP-005-A02 | mai 'vs Starlink' | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-005 | Open-High | 12 | 6 | CEO + comms + sovereign-strategist | RSK-REP-005-A03 | press training | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-005 | Open-High | 12 | 6 | CEO + comms + sovereign-strategist | RSK-REP-005-A04 | review pre-publication | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SUP-002 | Open-High | 12 | 6 | propulsion-energy-engineer + supply-chain | RSK-SUP-002-A01 | Azur Space (DE) qualification path | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-002 | Open-High | 12 | 6 | propulsion-energy-engineer + supply-chain | RSK-SUP-002-A02 | engagement Enel 3SUN (IT) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-002 | Open-High | 12 | 6 | propulsion-energy-engineer + supply-chain | RSK-SUP-002-A03 | EU CRMA Strategic Project status | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-TEC-012 | Open-High | 12 | 8 | avionics-gnc-engineer | RSK-TEC-012-A01 | Engagement early vendor EU (UAVOS, MicroPilot, Honeywell EU) | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-TEC-012 | Open-High | 12 | 8 | avionics-gnc-engineer | RSK-TEC-012-A02 | partnership con CIRA su FCS Italian sovereign | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-TEC-012 | Open-High | 12 | 8 | avionics-gnc-engineer | RSK-TEC-012-A03 | budget riservato 2-3M EUR R&D | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-TEC-018 | Open-High | 12 | 6 | earth-observation-expert | RSK-TEC-018-A01 | NUC (Non-Uniformity Correction) frequente + cross-check RGB + validation periodica vs ground truth (VVF, satellite) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-MKT-008 | Open-High | 10 | 8 | sovereign-strategist + CEO | RSK-MKT-008-A01 | Position paper 'Italian Stratospheric Sovereignty' Y1-Y2 | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-008 | Open-High | 10 | 8 | sovereign-strategist + CEO | RSK-MKT-008-A02 | engagement DG CNECT + DG DEFIS + SpaceRISE | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-MKT-008 | Open-High | 10 | 8 | sovereign-strategist + CEO | RSK-MKT-008-A03 | alternative narrative 'EU sovereign multi-layer' | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-OPS-002 | Open-Critical | 10 | 4 | aviation-regulatory + ops + safety | RSK-OPS-002-A01 | SORA M2 mitigation (parachute, flight termination) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-002 | Open-Critical | 10 | 4 | aviation-regulatory + ops + safety | RSK-OPS-002-A02 | GRC mitigation (geofence, Lost-Link) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-002 | Open-Critical | 10 | 4 | aviation-regulatory + ops + safety | RSK-OPS-002-A03 | assicurazione adeguata | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-002 | Open-Critical | 10 | 4 | aviation-regulatory + ops + safety | RSK-OPS-002-A04 | SOPs rigorosi | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-002 | Open-Critical | 10 | 4 | aviation-regulatory + ops + safety | RSK-OPS-002-A05 | training continuo | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-020 | Open-High | 10 | 4 | aviation-regulatory + ops + legal | RSK-REG-020-A01 | Assicurazione RC+casco BVLOS adeguata (>=5M EUR) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-020 | Open-High | 10 | 4 | aviation-regulatory + ops + legal | RSK-REG-020-A02 | D.Lgs.231 modello organizzativo | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-020 | Open-High | 10 | 4 | aviation-regulatory + ops + legal | RSK-REG-020-A03 | SOPs rigorosi | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-020 | Open-High | 10 | 4 | aviation-regulatory + ops + legal | RSK-REG-020-A04 | training PIC | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-020 | Open-High | 10 | 4 | aviation-regulatory + ops + legal | RSK-REG-020-A05 | safety reporting culture | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-001 | Open-Critical | 10 | 4 | CEO + comms | RSK-REP-001-A01 | Crisis communication plan | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-001 | Open-Critical | 10 | 4 | CEO + comms | RSK-REP-001-A02 | PR specialist on retainer | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-001 | Open-Critical | 10 | 4 | CEO + comms | RSK-REP-001-A03 | safety record positive + trasparenza | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-001 | Open-Critical | 10 | 4 | CEO + comms | RSK-REP-001-A04 | assicurazione legal protection + comms | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-TEC-008 | Open-High | 10 | 4 | propulsion-energy-engineer + safety | RSK-TEC-008-A01 | Cell-level fuse + intumescent barriers + BMS multi-sensor + hangar dedicato ATEX + assicurazione casco con clausola batteria | ongoing | Y1+ continuous | Mitigation deployed + verified by gate review next
RSK-FIN-003 | Open-High | 9 | 6 | financial-cfo + systems-engineer | RSK-FIN-003-A01 | Quotation parallel vendor multipli | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-FIN-003 | Open-High | 9 | 6 | financial-cfo + systems-engineer | RSK-FIN-003-A02 | contingency 20% in budget | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-FIN-003 | Open-High | 9 | 6 | financial-cfo + systems-engineer | RSK-FIN-003-A03 | scope reduction MVP se necessario | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-MKT-003 | Open-Medium | 9 | 6 | earth-observation-expert + business-model | RSK-MKT-003-A01 | Posizionamento high-resolution + low-latency vs Sentinel weekly + 10m | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-MKT-003 | Open-Medium | 9 | 6 | earth-observation-expert + business-model | RSK-MKT-003-A02 | servizi value-added analytics + report customized | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-MKT-006 | Open-Medium | 9 | 6 | business-model + Legacoop | RSK-MKT-006-A01 | Workshop cooperative Q+1 | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-MKT-006 | Open-Medium | 9 | 6 | business-model + Legacoop | RSK-MKT-006-A02 | valore proposto chiaro + canone accessibile | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-MKT-006 | Open-Medium | 9 | 6 | business-model + Legacoop | RSK-MKT-006-A03 | pilot gratuito M+0-3 | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-MKT-006 | Open-Medium | 9 | 6 | business-model + Legacoop | RSK-MKT-006-A04 | community engagement | TBD per phase | Y0-Y1 | Mitigation deployed + verified by gate review next
RSK-MKT-007 | Monitor | 9 | 6 | telecom-ntn-payload-expert + business-model | RSK-MKT-007-A01 | Servizi NTN target settori dedicated (emergency, IoT rurale) vs mass market | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-MKT-007 | Monitor | 9 | 6 | telecom-ntn-payload-expert + business-model | RSK-MKT-007-A02 | pricing capacity wholesale | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-OPS-001 | Open-High | 9 | 6 | vtol-uas-specialist + ops | RSK-OPS-001-A01 | Training pilota inverno | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-001 | Open-High | 9 | 6 | vtol-uas-specialist + ops | RSK-OPS-001-A02 | finestre operative meteo-dipendenti | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-001 | Open-High | 9 | 6 | vtol-uas-specialist + ops | RSK-OPS-001-A03 | de-icing batterie+celle | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-001 | Open-High | 9 | 6 | vtol-uas-specialist + ops | RSK-OPS-001-A04 | planning seasonal | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-004 | Open-Medium | 9 | 4 | vtol-uas-specialist + supply-chain | RSK-OPS-004-A01 | Order placement early M+3 | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-004 | Open-Medium | 9 | 4 | vtol-uas-specialist + supply-chain | RSK-OPS-004-A02 | stock spare parts | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-004 | Open-Medium | 9 | 4 | vtol-uas-specialist + supply-chain | RSK-OPS-004-A03 | rental option backup | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-005 | Open-Medium | 9 | 6 | ops + maintenance | RSK-OPS-005-A01 | Piano manutenzione preliminare | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-005 | Open-Medium | 9 | 6 | ops + maintenance | RSK-OPS-005-A02 | spare parts kit on-site | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-005 | Open-Medium | 9 | 6 | ops + maintenance | RSK-OPS-005-A03 | vendor support contract | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-005 | Open-Medium | 9 | 6 | ops + maintenance | RSK-OPS-005-A04 | secondo UAV backup Y2 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-006 | Monitor | 9 | 4 | ops + community-engagement | RSK-OPS-006-A01 | MoU PC Liguria + procedure attivazione 24/7 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-006 | Monitor | 9 | 4 | ops + community-engagement | RSK-OPS-006-A02 | training congiunto PC+Firmamento | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-006 | Monitor | 9 | 4 | ops + community-engagement | RSK-OPS-006-A03 | SLA contrattuale | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-009 | Monitor | 9 | 4 | HR + ops | RSK-OPS-009-A01 | Pianificazione hire Y2 (3-4 FTE ops) | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-OPS-009 | Monitor | 9 | 4 | HR + ops | RSK-OPS-009-A02 | training accelerato | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-OPS-009 | Monitor | 9 | 4 | HR + ops | RSK-OPS-009-A03 | tooling automazione operations management | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-PRV-006 | Monitor | 9 | 4 | data-privacy + systems-engineer | RSK-PRV-006-A01 | Engagement early NB | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-PRV-006 | Monitor | 9 | 4 | data-privacy + systems-engineer | RSK-PRV-006-A02 | pre-assessment documentazione | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-PRV-006 | Monitor | 9 | 4 | data-privacy + systems-engineer | RSK-PRV-006-A03 | design AI Act-compliant fin da concept | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-002 | Open-High | 9 | 6 | aviation-regulatory | RSK-REG-002-A01 | Pre-application meeting ENAC M+3-6 + M1 (operational mitigation) + M2 (technical mitigation, parachute + flight termination) | TBD per phase | Y1 (M+3-9) | Mitigation deployed + verified by gate review next
RSK-REG-003 | Monitor | 9 | 6 | telecom-ntn-payload-expert + aviation-regulatory | RSK-REG-003-A01 | Engagement AGCOM precoce (DR-005) | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-REG-003 | Monitor | 9 | 6 | telecom-ntn-payload-expert + aviation-regulatory | RSK-REG-003-A02 | domanda licenza sperimentale L1+L5 | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-REG-003 | Monitor | 9 | 6 | telecom-ntn-payload-expert + aviation-regulatory | RSK-REG-003-A03 | partecipazione consultazione ITU-R WP 5C | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-REG-009 | Monitor | 9 | 4 | systems-engineer + data-privacy | RSK-REG-009-A01 | Engagement early NB (TUV, IMQ, Bureau Veritas) | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-009 | Monitor | 9 | 4 | systems-engineer + data-privacy | RSK-REG-009-A02 | preparazione pre-assessment documentazione | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-013 | Open-High | 9 | 6 | aviation-regulatory + vtol-uas-specialist | RSK-REG-013-A01 | Engagement ENAV Genova ACC | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-013 | Open-High | 9 | 6 | aviation-regulatory + vtol-uas-specialist | RSK-REG-013-A02 | NOTAM dedicato per ogni missione | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-013 | Open-High | 9 | 6 | aviation-regulatory + vtol-uas-specialist | RSK-REG-013-A03 | coordinamento con CAA militare Mar Ligure | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-014 | Open-Medium | 9 | 4 | data-privacy-counsel | RSK-REG-014-A01 | Analisi precedenti Garante (DR-006) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-014 | Open-Medium | 9 | 4 | data-privacy-counsel | RSK-REG-014-A02 | DPIA conforme | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-014 | Open-Medium | 9 | 4 | data-privacy-counsel | RSK-REG-014-A03 | documentazione necessita/proporzionalita | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-022 | Open-Medium | 9 | 4 | propulsion-engineer + safety + ops | RSK-REG-022-A01 | Hangar dedicato con ventilazione anti-esplosione (LEL detection + emergency vent) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-022 | Open-Medium | 9 | 4 | propulsion-engineer + safety + ops | RSK-REG-022-A02 | procedure ATEX | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-022 | Open-Medium | 9 | 4 | propulsion-engineer + safety + ops | RSK-REG-022-A03 | formazione operatori | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-022 | Open-Medium | 9 | 4 | propulsion-engineer + safety + ops | RSK-REG-022-A04 | assicurazione adeguata | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-029 | Monitor | 9 | 4 | systems-engineer | RSK-REG-029-A01 | Design CE-compliant fin da concept | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-029 | Monitor | 9 | 4 | systems-engineer | RSK-REG-029-A02 | collaborazione con ente notificato | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-029 | Monitor | 9 | 4 | systems-engineer | RSK-REG-029-A03 | risk assessment + DoC | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REP-004 | Open-Medium | 9 | 4 | CEO + comms + sustainability | RSK-REP-004-A01 | LCA (Life Cycle Assessment) entro M+12 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-004 | Open-Medium | 9 | 4 | CEO + comms + sustainability | RSK-REP-004-A02 | claim ESG verificabili + report sostenibilita | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-004 | Open-Medium | 9 | 4 | CEO + comms + sustainability | RSK-REP-004-A03 | certification (B-Corp aspirazionale) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-004 | Monitor | 9 | 6 | CISO + supply-chain | RSK-SEC-004-A01 | SBOM (Software Bill of Materials) maintained | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-004 | Monitor | 9 | 6 | CISO + supply-chain | RSK-SEC-004-A02 | vendor security assessment | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-004 | Monitor | 9 | 6 | CISO + supply-chain | RSK-SEC-004-A03 | firmware signing | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-004 | Monitor | 9 | 6 | CISO + supply-chain | RSK-SEC-004-A04 | CVE monitoring continuous | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SUP-001 | Open-High | 9 | 6 | vtol-uas-specialist + supply-chain | RSK-SUP-001-A01 | Plan B Tekever (PT) pronto entro M+9 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SUP-001 | Open-High | 9 | 6 | vtol-uas-specialist + supply-chain | RSK-SUP-001-A02 | stock spare parts 12 mesi | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SUP-001 | Open-High | 9 | 6 | vtol-uas-specialist + supply-chain | RSK-SUP-001-A03 | valutazione Quantum (DE) terzo backup | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-TEC-004 | Open-High | 9 | 6 | systems-engineer | RSK-TEC-004-A01 | ICD rigoroso e validato pre-quotation | TBD per phase | Y1 (M+6 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-004 | Open-High | 9 | 6 | systems-engineer | RSK-TEC-004-A02 | test bed integrazione hardware-in-the-loop entro M+6 | TBD per phase | Y1 (M+6 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-004 | Open-High | 9 | 6 | systems-engineer | RSK-TEC-004-A03 | vendor compatibility matrix | TBD per phase | Y1 (M+6 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-010 | Open-High | 9 | 6 | avionics-gnc-engineer | RSK-TEC-010-A01 | Multi-constellation (GPS+Galileo+GLONASS+BeiDou) + RAIM + IMU dead-reckoning + opzione Galileo PRS Phase B | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-TEC-014 | Open-Medium | 9 | 4 | avionics-gnc-engineer | RSK-TEC-014-A01 | FPGA rad-tolerant (Microchip RTPolarFire o Xilinx Versal AI Edge) + 2oo3 voting + watchdog timer + memory ECC | TBD per phase | Y3-Y5 | Mitigation deployed + verified by gate review next
RSK-FIN-010 | Open-High | 8 | 6 | financial-cfo + risk | RSK-FIN-010-A01 | Tender broker + adeguamento periodico | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-FIN-010 | Open-High | 8 | 6 | financial-cfo + risk | RSK-FIN-010-A02 | captive insurance scenario Y3+ | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-GEO-002 | Monitor | 8 | 6 | sovereign-strategist + legal + CEO | RSK-GEO-002-A01 | [RESERVED] Engagement preventivo istituzioni | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-GEO-002 | Monitor | 8 | 6 | sovereign-strategist + legal + CEO | RSK-GEO-002-A02 | ownership stabile IT | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-GEO-002 | Monitor | 8 | 6 | sovereign-strategist + legal + CEO | RSK-GEO-002-A03 | notifica preventiva | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-GEO-002 | Monitor | 8 | 6 | sovereign-strategist + legal + CEO | RSK-GEO-002-A04 | compliance NIS2 | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-HR-003 | Open-High | 8 | 3 | CEO + HR | RSK-HR-003-A01 | Founder agreement con vesting + restrictive covenants | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-003 | Open-High | 8 | 3 | CEO + HR | RSK-HR-003-A02 | equity incentive plan team | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-003 | Open-High | 8 | 3 | CEO + HR | RSK-HR-003-A03 | succession planning | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-007 | Open-High | 8 | 6 | ops + business-model | RSK-OPS-007-A01 | Buffer giorni operativi piano | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-007 | Open-High | 8 | 6 | ops + business-model | RSK-OPS-007-A02 | UAV ricovero indoor | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-007 | Open-High | 8 | 6 | ops + business-model | RSK-OPS-007-A03 | servizi differiti accettati cliente PA | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-003 | Open-High | 8 | 3 | DPO + CISO | RSK-PRV-003-A01 | ISMS Part-IS + ISO 27001 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-003 | Open-High | 8 | 3 | DPO + CISO | RSK-PRV-003-A02 | crittografia at-rest + in-transit | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-003 | Open-High | 8 | 3 | DPO + CISO | RSK-PRV-003-A03 | incident response plan | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-003 | Open-High | 8 | 3 | DPO + CISO | RSK-PRV-003-A04 | assicurazione cyber | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-005 | Open-High | 8 | 3 | legal + ops | RSK-PRV-005-A01 | SLA realistici con buffer | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-005 | Open-High | 8 | 3 | legal + ops | RSK-PRV-005-A02 | assicurazione professional indemnity | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-005 | Open-High | 8 | 3 | legal + ops | RSK-PRV-005-A03 | ridondanza operativa | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-005 | Open-High | 8 | 3 | legal + ops | RSK-PRV-005-A04 | clausole force majeure | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-007 | Monitor | 8 | 3 | legal + IP counsel | RSK-PRV-007-A01 | Freedom-to-Operate analysis pre-Phase B | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-PRV-007 | Monitor | 8 | 3 | legal + IP counsel | RSK-PRV-007-A02 | patent portfolio Firmamento | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-PRV-007 | Monitor | 8 | 3 | legal + IP counsel | RSK-PRV-007-A03 | differenziazione design vs competitor | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-005 | Open-High | 8 | 3 | data-privacy-counsel + DPO | RSK-REG-005-A01 | DPIA pubblica + edge anonymization + consultazione preventiva Garante + geofence + retention policy stringente | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-010 | Open-High | 8 | 6 | supply-chain + sovereign-strategist | RSK-REG-010-A01 | Mapping componenti US-origin + EU sovereign alternatives roadmap (Azur Space, ACC, STM) + stock buffer 12 mesi | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-SEC-001 | Open-High | 8 | 3 | CISO (new) + IT | RSK-SEC-001-A01 | Zero-trust architecture | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-001 | Open-High | 8 | 3 | CISO (new) + IT | RSK-SEC-001-A02 | segregazione rete | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-001 | Open-High | 8 | 3 | CISO (new) + IT | RSK-SEC-001-A03 | NIS2 readiness + ISMS Part-IS | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-001 | Open-High | 8 | 3 | CISO (new) + IT | RSK-SEC-001-A04 | SOC managed service | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-001 | Open-High | 8 | 3 | CISO (new) + IT | RSK-SEC-001-A05 | ISO 27001 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-003 | Open-High | 8 | 3 | CISO + IT | RSK-SEC-003-A01 | Backup offsite 3-2-1 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-003 | Open-High | 8 | 3 | CISO + IT | RSK-SEC-003-A02 | immutable backups | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-003 | Open-High | 8 | 3 | CISO + IT | RSK-SEC-003-A03 | EDR su endpoint | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-003 | Open-High | 8 | 3 | CISO + IT | RSK-SEC-003-A04 | ZTNA su accessi remoti | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-003 | Open-High | 8 | 3 | CISO + IT | RSK-SEC-003-A05 | cyber insurance | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-007 | Monitor | 8 | 3 | CISO + sovereign-strategist | RSK-SEC-007-A01 | Multi-partner DOA option | TBD per phase | Y5+ | Mitigation deployed + verified by gate review next
RSK-SEC-007 | Monitor | 8 | 3 | CISO + sovereign-strategist | RSK-SEC-007-A02 | due diligence partner cybersecurity | TBD per phase | Y5+ | Mitigation deployed + verified by gate review next
RSK-SEC-007 | Monitor | 8 | 3 | CISO + sovereign-strategist | RSK-SEC-007-A03 | contract clauses continuity | TBD per phase | Y5+ | Mitigation deployed + verified by gate review next
RSK-SUP-004 | Open-High | 8 | 6 | avionics-gnc-engineer + supply-chain | RSK-SUP-004-A01 | STM (FR-IT) qualification path | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-004 | Open-High | 8 | 6 | avionics-gnc-engineer + supply-chain | RSK-SUP-004-A02 | engagement Leonardo Elettronica | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-004 | Open-High | 8 | 6 | avionics-gnc-engineer + supply-chain | RSK-SUP-004-A03 | dual sourcing US+EU | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-TEC-005 | Open-High | 8 | 4 | avionics-gnc-engineer + CISO (new) | RSK-TEC-005-A01 | Frequency hopping (FHSS) + crypto authentication AES-256 + multi-GNSS L1/L5 + dead-reckoning IMU fallback + Lost-Link procedure DAL-C | ongoing | Y1+ continuous | Mitigation deployed + verified by gate review next
RSK-TEC-006 | Open-High | 8 | 3 | data-privacy-counsel + DPO (new) | RSK-TEC-006-A01 | Edge anonymization (blur on-board obbligatorio) | TBD per phase | Y1 (M+0 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-006 | Open-High | 8 | 3 | data-privacy-counsel + DPO (new) | RSK-TEC-006-A02 | geofence aree residenziali | TBD per phase | Y1 (M+0 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-006 | Open-High | 8 | 3 | data-privacy-counsel + DPO (new) | RSK-TEC-006-A03 | DPIA preliminare entro M+6 | TBD per phase | Y1 (M+0 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-006 | Open-High | 8 | 3 | data-privacy-counsel + DPO (new) | RSK-TEC-006-A04 | consultazione preventiva Garante | TBD per phase | Y1 (M+0 → M+9) | Mitigation deployed + verified by gate review next
RSK-TEC-007 | Open-High | 8 | 3 | avionics-gnc-engineer | RSK-TEC-007-A01 | Lost-Link Profile documentato + Return-to-Base testato in flight test pre-deploy + procedura GS notifica + safety case ARP4761 | TBD per phase | Y1 (M+6) | Mitigation deployed + verified by gate review next
RSK-TEC-017 | Open-High | 8 | 3 | vtol-uas-specialist + ops | RSK-TEC-017-A01 | GS mobile ridondante + UPS GS fissa + SATCOM fallback + procedura RtB Lost-Link | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-FIN-007 | Monitor | 6 | 4 | financial-cfo + supply-chain | RSK-FIN-007-A01 | Hedging EUR/USD forward per acquisti CapEx | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-FIN-007 | Monitor | 6 | 4 | financial-cfo + supply-chain | RSK-FIN-007-A02 | quotation EUR-denominated vendor EU (Tekever, Quantum) come benchmark | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-HR-004 | Open-Medium | 6 | 4 | HR + CISO | RSK-HR-004-A01 | Training plan certificazioni (ISO 27001 LA, CISM, CISSP) | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-004 | Open-Medium | 6 | 4 | HR + CISO | RSK-HR-004-A02 | budget formazione 10k EUR/FTE/anno | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-004 | Open-Medium | 6 | 4 | HR + CISO | RSK-HR-004-A03 | e-learning piattaforma | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-005 | Monitor | 6 | 4 | HR + CEO | RSK-HR-005-A01 | GEP formalizzato | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-005 | Monitor | 6 | 4 | HR + CEO | RSK-HR-005-A02 | hire diversificato | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-005 | Monitor | 6 | 4 | HR + CEO | RSK-HR-005-A03 | partnership universita STEM women | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-HR-005 | Monitor | 6 | 4 | HR + CEO | RSK-HR-005-A04 | mentoring programma | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-MKT-009 | Monitor | 6 | 4 | business-model | RSK-MKT-009-A01 | Differenziazione service-only + cooperative + sovranita | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-MKT-009 | Monitor | 6 | 4 | business-model | RSK-MKT-009-A02 | bundling value-added analytics | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-MKT-009 | Monitor | 6 | 4 | business-model | RSK-MKT-009-A03 | vertical integration use cases SNAI | TBD per phase | Y2+ | Mitigation deployed + verified by gate review next
RSK-MKT-010 | Monitor | 6 | 4 | snai-funding | RSK-MKT-010-A01 | Diversificazione cliente PA (PC, Difesa civile, agricoltura) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-MKT-010 | Monitor | 6 | 4 | snai-funding | RSK-MKT-010-A02 | fondi Horizon + INTERREG | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-OPS-008 | Open-Medium | 6 | 2 | community-engagement + ops | RSK-OPS-008-A01 | Workshop comunita pre-deploy M+6 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-008 | Open-Medium | 6 | 2 | community-engagement + ops | RSK-OPS-008-A02 | canone partecipazione + benefit locali | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-008 | Open-Medium | 6 | 2 | community-engagement + ops | RSK-OPS-008-A03 | trasparenza operazioni | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-008 | Open-Medium | 6 | 2 | community-engagement + ops | RSK-OPS-008-A04 | finestre orarie | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-010 | Monitor | 6 | 4 | earth-observation-expert + IT | RSK-OPS-010-A01 | Edge processing UAV + cloud parallel | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-010 | Monitor | 6 | 4 | earth-observation-expert + IT | RSK-OPS-010-A02 | ottimizzazione pipeline | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-010 | Monitor | 6 | 4 | earth-observation-expert + IT | RSK-OPS-010-A03 | SLA realistico con cliente | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-011 | Open-Medium | 6 | 2 | safety + HR | RSK-OPS-011-A01 | DUVRI formalizzato M+3 | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-011 | Open-Medium | 6 | 2 | safety + HR | RSK-OPS-011-A02 | formazione D.Lgs.81 obbligatoria | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-011 | Open-Medium | 6 | 2 | safety + HR | RSK-OPS-011-A03 | PPE adeguati | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-011 | Open-Medium | 6 | 2 | safety + HR | RSK-OPS-011-A04 | medical surveillance | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-OPS-012 | Open-Medium | 6 | 2 | ops + community | RSK-OPS-012-A01 | Survey siti alternativi Torriglia/Casella | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-012 | Open-Medium | 6 | 2 | ops + community | RSK-OPS-012-A02 | container temporaneo | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-OPS-012 | Open-Medium | 6 | 2 | ops + community | RSK-OPS-012-A03 | partnership cooperative locali per spazi | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-PRV-001 | Open-Medium | 6 | 2 | data-privacy-counsel + DPO | RSK-PRV-001-A01 | Privacy by design fin da concept | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-PRV-001 | Open-Medium | 6 | 2 | data-privacy-counsel + DPO | RSK-PRV-001-A02 | edge anonymization | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-PRV-001 | Open-Medium | 6 | 2 | data-privacy-counsel + DPO | RSK-PRV-001-A03 | geofence aree residenziali | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-PRV-001 | Open-Medium | 6 | 2 | data-privacy-counsel + DPO | RSK-PRV-001-A04 | DPIA consultazione preventiva Garante | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-PRV-002 | Open-Medium | 6 | 2 | data-privacy-counsel + legal | RSK-PRV-002-A01 | Trasparenza operazioni | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-002 | Open-Medium | 6 | 2 | data-privacy-counsel + legal | RSK-PRV-002-A02 | consenso preventivo proprietari grandi appezzamenti | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-002 | Open-Medium | 6 | 2 | data-privacy-counsel + legal | RSK-PRV-002-A03 | assicurazione legal protection | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-002 | Open-Medium | 6 | 2 | data-privacy-counsel + legal | RSK-PRV-002-A04 | mediation community | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-004 | Monitor | 6 | 2 | legal + business-model | RSK-PRV-004-A01 | Accordo cooperativa formalizzato + statuto chiaro | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-004 | Monitor | 6 | 2 | legal + business-model | RSK-PRV-004-A02 | arbitrato Legacoop | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-PRV-004 | Monitor | 6 | 2 | legal + business-model | RSK-PRV-004-A03 | comunicazione trasparente | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-004 | Monitor | 6 | 4 | aviation-regulatory | RSK-REG-004-A01 | Engagement ENAC U-Space tavolo nazionale | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-004 | Monitor | 6 | 4 | aviation-regulatory | RSK-REG-004-A02 | partecipazione D-Flight pilot Pentema | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-004 | Monitor | 6 | 4 | aviation-regulatory | RSK-REG-004-A03 | SORA fallback continua | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-006 | Monitor | 6 | 3 | aviation-regulatory | RSK-REG-006-A01 | Verifica D-Flight pre-mission | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-006 | Monitor | 6 | 3 | aviation-regulatory | RSK-REG-006-A02 | coordinamento Ente Parco Antola | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-006 | Monitor | 6 | 3 | aviation-regulatory | RSK-REG-006-A03 | NOTAM dedicato | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-006 | Monitor | 6 | 3 | aviation-regulatory | RSK-REG-006-A04 | finestre temporali | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-007 | Open-Medium | 6 | 4 | aviation-regulatory | RSK-REG-007-A01 | SORA documentation SORA 2.5 compliant fin da prima applicazione | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-007 | Open-Medium | 6 | 4 | aviation-regulatory | RSK-REG-007-A02 | consulenza ENAC pre-app | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-012 | Monitor | 6 | 4 | aviation-regulatory | RSK-REG-012-A01 | Monitoring NPA EASA | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-012 | Monitor | 6 | 4 | aviation-regulatory | RSK-REG-012-A02 | partecipazione consultation | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-012 | Monitor | 6 | 4 | aviation-regulatory | RSK-REG-012-A03 | flessibilita design | TBD per phase | Y2-Y3 | Mitigation deployed + verified by gate review next
RSK-REG-017 | Monitor | 6 | 4 | sovereign-strategist | RSK-REG-017-A01 | Engagement EUSPA via CASSINI accelerator | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-017 | Monitor | 6 | 4 | sovereign-strategist | RSK-REG-017-A02 | workshop downstream services HAPS | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-017 | Monitor | 6 | 4 | sovereign-strategist | RSK-REG-017-A03 | mapping intersezione GOVSATCOM | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-023 | Monitor | 6 | 4 | systems-engineer + supply-chain | RSK-REG-023-A01 | Verifica DoC ogni componente BoM | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-023 | Monitor | 6 | 4 | systems-engineer + supply-chain | RSK-REG-023-A02 | audit RoHS pre-deployment | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-023 | Monitor | 6 | 4 | systems-engineer + supply-chain | RSK-REG-023-A03 | sostituzione componenti non-compliant | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-024 | Monitor | 6 | 2 | regulatory + community + ops | RSK-REG-024-A01 | Mappa aree militari/sensibili Liguria | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-024 | Monitor | 6 | 2 | regulatory + community + ops | RSK-REG-024-A02 | consenso proprietari grandi appezzamenti | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-024 | Monitor | 6 | 2 | regulatory + community + ops | RSK-REG-024-A03 | NOTAM coordinato | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-024 | Monitor | 6 | 2 | regulatory + community + ops | RSK-REG-024-A04 | engagement comunita Pentema | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REG-028 | Monitor | 6 | 2 | sovereign-strategist + CASD | RSK-REG-028-A01 | Y1 usare GNSS standard L1/L5 + Galileo open service + anti-spoofing software-based | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REG-028 | Monitor | 6 | 2 | sovereign-strategist + CASD | RSK-REG-028-A02 | engagement CASD solo se dual-use Fase 3+ | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-REP-002 | Open-Medium | 6 | 2 | community-engagement + CEO | RSK-REP-002-A01 | Engagement comunita continuo + benefit locali | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-002 | Open-Medium | 6 | 2 | community-engagement + CEO | RSK-REP-002-A02 | mediazione Comune Torriglia + ENTE Parco | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-002 | Open-Medium | 6 | 2 | community-engagement + CEO | RSK-REP-002-A03 | community advisory board | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-003 | Monitor | 6 | 2 | business-model + Legacoop | RSK-REP-003-A01 | Trasparenza governance | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-003 | Monitor | 6 | 2 | business-model + Legacoop | RSK-REP-003-A02 | mediazione Legacoop | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-REP-003 | Monitor | 6 | 2 | business-model + Legacoop | RSK-REP-003-A03 | comunicazione one-voice | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-005 | Monitor | 6 | 2 | CISO + HR | RSK-SEC-005-A01 | RBAC + least privilege | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-005 | Monitor | 6 | 2 | CISO + HR | RSK-SEC-005-A02 | DLP solution | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-005 | Monitor | 6 | 2 | CISO + HR | RSK-SEC-005-A03 | background check personale critico | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-005 | Monitor | 6 | 2 | CISO + HR | RSK-SEC-005-A04 | offboarding procedure | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-006 | Monitor | 6 | 2 | CISO + telecom-ntn | RSK-SEC-006-A01 | DDoS protection upstream provider (Cloudflare, Akamai) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SEC-006 | Monitor | 6 | 2 | CISO + telecom-ntn | RSK-SEC-006-A02 | rate limiting | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SEC-006 | Monitor | 6 | 2 | CISO + telecom-ntn | RSK-SEC-006-A03 | geo-blocking | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-005 | Monitor | 6 | 4 | avionics-gnc-engineer + supply-chain | RSK-SUP-005-A01 | Xilinx Versal AI Edge alternative | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-005 | Monitor | 6 | 4 | avionics-gnc-engineer + supply-chain | RSK-SUP-005-A02 | stock buffer 24 mesi | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-005 | Monitor | 6 | 4 | avionics-gnc-engineer + supply-chain | RSK-SUP-005-A03 | design flessibile FPGA-vendor agnostic | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-006 | Monitor | 6 | 4 | aero-structures-engineer + supply-chain | RSK-SUP-006-A01 | Solvay (BE) qualification + Italian carbon producers (Mapei, Saati) + stock 12 mesi | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-007 | Monitor | 6 | 4 | aero-structures-engineer + supply-chain | RSK-SUP-007-A01 | Multi-vendor lino IT (Linificio Canapificio Nazionale, Biogear partner) | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-007 | Monitor | 6 | 4 | aero-structures-engineer + supply-chain | RSK-SUP-007-A02 | test qualifica panel | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-SUP-007 | Monitor | 6 | 4 | aero-structures-engineer + supply-chain | RSK-SUP-007-A03 | backup vendor BE/NL | TBD per phase | Y3+ | Mitigation deployed + verified by gate review next
RSK-TEC-009 | Open-Medium | 6 | 4 | aero-structures-engineer | RSK-TEC-009-A01 | Lino solo in strutture secondarie con coating idrorepellente | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-TEC-009 | Open-Medium | 6 | 4 | aero-structures-engineer | RSK-TEC-009-A02 | longherone primario CFRP | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-TEC-009 | Open-Medium | 6 | 4 | aero-structures-engineer | RSK-TEC-009-A03 | LCA + qualification path posticipato | TBD per phase | Y3-Y4 | Mitigation deployed + verified by gate review next
RSK-TEC-011 | Monitor | 6 | 4 | propulsion-energy-engineer | RSK-TEC-011-A01 | Margine design 30% su energy budget | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-TEC-011 | Monitor | 6 | 4 | propulsion-energy-engineer | RSK-TEC-011-A02 | cell qualification per ambiente stratosferico | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-TEC-011 | Monitor | 6 | 4 | propulsion-energy-engineer | RSK-TEC-011-A03 | vendor Spectrolab/Azur Space datasheet flight heritage | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-TEC-013 | Monitor | 6 | 2 | telecom-ntn-payload-expert | RSK-TEC-013-A01 | Adaptive coding modulation (ACM) + site diversity gateway Ka-band + buffer queue + scheduled re-transmission | TBD per phase | Y4+ | Mitigation deployed + verified by gate review next
RSK-SEC-002 | Open-High | 5 | 4 | CISO + avionics-gnc-engineer | RSK-SEC-002-A01 | Crypto authentication AES-256 + mutual TLS | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-002 | Open-High | 5 | 4 | CISO + avionics-gnc-engineer | RSK-SEC-002-A02 | rolling keys | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-002 | Open-High | 5 | 4 | CISO + avionics-gnc-engineer | RSK-SEC-002-A03 | flight termination automatica su anomaly | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-SEC-002 | Open-High | 5 | 4 | CISO + avionics-gnc-engineer | RSK-SEC-002-A04 | air-gap FCS critical | M+0-12 + ongoing | Y1+ | Mitigation deployed + verified by gate review next
RSK-FIN-002 | Open-Medium | 4 | 4 | financial-cfo + snai-funding | RSK-FIN-002-A01 | Alternative funding (FESR Liguria, bandi tematici Horizon, equity seed) | TBD per phase | Y0 | Mitigation deployed + verified by gate review next
RSK-FIN-002 | Open-Medium | 4 | 4 | financial-cfo + snai-funding | RSK-FIN-002-A02 | bridge financing founder | TBD per phase | Y0 | Mitigation deployed + verified by gate review next
RSK-REG-011 | Monitor | 4 | 2 | environmental + ops | RSK-REG-011-A01 | VIA preliminare M+6 | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-011 | Monitor | 4 | 2 | environmental + ops | RSK-REG-011-A02 | coordinamento con Ente Parco Antola | M+3-12 | Y1 | Mitigation deployed + verified by gate review next
RSK-REG-011 | Monitor | 4 | 2 | environmental + ops | RSK-REG-011-A03 | design infrastruttura minimale + reversibile | M+3-12 | Y1 | Mitigation deployed + verified by gate review next

## Residual_Risk_Matrix
P x I Residual Risk Matrix (post-mitigation)
Rows = Impact (5 top - 1 bottom) ¦ Cols = Probability (1 left - 5 right)
I \ P | P=1 | P=2 | P=3 | P=4 | P=5
I=5 | 0 - | 0 - | 0 - | 0 - | 0 -
I=4 | 6 RSK-TEC-005 RSK-TEC-008 RSK-REG-020 RSK-OPS-002 RSK-SEC-002 RSK-REP-001 | 4 RSK-TEC-002 RSK-TEC-012 RSK-MKT-005 RSK-MKT-008 | 2 RSK-TEC-015 RSK-FIN-001 | 1 RSK-REG-001 | 1 RSK-TEC-001
I=3 | 12 RSK-TEC-006 RSK-TEC-007 RSK-TEC-017 RSK-REG-005 RSK-REG-006 RSK-PRV-003 | 28 RSK-TEC-004 RSK-TEC-010 RSK-TEC-018 RSK-REG-002 RSK-REG-003 RSK-REG-010 | 11 RSK-TEC-016 RSK-REG-008 RSK-REG-018 RSK-REG-019 RSK-REG-025 RSK-REG-030 | 1 RSK-TEC-003 | 0 -
I=2 | 14 RSK-TEC-013 RSK-REG-011 RSK-REG-024 RSK-REG-028 RSK-OPS-008 RSK-OPS-011 | 27 RSK-TEC-009 RSK-TEC-011 RSK-TEC-014 RSK-REG-004 RSK-REG-007 RSK-REG-009 | 8 RSK-REG-015 RSK-REG-026 RSK-FIN-005 RSK-FIN-010 RSK-MKT-007 RSK-OPS-003 | 1 RSK-FIN-004 | 0 -
I=1 | 0 - | 0 - | 0 - | 0 - | 0 -
Statistiche residual risk
RED (>=15) residual: 2
YELLOW (8-14) residual: 19
GREEN (<8) residual: 95
Totale: 116
Statistiche pre-mitigation (baseline)
RED (>=15) baseline: 17
YELLOW (8-14) baseline: 66
GREEN (<8) baseline: 33
Reduzione RED: 17 -> 2 (88% reduction)
Mitigation effectiveness: 75% of RED+YELLOW reduced

## EWI
Early Warning Indicators - Top-25 Risks
Monitoraggio quarterly (default); rischi RED monthly. Owner = funzione responsabile.
RSK-ID | EWI Indicatore | Frequenza monitoring | Threshold trigger | Owner
RSK-TEC-001 | Sim energy balance update mensile | Monthly + quarterly review | Sim allegato A.7 deficit > 50% giorni | propulsion-energy-engineer
RSK-TEC-002 | Aeroelastic FEA subscale | Trimestrale | Flutter speed < 1.3x Vd | aero-structures-engineer
RSK-TEC-003 | EASA RMT HAPS calendar | Trimestrale | RMT non aperto entro Y3 | aviation-regulatory
RSK-TEC-004 | Test bench HIL | Mensile | Mismatch ICD > 2 critical | systems-engineer
RSK-TEC-005 | GPS interference EASA bulletin | Settimanale | Eventi jamming Mar Ligure > 3/mese | avionics-gnc-engineer
RSK-TEC-008 | Battery thermal events sector | Mensile | Recall cella o vendor incident | propulsion-energy-engineer
RSK-REG-001 | EASA RMT HAPS published | Trimestrale | RMT non in workplan 2026-28 | aviation-regulatory
RSK-REG-002 | ENAC SAIL pre-app feedback | Mensile | SAIL > III determination | aviation-regulatory
RSK-REG-018 | EUROCONTROL HAPS workplan | Semestrale | HAPS procedure absent | avionics-gnc-engineer
RSK-REG-019 | CISO hire + ISMS gap analysis | Mensile | CISO non hired entro M+6 | aviation-regulatory + CISO
RSK-REG-020 | Settore UAS BVLOS incidents | Mensile | Incidente grave settore IT | ops + safety
RSK-REG-021 | AgID PSN qualifica list | Trimestrale | Cloud Aruba non qualificato | data-privacy + IT
RSK-REG-025 | Procedura affidamento Regione | Mensile | Avvio gara competitor incluso | snai-funding + legal
RSK-REG-027 | ACN classification notice | Mensile | Firmamento classificata essenziale | CISO + legal
RSK-REG-030 | ENAV procedure FL400+ pubbl. | Trimestrale | Procedure absent al Y3 | avionics + sovereign
RSK-FIN-001 | Pipeline Phase B funding | Mensile | Commitment < 30% al gate G5 | financial-cfo
RSK-FIN-004 | FTE hire pipeline regulatory | Settimanale | 3 ruoli senior non riempiti M+9 | HR + CFO
RSK-MKT-001 | Contratti Regione Liguria pipeline | Mensile | Tempo cycle > 18 mesi | snai-funding
RSK-MKT-002 | AALTO-Leonardo JV announcements | Mensile | Annuncio JV o pilota multi-regione | competitive-intelligence
RSK-MKT-005 | Cambio amministrazione Regione | Annuale + eventi | Elezioni 2025+ | sovereign-strategist + business
RSK-OPS-001 | Giorni op. inverno Pentema | Mensile | < 60% giorni op. piano inverno | vtol-uas-specialist
RSK-OPS-002 | Near-miss + incident reports | Settimanale | Near-miss vs aviazione manned | ops + safety
RSK-SUP-001 | USA BIS notices + tariffe USA-CN | Settimanale | Restrizioni HAPS-related | supply-chain + sovereign
RSK-SEC-001 | SIEM alerts + ACN threat intel | Settimanale | Intrusion detected o ACN sector alert | CISO
RSK-HR-002 | Hire pipeline CISO+DPO+RegAff | Settimanale | Tempo hire > 6 mesi | HR + CEO
RSK-REP-001 | Settore drone incidents IT/EU | Mensile | Incidente coverage stampa nazionale | CEO + comms

## Audit_Trail
Audit Trail - Risk Register versioning
Versione | Data | Modifica | Autore | Note
v0.1 | 2026-03-15 | Stesura iniziale top-10 Cap. 6.4 | risk-register-builder skill | Top-10 + FMECA Payload preliminari
v0.2 | 2026-04-10 | Aggiunta 5 showstopper Cap. 10 §10.2 | risk-register-builder skill | RSK-FIN-001 + ridondanza RSK-TEC-003 vs RSK-REG-001
v0.3 | 2026-05-01 | Aggiunta 5 RSK-GEO da RESERVED (reference, no detail) | sovereign-strategist | Geopolitical risks formalmente trackati
v0.4 | 2026-05-10 | Aggiunta 15 RSK-REG-016..030 da Cap. 5 §5.16 audit Regulatory Adversary | regulatory-adversary audit | Showstopper regolatori non coperti pre-audit
v1.0 | 2026-05-17 | Consolidamento Allegato A.2 + FMECA + FTA + EWI + Mitigation Plan | senior risk manager + safety engineer | Risk Register completo v1.0 per gate M+3
Prossimo aggiornamento previsto
v1.1 | 2026-08-17 (M+6) | Post gate G3 (M+10) review + chiusura RSK-FIN-001/REG-001 update | risk-register-builder + steering | Trigger: gate G3 outcomes + EWI quarterly review